## %Cost vs Budget
Partner | Used of Budget
GOT | 20.4981
MNU | 29.3344
SCA | 22.228
FOC | 23.3291
CLTV | 15.3444
MAI | 10.4211
BIN | 7.6098
IOC | 6.7957
HIE | 22.4682
BAL | 45.7808
MEERI | 23.914
MCN | 11.2897
CKR | 33.1177

## WP Cost vs Budget
Task/WP | TOTAL COST | TOTAL BUDGET
WP1 | 107552.1769 | 226991.17
T1.1 | 41951.0537 | 88440.74
T1.2 | 30527.424 | 53116.01
T1.3 | 31448.3898 | 85434.42
Task/WP | TOTAL COST | TOTAL BUDGET
WP2 | 67975.2659 | 153493.81
T2.1 | 19638.1337 | 67887.51
T2.2 | 5204.3416 | 3343.75
T2.3 | 10843.0419 | 12525
T2.4 | 32340.6592 | 69737.55
Task/WP | TOTAL COST | TOTAL BUDGET
WP3 | 84518.5147 | 434125.12
T3.1 | 47272.4947 | 68475.03
T3.2 | 14726.0428 | 18562.5
T3.3 | 15885.025 | 121637.57
T3.4 | 0 | 26750
T3.5 | 0 | 26750
T3.6 | 6187.5 | 171950.02
Task/WP | TOTAL COST | TOTAL BUDGET
WP4 | 21952.6033 | 700689.32
T4.1 | 8347.2261 | 24218.75
T4.2 | 5371.85 | 169499.08
T4.3 | 326.75 | 113875.05
T4.4 | 0 | 70268.81
T4.5 | 359.9075 | 114196.76
T4.6 | 230.555 | 6925
T4.7 | 798.075 | 54018.33
T4.8 | 595.1947 | 53087.47
T4.9 | 5748.05 | 94600.07
Task/WP | TOTAL COST | TOTAL BUDGET
WP5 | 42546.3243 | 148095.23
T5.1 | 40961.1874 | 55221.35
T5.2 | 771.5 | 55221.35
T5.3 | 796.2062 | 37652.53
Task/WP | TOTAL COST | TOTAL BUDGET
WP6 | 56508.9497 | 231218.95
T6.1 | 39463.0925 | 55825.06
T6.2 | 10860.0632 | 108168.84
T6.3 | 1066.5956 | 67225.05
Task/WP | TOTAL COST | TOTAL BUDGET
WP7 | 116025.3313 | 214000
T7.1 | 42675.2639 | 147125
T7.2 | 50402.5615 | 46812.5
T7.3 | 22855.6075 | 20062.5

## Direct &Indirect Personnal Cost
ALL DIRECT & INDIRECT COST CALCULATIONS PER PARTNER
TOTAL BUDGET IS NOT EQUAL TO EC CONTRIBUTION DUE TO THE SME PARTNERS
70%.
GreenOfshoreTech TOTAL (Period M1 to M9) | Task/ WP | TOTAL COST | Other Dir. Cost Budget | TOTAL BUDGET | % spend | MNU COST | Other Dir. Cost Budget | MNU BUDGET | % spend | SCA COST | Other Dir. Cost Budget | SCA BUDGET | % spend | FOC COST | Other Dir. Cost Budget | FOC BUDGET | % spend | CTLV COST | Other Dir. Cost Budget | CTLV BUDGET | % spend | MAI COST | Other Dir. Cost | MAI BUDGET | % spend | BIN COST | Other Dir. Cost | BIN BUDGET | % spend | IOC COST | Other Dir. Cost | IOC BUDGET | % spend | HIE COST | Other Dir. Cost | HIE BUDGET | % spend | BAL COST | Other Dir. Cost | BAL BUDGET | % spend | MEERI COST | Other Dir. Cost | MEERI BUDGET | % spend | MCN COST | Other Dir. Cost | MCN BUDGET | % spend | CKR COST | Other Dir. Cost | CKR BUDGET | % spend
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ODC | 0 |  | 343929 | 0 | 0 |  | 39500 | 0 | 0 |  | 20750 | 0 | 0 |  | 42500 | 0 | 0 |  | 20750 | 0 | 0 |  | 20750 | 0 | 0 |  | 56429 | 0 | 0 |  | 20750 | 0 | 5763.75 |  | 20750 | 27.7771 | 0 |  | 20750 | 0 | 0 |  | 20750 | 0 | 0 |  | 39500 | 0 | 0 |  | 20750 | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 107552.1769 | 31600 | 226991.17 | 47.3817 | 8024.875 | 31600 | 20062.5 | 39.9994 | 13497.1651 | 0 | 11712.46 | 115.2377 | 1875.625 | 0 | 7790.62 | 24.0754 | 6823.4177 | 0 | 10546.88 | 64.6961 | 12627.3375 | 0 | 31484.38 | 40.1067 | 16250.9219 | 0 | 36562.5 | 44.447 | 2402.5312 | 0 | 17306.54 | 13.8822 | 12255.2459 | 0 | 23906.25 | 51.2638 | 13402.8875 | 0 | 12375 | 108.3062 | 8319.05 | 0 | 13406.25 | 62.0535 | 7696.99 | 0 | 10312.5 | 74.6375 | 4376.13 | 0 | 14218.75 | 30.7772
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 41951.0537 | 31600 | 88440.74 | 47.4341 | 3265.9375 | 31600 | 13375 | 24.4182 | 6648.4552 |  | 5856.22 | 113.5281 | 780.13 |  | 3462.5 | 22.5308 | 508.6807 |  | 4687.5 | 10.8519 | 0 |  | 2421.88 | 0 | 3222.6188 |  | 2812.5 | 114.582 | 310.5312 |  | 11537.57 | 2.6915 | 11586.2678 |  | 18593.75 | 62.3127 | 7215.3875 |  | 6187.5 | 116.6123 | 307.44 |  | 0 | #DIV/0! | 6508.745 |  | 6875 | 94.6727 | 1596.86 |  | 1093.75 | 145.9986
Assessment of emerging technology trends and solutions | T1.2 | 30527.424 | 0 | 53116.01 | 57.4731 | 1399.6875 |  | 3343.75 | 41.8598 | 3484.4313 |  | 2928.12 | 118.9989 | 194.2 |  | 865.62 | 22.4348 | 2541.4263 |  | 1171.88 | 216.8675 | 5070.8375 |  | 9687.5 | 52.3441 | 7450.025 |  | 11250 | 66.2224 | 1470.9375 |  | 2884.57 | 50.9933 | 411.6788 |  | 2656.25 | 15.4985 | 3093.75 |  | 3093.75 | 100 | 4060.45 |  | 6256.25 | 64.9023 | 0 |  | 1718.75 | 0 | 1350 |  | 4375 | 30.8571
Potential new value chains and selection of Call Topics | T1.3 | 31448.3898 | 0 | 85434.42 | 36.81 | 3359.25 |  | 3343.75 | 100.4636 | 3364.2785 |  | 2928.12 | 114.8955 | 526.17 |  | 3462.5 | 15.1962 | 3773.3108 |  | 4687.5 | 80.4973 | 7556.5 |  | 19375 | 39.0013 | 2328.0938 |  | 22500 | 10.3471 | 621.0625 |  | 2884.4 | 21.5318 | 257.2993 |  | 2656.25 | 9.6866 | 3093.75 |  | 3093.75 | 100 | 3951.16 |  | 7150 | 55.261 | 1188.245 |  | 1718.75 | 69.1343 | 1429.27 |  | 8750 | 16.3345
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 67975.2659 | 0 | 153493.81 | 44.2853 | 5346.8063 | 0 | 6687.5 | 79.9522 | 3123.9729 | 0 | 5856.22 | 53.3445 | 174.2875 | 0 | 8656.24 | 2.0134 | 3711.9305 | 0 | 11718.76 | 31.6751 | 0 | 0 | 4843.76 | 0 | 816.875 | 0 | 5625 | 14.5222 | 555.6875 | 0 | 5768.79 | 9.6327 | 15281.059 | 0 | 37187.5 | 41.0919 | 30049.1875 | 0 | 47406.25 | 63.3866 | 1776.61 | 0 | 1787.5 | 99.3908 | 565.24 | 0 | 3437.5 | 16.4433 | 6573.6097 | 0 | 8750 | 75.127
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 19638.1337 | 0 | 67887.51 | 28.9275 | 1306.375 |  | 3343.75 | 39.0692 | 40.0509 |  | 2928.1 | 1.3678 | 0 |  | 4328.12 | 0 | 1816.2619 |  | 5859.38 | 30.9975 | 0 |  | 2421.88 | 0 | 163.375 |  | 2812.5 | 5.8089 | 0 |  | 2884.39 | 0 | 14637.8109 |  | 34531.25 | 42.39 | 0 |  | 0 | #DIV/0! | 1115.02 |  | 893.75 | 124.7575 | 559.24 |  | 1718.75 | 32.5376 | 0 |  | 3281.25 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 5204.3416 | 0 | 3343.75 | 155.6439 | 4040.4313 |  | 3343.75 | 120.8353 | 520.6622 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 643.2482 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Establishment of a Survey tool | T2.3 | 10843.0419 | 0 | 12525 | 86.5712 | 0 |  | 0 | #DIV/0! | 1321.6809 |  | 0 | #DIV/0! | 139.43 |  | 3462.5 | 4.0269 | 1895.6686 |  | 4687.5 | 40.4409 | 0 |  | 0 | #DIV/0! | 245.0625 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 661.59 |  | 0 | #DIV/0! | 6 |  | 0 | #DIV/0! | 6573.61 |  | 4375 | 150.2539
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 32340.6592 | 0 | 69737.55 | 46.3748 | 0 |  | 0 | #DIV/0! | 1241.579 |  | 2928.12 | 42.4019 | 0 |  | 865.62 | 0 | 249.1427 |  | 1171.88 | 21.2601 | 0 |  | 2421.88 | 0 | 245.0625 |  | 2812.5 | 8.7133 | 555.6875 |  | 2884.4 | 19.2653 | 0 |  | 2656.25 | 0 | 30049.1875 |  | 47406.25 | 63.3866 | 0 |  | 893.75 | 0 | 0 |  | 1718.75 | 0 | 0 |  | 1093.75 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 84518.5147 | 91428.57 | 434125.12 | 19.4687 | 1306.375 | 0 | 94375 | 1.3842 | 11374.4655 | 8000 | 52706.11 | 21.5809 | 2002.375 | 8000 | 8656.25 | 23.1321 | 962.4105 | 8000 | 16406.25 | 5.8661 | 0 | 8000 | 33906.25 | 0 | 1705.2656 | 11428.57 | 39375 | 4.3308 | 1307.5 | 8000 | 28843.88 | 4.533 | 6539.2514 | 8000 | 26562.5 | 24.6184 | 34570.4875 | 8000 | 48500 | 71.2794 | 2131.5 | 8000 | 12512.5 | 17.035 | 2898.055 | 8000 | 17187.5 | 16.8614 | 19720.8291 | 8000 | 26250 | 75.127
Preparation of the Call for Proposals | T3.1 | 47272.4947 | 19000 | 68475.03 | 69.0361 | 559.875 | 0 | 6687.5 | 8.372 | 10613.4978 | 1000 | 5856.22 | 181.2346 | 1601.9 | 2000 | 1731.25 | 92.5285 | 962.4105 | 1000 | 2343.75 | 41.0628 | 0 | 1000 | 4843.75 | 0 | 816.875 | 2000 | 5625 | 14.5222 | 1046 | 2000 | 5768.78 | 18.1321 | 1628.0514 | 2000 | 5312.5 | 30.6457 | 6187.5 | 1000 | 6187.5 | 100 | 2131.5 | 2000 | 1787.5 | 119.2448 | 2004.055 | 2000 | 3437.5 | 58.2998 | 19720.83 | 3000 | 13125 | 150.2539
Publication of the Call for Proposals and Proposal reception. | T3.2 | 14726.0428 | 2000 | 18562.5 | 79.3322 | 466.5625 | 0 | 6687.5 | 6.9766 | 760.9678 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 841.4125 |  | 0 | #DIV/0! | 261.5 |  | 0 | #DIV/0! | 4911.2 |  | 0 | #DIV/0! | 7484.4 | 2000 | 11875 | 63.0265 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Evaluation and Selection of SMEs Proposals | T3.3 | 15885.025 | 33000 | 121637.57 | 13.0593 | 279.9375 | 0 | 13750 | 2.0359 | 0 | 2000 | 11712.47 | 0 | 0 | 3000 | 3462.5 | 0 | 0 | 3000 | 4687.5 | 0 | 0 | 3000 | 9687.5 | 0 | 0 | 5000 | 11250 | 0 | 0 | 3000 | 11537.55 | 0 | 0 | 3000 | 10625 | 0 | 14711.0875 | 3000 | 18562.5 | 79.2516 | 0 | 3000 | 3575 | 0 | 894 | 3000 | 6875 | 13.0036 | 0 | 2000 | 4375 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 26750 | 0 | 0 | 0 | 26750 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 26750 | 0 | 0 | 0 | 26750 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Technical monitoring of winner SMEs Projects | T3.6 | 6187.5 | 37428.57 | 171950.02 | 3.5984 | 0 | 0 | 13750 | 0 | 0 | 5000 | 35137.42 | 0 | 0 | 3000 | 3462.5 | 0 | 0 | 4000 | 9375 | 0 | 0 | 4000 | 19375 | 0 | 0 | 4428.57 | 22500 | 0 | 0 | 3000 | 11537.55 | 0 | 0 | 3000 | 10625 | 0 | 6187.5 | 2000 | 11875 | 52.1053 | 0 | 3000 | 7150 | 0 | 0 | 3000 | 6875 | 0 | 0 | 3000 | 8750 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 21952.6033 | 151514.29 | 700689.32 | 3.133 | 6681.175 | 0 | 72511.5 | 9.214 | 2723.4636 | 8000 | 149334.17 | 1.8237 | 58.1 | 26000 | 29431.25 | 0.19741 | 595.1947 | 8600 | 32812.5 | 1.8139 | 4120.2875 | 8600 | 77500 | 5.3165 | 816.875 | 33714.29 | 101250 | 0.80679 | 0 | 8600 | 34612.7 | 0 | 0 | 8600 | 74374.5 | 0 | 5126.7875 | 8600 | 30937.5 | 16.5714 | 661.59 | 8600 | 8937.5 | 7.4024 | 1169.13 | 23600 | 41250 | 2.8343 | 0 | 8600 | 13125 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 8347.2261 | 1000 | 24218.75 | 34.466 | 933.125 | 0 | 0 | #DIV/0! | 2403.0561 |  | 0 | #DIV/0! | 46.48 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 4120.2875 | 1000 | 24218.75 | 17.0128 | 81.6875 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 661.59 |  | 0 | #DIV/0! | 101 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Business Support Service #1 Business & Tech Academy | T4.2 | 5371.85 | 44600 | 169499.08 | 3.1693 | 0 | 0 | 12324 | 0 | 0 | 1000 | 11712.46 | 0 | 0 | 5000 | 3462.5 | 0 | 0 | 2000 | 4687.5 | 0 | 0 | 5000 | 29062.5 | 0 | 245.0625 | 10000 | 39375 | 0.62238 | 0 | 3000 | 11537.56 | 0 | 0 | 1000 | 10625 | 0 | 5126.7875 | 4600 | 18562.5 | 27.6191 | 0 | 6000 | 5362.5 | 0 | 0 | 5000 | 6875 | 0 | 0 | 2000 | 4375 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 326.75 | 34100 | 113875.05 | 0.28694 | 0 | 0 | 6687.5 | 0 | 0 | 1000 | 5856.24 | 0 | 0 | 10000 | 13850 | 0 | 0 | 2000 | 2343.75 | 0 | 0 | 500 | 9687.5 | 0 | 326.75 | 10000 | 45000 | 0.72611 | 0 | 1500 | 5768.78 | 0 | 0 | 1000 | 5312.5 | 0 | 0 | 2000 | 6187.5 | 0 | 0 | 1600 | 1787.5 | 0 | 0 | 2500 | 3437.5 | 0 | 0 | 2000 | 2187.5 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 10700 | 70268.81 | 0 | 0 | 0 | 6687.5 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 1731.25 | 0 | 0 |  | 2343.75 | 0 | 0 | 100 | 4843.75 | 0 | 0 | 4000 | 5625 | 0 | 0 | 1500 | 5768.78 | 0 | 0 | 2600 | 31875 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 | 2500 | 3437.5 | 0 | 0 |  | 2187.5 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 359.9075 | 6000 | 114196.76 | 0.31516 | 0 | 0 | 0 | #DIV/0! | 320.4075 | 6000 | 114196.76 | 0.28057 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 39.5 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Business Support Service #5 Branding | T4.6 | 230.555 | 4000 | 6925 | 3.3293 | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 | 4000 | 6925 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 230.555 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Business Support Service #6 Internationalisation | T4.7 | 798.075 | 19800 | 54018.33 | 1.4774 | 0 | 0 | 6687.5 | 0 | 0 |  | 0 | #DIV/0! | 0 | 3000 | 1731.25 | 0 | 0 | 1000 | 2343.75 | 0 | 0 | 1000 | 4843.75 | 0 | 0 | 4000 | 5625 | 0 | 0 | 1800 | 5768.79 | 0 | 0 | 1000 | 5312 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 798.075 | 6000 | 13750 | 5.8042 | 0 | 2000 | 2187.5 | 0
Business Support Service #7 Investor pitching | T4.8 | 595.1947 | 5000 | 53087.47 | 1.1212 | 0 | 0 | 6687.5 | 0 | 0 |  | 11712.47 | 0 | 0 |  | 0 | #DIV/0! | 595.1947 | 3000 | 18750 | 3.1744 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 | 2000 | 15937.5 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Business Support Service #8 Investor rounds | T4.9 | 5748.05 | 26314.29 | 94600.07 | 6.0762 | 5748.05 | 0 | 33437.5 | 17.1904 | 0 |  | 5856.24 | 0 | 0 | 4000 | 1731.25 | 0 | 0 | 600 | 2343.75 | 0 | 0 | 1000 | 4843.75 | 0 | 0 | 5714.29 | 5625 | 0 | 0 | 800 | 5768.79 | 0 | 0 | 1000 | 5312.5 | 0 | 0 | 2000 | 6187.5 | 0 | 0 | 1000 | 1787.5 | 0 | 0 | 7600 | 13750 | 0 | 0 | 2600 | 2187.5 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 42546.3243 | 0 | 148095.23 | 28.729 | 4189.7313 | 0 | 10331.25 | 40.554 | 33402.4798 | 0 | 70274.73 | 47.5313 | 87.15 | 0 | 2596.86 | 3.356 | 700.0901 | 0 | 3515.64 | 19.9136 | 0 | 0 | 7265.64 | 0 | 0 | 0 | 8436 | 0 | 359.5625 | 0 | 8653.18 | 4.1553 | 0 | 0 | 7968.75 | 0 | 0 | 0 | 9281.25 | 0 | 1742.07 | 0 | 2681.25 | 64.9723 | 1627 | 0 | 5156.25 | 31.5539 | 438.2406 | 0 | 3281.25 | 13.3559
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 40961.1874 | 0 | 55221.35 | 74.1764 | 2874.025 |  | 3443.75 | 83.4563 | 33402.4798 |  | 29281.19 | 114.0749 | 69.72 |  | 865.62 | 8.0543 | 700.0901 |  | 1171.88 | 59.7408 | 0 |  | 2421.88 | 0 | 0 |  | 2812 | 0 | 359.5625 |  | 2884.39 | 12.4658 | 0 |  | 2656.25 | 0 | 0 |  | 3093.75 | 0 | 1742.07 |  | 893.75 | 194.9169 | 1375 |  | 1718.75 | 80 | 438.24 |  | 1093.75 | 40.0677
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 771.5 | 0 | 55221.35 | 1.3971 | 746.5 |  | 3443.75 | 21.677 | 0 |  | 29281.19 | 0 | 0 |  | 865.62 | 0 | 0 |  | 1171.88 | 0 | 0 |  | 2421.88 | 0 | 0 |  | 2812 | 0 | 0 |  | 2884.39 | 0 | 0 |  | 2656.25 | 0 | 0 |  | 3093.75 | 0 | 0 |  | 893.75 | 0 | 25 |  | 1718.75 | 1.4545 | 0 |  | 1093.75 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 796.2062 | 0 | 37652.53 | 2.1146 | 569.2062 |  | 3443.75 | 16.5287 | 0 |  | 11712.35 | 0 | 0 |  | 865.62 | 0 | 0 |  | 1171.88 | 0 | 0 |  | 2421.88 | 0 | 0 |  | 2812 | 0 | 0 |  | 2884.4 | 0 | 0 |  | 2656.25 | 0 | 0 |  | 3093.75 | 0 | 0 |  | 893.75 | 0 | 227 |  | 1718.75 | 13.2073 | 0 |  | 1093.75 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 56508.9497 | 0 | 231218.95 | 24.4396 | 8425.1856 | 0 | 26750 | 31.496 | 5847.4365 | 0 | 11712.44 | 49.925 | 25103.8625 | 0 | 25968.75 | 96.6695 | 3337.7579 | 0 | 9375 | 35.6028 | 4596 | 0 | 29062.5 | 15.8142 | 510.5469 | 0 | 22500 | 2.2691 | 4821.4062 | 0 | 23075.13 | 20.8944 | 2261.1825 | 0 | 21250 | 10.6409 | 0 | 0 | 12375 | 0 | 590.43 | 0 | 3575 | 16.5155 | 620.725 | 0 | 13750 | 4.5144 | 394.4166 | 0 | 8750 | 4.5076
Communication plan and Communication activities | T6.1 | 39463.0925 | 0 | 55825.06 | 70.6906 | 6531.875 |  | 6687.5 | 97.6729 | 4886.2141 |  | 0 | #DIV/0! | 16847.5 |  | 13850 | 121.6426 | 459.2447 |  | 2343.75 | 19.5944 | 4596 |  | 4843.75 | 94.8852 | 408.4375 |  | 5625 | 7.2611 | 4821.4062 |  | 5768.78 | 83.5776 | 0 |  | 5312.5 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 514.315 |  | 3437.5 | 14.9619 | 398.1 |  | 2187.5 | 18.1989
Dissemination strategy and Dissemination activities | T6.2 | 10860.0632 | 0 | 108168.84 | 10.0399 | 933.125 |  | 13375 | 6.9766 | 961.2224 |  | 5856.22 | 16.4137 | 3235.59 |  | 10387.5 | 31.1489 | 2878.5132 |  | 4687.5 | 61.4083 | 0 |  | 9687.5 | 0 | 0 |  | 11250 | 0 | 0 |  | 11537.56 | 0 | 2261.1825 |  | 10625 | 21.2817 | 0 |  | 6187.5 | 0 | 590.43 |  | 1787.5 | 33.031 | 0 |  | 6875 | 0 | 0 |  | 4375 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 1066.5956 | 0 | 67225.05 | 1.5866 | 960.1856 |  | 6687.5 | 14.3579 | 0 |  | 5856.22 | 0 | 0 |  | 1731.25 | 0 | 0 |  | 2343.75 | 0 | 0 |  | 14531.25 | 0 | 0 |  | 5625 | 0 | 0 |  | 5768.79 | 0 | 0 |  | 5312.5 | 0 | 0 |  | 6187.5 | 0 | 0 |  | 1787.5 | 0 | 106.41 |  | 3437.5 | 3.0956 | 0 |  | 2187.5 | 0
Project Management and Coordination | WP7 | 116025.3313 | 0 | 214000 | 54.2174 | 108068.0056 | 0 | 214000 | 50.4991 | 1682.1393 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 459.4922 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 5531.9342 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 283.76 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Project coordination | T7.1 | 42675.2639 | 0 | 147125 | 29.0061 | 37674.9219 |  | 147125 | 25.6074 | 240.3056 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 4760.0364 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Project administration & Financial Management | T7.2 | 50402.5615 | 0 | 46812.5 | 107.669 | 48909.7469 |  | 46812.5 | 104.4801 | 720.9168 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 771.8978 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Quality Assurance | T7.3 | 22855.6075 | 0 | 20062.5 | 113.922 | 21483.3369 |  | 20062.5 | 107.0821 | 720.9168 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 367.5938 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 283.76 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
TOTAL |  | 502725.6785 | 274542.86 | 2452542.6 | 20.4981 | 142042.1538 | 31600 | 484217.75 | 29.3344 | 71651.1227 | 16000 | 322346.13 | 22.228 | 29301.4 | 34000 | 125599.97 | 23.3291 | 16130.8013 | 16600 | 105125.03 | 15.3444 | 21343.625 | 16600 | 204812.53 | 10.4211 | 20559.9766 | 45142.86 | 270177.5 | 7.6098 | 9446.6875 | 16600 | 139010.22 | 6.7957 | 47632.4232 | 16600 | 211999.5 | 22.4682 | 83149.35 | 16600 | 181625 | 45.7808 | 15221.25 | 16600 | 63650 | 23.914 | 14743.6624 | 31600 | 130593.75 | 11.2897 | 31503.2261 | 16600 | 95125 | 33.1177
FOC
BAL
MCN
HIE
IOC
MAI
CTLV
MNU
SCA
MEERI
CKR
BIN
TOTAL
All Direct & Indirect Cost (EUR)
ACTUAL & BUDGET

## MNU
TOTAL COSTS
Dir & Indir (EUR)
ACTUAL
GreenOfshoreTech MNU (Period M1 to M10) | Task/ | M1-M10
WP
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC)
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 8024.875
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 3265.9375
Assessment of emerging technology trends and solutions | T1.2 | 1399.6875 | Budget rate |  | Actual |  |  | 1PM iequals to | 143.333
Potential new value chains and selection of Call Topics | T1.3 | 3359.25 | Project manager |  | Project manager
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 5346.8063 | hrs | Salery rate | hrs | Salery rate
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1306.375 |  | 74.65 |  | 82
Establishment of a Collaborative Virtual Environment | T2.2 | 4040.4313 | 86 | 6419.9 | 0 | 0 | PM | 0.6
Establishment of a Survey tool | T2.3 | 0 | 35 | 2612.75 | 0 | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 15 | 1119.75 | 0 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 1306.375 | 36 | 2687.4 | 0 | 0
Preparation of the Call for Proposals | T3.1 | 559.875 | 57.3 | 4277.445 |  | 0 | PM | 0.4
Publication of the Call for Proposals and Proposal reception. | T3.2 | 466.5625 | 14 | 1045.1 | 0 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 279.9375 | 43.3 | 3232.345 | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 14 | 1045.1 | 0 | 0 | PM | 0.1
Business Support Services to winner SMEs (preparation) | WP4 | 6681.175 | 6 | 447.9 | 0 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 933.125 | 5 | 373.25 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 3 | 223.95 | 0 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 | 0 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 0 | 0 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | 0 | 0 | 0
Business Support Service #5 Branding | T4.6 | 0 | 71.6 | 5344.94 |  | 0 | PM | 0.5
Business Support Service #6 Internationalisation | T4.7 | 0 | 10 | 746.5 | 0 | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0 | 0 | 0
Business Support Service #8 Investor rounds | T4.9 | 5748.05 | 0 | 0 | 0 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 4189.7313 | 0 | 0 | 0 | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 2874.025 | 0 | 0 | 0 | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 746.5 | 0 | 0 | 0 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 569.2062 | 0 | 0 | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 8425.1856 | 0 | 0 | 0 | 0
Communication plan and Communication activities | T6.1 | 6531.875 | 61.6 | 4598.44 | 0 | 0
Dissemination strategy and Dissemination activities | T6.2 | 933.125 | 44.9 | 3351.785 |  | 0 | PM | 0.31
Exploitation strategy, IPR and Sustainability | T6.3 | 960.1856 | 30.8 | 2299.22 | 0 | 0
Project Management and Coordination | WP7 | 108068.0056 | 8 | 597.2 | 0 | 0
Project coordination | T7.1 | 37674.9219 | 6.1 | 455.365 | 0 | 0
Project administration & Financial Management | T7.2 | 48909.7469 | 90.29 | 6740.1485 |  | 0 | PM | 0.63
Quality Assurance | T7.3 | 21483.3369 | 70 | 5225.5 | 0 | 0
TOTAL |  | 142042.1538 | 10 | 746.5 | 0 | 0
|  |  | 10.29 | 768.1485 | 0 | 0
|  |  | 1158.13 | 86454.4045 |  | 0 | PM | 8.08
|  |  | 403.75 | 30139.9375 | 0 | 0
|  |  | 524.15 | 39127.7975 | 0 | 0
|  |  | 230.23 | 17186.6695 | 0 | 0
|  |  | 1522.22 | 113633.723 | 0 | 0 | PM | 10.62

## SCA
TOTAL COSTS
10797.74 |  | Dir & Indir (EUR)
ACTUAL
SCABERIA AS | Task/ | M1-M9
WP
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ALL | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 13497.1651
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 6648.4552
Assessment of emerging technology trends and solutions | T1.2 | 3484.4313
Potential new value chains and selection of Call Topics | T1.3 | 3364.2785
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 3123.9729
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 40.0509
Establishment of a Collaborative Virtual Environment | T2.2 | 520.6622
Establishment of a Survey tool | T2.3 | 1321.6809
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 1241.579
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 11374.4655
Preparation of the Call for Proposals | T3.1 | 10613.4978
Publication of the Call for Proposals and Proposal reception. | T3.2 | 760.9678
Evaluation and Selection of SMEs Proposals | T3.3 | 0
Contracting with winner SMEs Projects | T3.4 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 2723.4636
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 2403.0561
Business Support Service #1 Business & Tech Academy | T4.2 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0
Business Support Service #3 Access to Finance | T4.4 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 320.4075
Business Support Service #5 Branding | T4.6 | 0
Business Support Service #6 Internationalisation | T4.7 | 0
Business Support Service #7 Investor pitching | T4.8 | 0
Business Support Service #8 Investor rounds | T4.9 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 33402.4798
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 33402.4798
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 5847.4365
Communication plan and Communication activities | T6.1 | 4886.2141
Dissemination strategy and Dissemination activities | T6.2 | 961.2224
Exploitation strategy, IPR and Sustainability | T6.3 | 0
Project Management and Coordination | WP7 | 1682.1393
Project coordination | T7.1 | 240.3056
Project administration & Financial Management | T7.2 | 720.9168
Quality Assurance | T7.3 | 720.9168
71651.1227

## FOC
TOTAL COSTS
Indir & DIR (EUR)
ACTUAL
GreenOffshoreTech - FÓRUM OCEANO | Task/ | M1-M9
WP
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ALL | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 1875.625
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 780.13
Assessment of emerging technology trends and solutions | T1.2 | 194.2
Potential new value chains and selection of Call Topics | T1.3 | 526.17
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 174.2875
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0
Establishment of a Survey tool | T2.3 | 139.43
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 2002.375
Preparation of the Call for Proposals | T3.1 | 1601.9
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 0
Contracting with winner SMEs Projects | T3.4 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 58.1
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 46.48
Business Support Service #1 Business & Tech Academy | T4.2 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0
Business Support Service #3 Access to Finance | T4.4 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0
Business Support Service #5 Branding | T4.6 | 0
Business Support Service #6 Internationalisation | T4.7 | 0
Business Support Service #7 Investor pitching | T4.8 | 0
Business Support Service #8 Investor rounds | T4.9 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 87.15
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 69.72
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 25103.8625
Communication plan and Communication activities | T6.1 | 16847.5
Dissemination strategy and Dissemination activities | T6.2 | 3235.59
Exploitation strategy, IPR and Sustainability | T6.3 | 0
Project Management and Coordination | WP7 | 0
Project coordination | T7.1 | 0
Project administration & Financial Management | T7.2 | 0
Quality Assurance | T7.3 | 0
TOTAL |  | 29301.4

## CLTV
|  | TOTAL COSTS | TOTAL COSTS
|  | DIR | Indir & DIR
|  | ACTUAL | ACTUAL
GreenOfshoreTech PARTNER NAME | Task/ | M1-M9 | M1-M9
WP
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ALL | 0 | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 5458.7342 | 6823.4177
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 406.9445 | 508.6807
Assessment of emerging technology trends and solutions | T1.2 | 2033.141 | 2541.4263
Potential new value chains and selection of Call Topics | T1.3 | 3018.6486 | 3773.3108
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 2969.5444 | 3711.9305
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1453.0095 | 1816.2619
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0
Establishment of a Survey tool | T2.3 | 1516.5348 | 1895.6686
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 199.3141 | 249.1427
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 769.9284 | 962.4105
Preparation of the Call for Proposals | T3.1 | 769.9284 | 962.4105
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 476.1557 | 595.1947
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0 | 0
Business Support Service #7 Investor pitching | T4.8 | 476.1557 | 595.1947
Business Support Service #8 Investor rounds | T4.9 | 0 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 560.0721 | 700.0901
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 560.0721 | 700.0901
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 2670.2063 | 3337.7579
Communication plan and Communication activities | T6.1 | 367.3957 | 459.2447
Dissemination strategy and Dissemination activities | T6.2 | 2302.8105 | 2878.5132
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0
Project Management and Coordination | WP7 | 0 | 0
Project coordination | T7.1 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0
Quality Assurance | T7.3 | 0 | 0
TOTAL |  | 12904.6411 | 16130.8013

## MAI
TOTAL COSTS
Dir & Indir (EUR)
ACTUAL
MAI Carbon | Task/ | M1-M8
WP
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ALL | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 12627.3375
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 0
Assessment of emerging technology trends and solutions | T1.2 | 5070.8375
Potential new value chains and selection of Call Topics | T1.3 | 7556.5
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 0
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0
Establishment of a Survey tool | T2.3 | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 0
Preparation of the Call for Proposals | T3.1 | 0
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 0
Contracting with winner SMEs Projects | T3.4 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 4120.2875
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 4120.2875
Business Support Service #1 Business & Tech Academy | T4.2 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0
Business Support Service #3 Access to Finance | T4.4 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0
Business Support Service #5 Branding | T4.6 | 0
Business Support Service #6 Internationalisation | T4.7 | 0
Business Support Service #7 Investor pitching | T4.8 | 0
Business Support Service #8 Investor rounds | T4.9 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 4596
Communication plan and Communication activities | T6.1 | 4596
Dissemination strategy and Dissemination activities | T6.2 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0
Project Management and Coordination | WP7 | 0
Project coordination | T7.1 | 0
Project administration & Financial Management | T7.2 | 0
Quality Assurance | T7.3 | 0
TOTAL |  | 21343.625

## BIN
TOTAL COSTS
|  | Dir & Indir (EUR) | Ind. Costs flat rate |  |  | 25%
|  | ACTUAL | Project manager |  | Assistant
GreenOfshoreTech BIN (Periode1, 09/21-06/22) | Task/ | M1-M9 | hrs | Salery rate | hrs | Salery rate
| WP |  |  | 65.35 |  | 50.11
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ALL | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 16250.9219 | 146.5 | 11967.2188 | 16.5 | 1033.5187
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 3222.6188 | 36 | 2940.75 | 4.5 | 281.8687
Assessment of emerging technology trends and solutions | T1.2 | 7450.025 | 82 | 6698.375 | 12 | 751.65
Potential new value chains and selection of Call Topics | T1.3 | 2328.0938 | 28.5 | 2328.0938 | 0 | 0
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 816.875 | 8 | 653.5 |  | 0
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 163.375 | 2 | 163.375 | 0 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 | 0 | 0
Establishment of a Survey tool | T2.3 | 245.0625 | 3 | 245.0625 | 0 | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 245.0625 | 3 | 245.0625 | 0 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 1705.2656 | 18 | 1470.375 | 3 | 187.9125
Preparation of the Call for Proposals | T3.1 | 816.875 | 10 | 816.875 | 0 | 0
Publication of the Call for Proposals and Proposal reception. | T3.2 | 841.4125 | 8 | 653.5 | 3 | 187.9125
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0 | 0 | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 | 0 | 0 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 816.875 | 8 | 653.5 |  | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 81.6875 | 1 | 81.6875 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 245.0625 | 3 | 245.0625 | 0 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 326.75 | 4 | 326.75 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 0 | 0 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | 0 | 0 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0 | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 | 0 | 0 | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0 | 0 | 0
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 | 0 | 0 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0 | 0 | 0 |  | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0 | 0 | 0 | 0 | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 | 0 | 0 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 | 0 | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 510.5469 | 5 | 408.4375 |  | 0
Communication plan and Communication activities | T6.1 | 408.4375 | 5 | 408.4375 | 0 | 0
Dissemination strategy and Dissemination activities | T6.2 | 0 | 0 | 0 | 0 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0 | 0 | 0 | 0
Project Management and Coordination | WP7 | 459.4922 | 4.5 | 367.5938 |  | 0
Project coordination | T7.1 | 0 | 0 | 0 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0 | 0 | 0 | 0
Quality Assurance | T7.3 | 367.5938 | 4.5 | 367.5938 | 0 | 0
TOTAL |  | 20559.9766 | 190 | 15520.625 | 19.5 | 1221.4313

## IOC
|  | (to May) |  | (to May)
|  | TOTAL COSTS |  | TOTAL COSTS
|  | Dir & Indir (EUR) |  | Dir & Indir (EUR)
|  | ACTUAL |  | ACTUAL
GreenOfshoreTech Iceland Ocean Cluster | Task/ | M1-M9 |  | M1-M9
| WP |  | Hours/task
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) |  |  |  | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 2402.5312 | 36.75 | 2402.5312
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 248.425 | 4.75 | 310.5312
Assessment of emerging technology trends and solutions | T1.2 | 1176.75 | 22.5 | 1470.9375
Potential new value chains and selection of Call Topics | T1.3 | 496.85 | 9.5 | 621.0625
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 555.6875 | 8.5 | 555.6875
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0 | 0 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0
Establishment of a Survey tool | T2.3 | 0 | 0 | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 444.55 | 8.5 | 555.6875
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 1307.5 | 20 | 1307.5
Preparation of the Call for Proposals | T3.1 | 836.8 | 16 | 1046
Publication of the Call for Proposals and Proposal reception. | T3.2 | 209.2 | 4 | 261.5
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 0 | 0 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 359.5625 | 5.5 | 359.5625
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 287.65 | 5.5 | 359.5625
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 4821.4062 | 73.75 | 4821.4062
Communication plan and Communication activities | T6.1 | 3857.125 | 73.75 | 4821.4062
Dissemination strategy and Dissemination activities | T6.2 | 0 | 0 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0 | 0
Project Management and Coordination | WP7 | 0 | 0 | 0
Project coordination | T7.1 | 0 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0 | 0
Quality Assurance | T7.3 | 0 | 0 | 0
TOTAL |  | 9446.6875 | 144.5 | 9446.6875

## HIE
HIE
INCLDING IND COST
|  | TOTAL COSTS | TOTAL COSTS |  |  | TOTAL COSTS
|  | Dir & Indir (EUR) | Dir (EUR) |  |  | Dir & Indir (EUR)
|  | ACTUAL | ACTUAL |  |  | ACTUAL
GreenOfshoreTech PARTNER NAME | Task/ | M1-M9 | M1-M9 |  |  | M1-M9
WP
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | All | 4611 | 4611 |  |  | 5763.75
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 15319.0574 | 15319.0574 |  |  | 12255.2459
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 11586.2678 | 14482.8348 |  |  | 11586.2678
Assessment of emerging technology trends and solutions | T1.2 | 411.6788 | 514.5985 |  |  | 411.6788
Potential new value chains and selection of Call Topics | T1.3 | 257.2993 | 321.6241 |  |  | 257.2993
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 15281.059 | 21820.3105 |  |  | 15281.059
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 11710.2487 | 14637.8109 |  |  | 14637.8109
Establishment of a Collaborative Virtual Environment | T2.2 | 514.5985 | 643.2482 |  |  | 643.2482
Establishment of a Survey tool | T2.3 | 0 | 0 |  |  | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 0 |  |  | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 6539.2514 | 6539.2514 |  |  | 6539.2514
Preparation of the Call for Proposals | T3.1 | 1302.4411 | 1628.0514 |  |  | 1628.0514
Publication of the Call for Proposals and Proposal reception. | T3.2 | 3928.96 | 4911.2 | Travel costs 4611 euro added to T3.2 | 0 | 4911.2
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0 |  |  | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 |  |  | 0 | WP1 | 15319.0574
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 |  |  | 0 | WP2 | 15281.059
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 |  |  | 0 | WP3 | 6539.2514
Business Support Services to winner SMEs (preparation) | WP4 | 0 | 0 |  |  | 0 | WP4 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0 |  |  | 0 | WP5 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 |  |  | 0 | WP6 | 2261.1825
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 |  |  | 0 | WP7 | 5531.9342
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 |  |  | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 |  |  | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 |  |  | 0
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 |  |  | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 |  |  | 0
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 |  |  | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0 | 0 |  |  | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0 | 0 |  |  | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 |  |  | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 |  |  | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 2261.1825 | 2261.1825 |  |  | 2261.1825
Communication plan and Communication activities | T6.1 | 0 | 0 |  |  | 0
Dissemination strategy and Dissemination activities | T6.2 | 1808.946 | 2261.1825 |  |  | 2261.1825
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0 |  |  | 0
Project Management and Coordination | WP7 | 5531.9342 | 5531.9342 |  |  | 5531.9342
Project coordination | T7.1 | 3808.0292 | 4760.0364 |  |  | 4760.0364
Project administration & Financial Management | T7.2 | 617.5182 | 771.8978 |  |  | 771.8978
Quality Assurance | T7.3 | 0 | 0 |  |  | 0
TOTAL |  | 49543.4847 | 56082.7361 |  |  | 47632.4232

## BAL
[6 empty] | 12375 |  |  | 16600 | 1.25
[6 empty] | 6187.5 |  |  | 9900
[6 empty] | 3093.75 |  |  | 4950
|  | TOTAL COSTS |  | Hourly cost | 83.952 | 3093.75 |  |  | 2475
|  | Dir & Indir (EUR) |  |  |  | 47406.25 |  |  | 2475
|  | ACTUAL |  |  |  | 0 |  |  | 37925
GreenOfshoreTech PARTNER NAME | Task/ | M1-M9 |  |  |  | 0 |  |  | 0
| WP |  |  |  |  | 0 |  |  | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 13402.8875 | 10722.31 |  |  | 47406.25 |  |  | 0
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 7215.3875 | 5772.31 |  |  | 58500 |  |  | 37925
Assessment of emerging technology trends and solutions | T1.2 | 3093.75 | 2475 |  |  | 7437.5 |  |  | 46800
Potential new value chains and selection of Call Topics | T1.3 | 3093.75 | 2475 |  |  | 14375 |  |  | 5950
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 30049.1875 | 24039.35 |  |  | 22312.5 |  |  | 11500
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0 | 0 |  |  | 0 |  |  | 17850
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 |  |  | 0 |  |  | 0
Establishment of a Survey tool | T2.3 | 0 | 0 |  |  | 14375 |  |  | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 30049.1875 | 24039.35 |  |  | 41687.5 |  |  | 11500
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 34570.4875 | 27656.39 |  |  | 0 |  |  | 33350
Preparation of the Call for Proposals | T3.1 | 6187.5 | 4950 |  |  | 24312.5 |  |  | 0
Publication of the Call for Proposals and Proposal reception. | T3.2 | 7484.4 | 5987.52 |  |  | 8687.5 |  |  | 19450
Evaluation and Selection of SMEs Proposals | T3.3 | 14711.0875 | 11768.87 |  |  | 0 |  |  | 6950
Contracting with winner SMEs Projects | T3.4 | 0 | 0 |  |  | 0 | WP1 | 13402.8875 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 |  |  | 0 | WP2 | 30049.1875 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 6187.5 | 4950 |  |  | 0 | WP3 | 34570.4875 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 5126.7875 | 4101.43 |  |  | 0 | WP4 | 5126.7875 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0 |  |  | 8687.5 | WP5 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 5126.7875 | 4101.43 |  |  | 9281.25 | WP6 | 0 | 6950
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 |  |  | 3093.75 | WP7 | 0 | 7425
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 |  |  | 3093.75 |  |  | 2475
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 |  |  | 3093.75 |  |  | 2475
Business Support Service #5 Branding | T4.6 | 0 | 0 |  |  | 12375 |  |  | 2475
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 |  |  | 0 |  |  | 9900
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 |  |  | 6187.5 |  |  | 0
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 |  |  | 6187.5 |  |  | 4950
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0 | 0 |  |  | 0 |  |  | 4950
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0 | 0 |  |  | 0 |  |  | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 |  |  | 0 |  |  | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 |  |  | 0 |  |  | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 0 | 0 |  |  | 181625 |  |  | 0
Communication plan and Communication activities | T6.1 | 0 | 0 | [5 empty] | 145300
Dissemination strategy and Dissemination activities | T6.2 | 0 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0
Project Management and Coordination | WP7 | 0 | 0
Project coordination | T7.1 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0
Quality Assurance | T7.3 | 0 | 0
TOTAL |  | 83149.35 | 66519.48

## MEERI
|  |  |  | 16600 | 1.25
|  |  |  | 10725 |  |  | 13406.25
|  |  |  | 0 |  |  | 0
|  |  |  | 5005 |  |  | 6256.25
|  | TOTAL COSTS |  | 5720 |  |  | 7150
|  | Dir & Indir (EUR) |  | 1430 |  |  | 1787.5
|  | ACTUAL |  | 715 |  |  | 893.75
GreenOfshoreTech PARTNER NAME: MEERI | Task/ | M1-M9 |  | 0 |  |  | 0
| WP |  |  | 0 |  |  | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 8319.05 | 6655.24 | 715 |  |  | 893.75
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 307.44 | 245.952 | 18010 |  |  | 22512.5
Assessment of emerging technology trends and solutions | T1.2 | 4060.45 | 3248.36 | 3430 |  |  | 4287.5
Potential new value chains and selection of Call Topics | T1.3 | 3951.16 | 3160.928 | 0 |  |  | 0
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 1776.61 | 1421.288 | 5860 |  |  | 7325
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1115.02 | 892.016 | 0 |  |  | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 |  |  | 0
Establishment of a Survey tool | T2.3 | 661.59 | 529.272 | 8720 |  |  | 10900
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 0 | 15750 |  |  | 19687.5
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 2131.5 | 1705.2 | 0 |  |  | 0
Preparation of the Call for Proposals | T3.1 | 2131.5 | 1705.2 | 10290 |  |  | 12862.5
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 | 3030 |  |  | 3787.5
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0 | 0 |  |  | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | WP1 | 8319.05 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | WP2 | 1776.61 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 | 0 | WP3 | 2131.5 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 661.59 | 529.272 | 0 | WP4 | 661.59 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 661.59 | 529.272 | 2430 | WP5 | 1742.07 | 3037.5
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 | 2145 | WP6 | 590.43 | 2681.25
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 | 715 | WP7 | 0 | 893.75
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 715 |  |  | 893.75
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | 715 |  |  | 893.75
Business Support Service #5 Branding | T4.6 | 0 | 0 | 2860 |  |  | 3575
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 | 0 |  |  | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 1430 |  |  | 1787.5
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 | 1430 |  |  | 1787.5
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 1742.07 | 1393.656 | 0 |  |  | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 1742.07 | 1393.656 | 0 |  |  | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 | 0 |  |  | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 | 0 |  |  | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 590.43 | 472.344 | 50920 |  |  | 63650
Communication plan and Communication activities | T6.1 | 0 | 0
Dissemination strategy and Dissemination activities | T6.2 | 590.43 | 472.344
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0
Project Management and Coordination | WP7 | 0 | 0
Project coordination | T7.1 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0
Quality Assurance | T7.3 | 0 | 0
TOTAL |  | 15221.25 | 12177

## MCN
[13 empty] | 1.25 | 31600
|  | TOTAL COSTS | [11 empty] | 8250 | 10312.5
|  | Dir & Indir (EUR) | Dir (EUR) |  | INCLDING IND COST |  | This calculation is done by MNU since MCN have not delivered the contribution to D7.5 | [6 empty] | 5500 | 6875
|  | ACTUAL |  |  |  |  | Cost is calculated based on PM3,37 delivered for D7.4 | [6 empty] | 1375 | 1718.75
GreenOfshoreTech TOTAL (Period M1 to M10) | Task/ | M1-M10 |  |  |  |  | Evsaryone is informed to calculate 1PM as 143.333 hours. | [6 empty] | 1375 | 1718.75
| WP | [5 empty] | Your budgeted hourly cost is than 35,47 Euro per hour. | [6 empty] | 2750 | 3437.5
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 7696.99 | 6157.592 | PM | 1.5 | 7696.99 | PM | 3.37 | [5 empty] | 1375 | 1718.75
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 6508.745 | 5206.996 |  |  | 6508.745 | Hourly rate | 35.47 | [5 empty] | 0 | 0
Assessment of emerging technology trends and solutions | T1.2 | 0 | 0 |  |  | 0 | Total hours |  | 483.03 |  |  |  |  | 0 | 0
Potential new value chains and selection of Call Topics | T1.3 | 1188.245 | 950.596 |  |  | 1188.245 | [7 empty] | 1375 | 1718.75
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 565.24 | 452.192 | PM | 0.11 | 565.24 | Net cost total |  | 17133.0741 |  |  |  |  | 21749 | 27186.25
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 559.24 | 447.392 |  |  | 559.24 | [7 empty] | 4649 | 5811.25
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 |  |  | 0 | 1PM | 143.333 | [5 empty] | 0 | 0
Establishment of a Survey tool | T2.3 | 6 | 4.8 |  |  | 6 | [7 empty] | 8550 | 10687.5
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 0 |  |  | 0 | In d7.4 it is reported PM3,37 and a cost of 22,402.00 and this is impossible for me to evaluate without your actual calculation. | [6 empty] | 0 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 2898.055 | 2318.444 | PM | 0.45 | 2898.055 | [7 empty] | 0 | 0
Preparation of the Call for Proposals | T3.1 | 2004.055 | 1603.244 |  |  | 2004.055 | [7 empty] | 8550 | 10687.5
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 |  |  | 0 | [7 empty] | 56600 | 70750
Evaluation and Selection of SMEs Proposals | T3.3 | 894 | 715.2 |  |  | 894 | [7 empty] | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 |  |  | 0 | [7 empty] | 10500 | 13125
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 |  |  | 0 | [7 empty] | 5250 | 6562.5
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 |  |  | 0 |  |  |  | MCN |  |  |  | 5250 | 6562.5
Business Support Services to winner SMEs (preparation) | WP4 | 1169.13 | 935.304 | PM | 0.22 | 1169.13 |  |  |  | WP1 | 7696.99 | #REF! |  | 0 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 101 | 80.8 |  |  | 101 |  |  |  | WP2 | 565.24 | #REF! |  | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 |  |  | 0 |  |  |  | WP3 | 2898.055 | #REF! |  | 17000 | 21250
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 |  |  | 0 |  |  |  | WP4 | 1169.13 | #REF! |  | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 |  |  | 0 |  |  |  | WP5 | 1627 | #REF! |  | 18600 | 23250
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 39.5 | 31.6 |  |  | 39.5 |  |  |  | WP6 | 620.725 | #REF! |  | 4125 | 5156.25
Business Support Service #5 Branding | T4.6 | 230.555 | 184.444 |  |  | 230.555 |  |  |  | WP7 | 283.76 | #REF! |  | 1375 | 1718.75
Business Support Service #6 Internationalisation | T4.7 | 798.075 | 638.46 |  |  | 798.075 | [7 empty] | 1375 | 1718.75
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 |  |  | 0 | [7 empty] | 1375 | 1718.75
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 |  |  | 0 | [7 empty] | 11000 | 13750
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 1627 | 1301.6 | PM | 0.82 | 1627 | [7 empty] | 2750 | 3437.5
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 1375 | 1100 |  |  | 1375 | [7 empty] | 5500 | 6875
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 25 | 20 |  |  | 25 | [7 empty] | 2750 | 3437.5
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 227 | 181.6 |  |  | 227 | [7 empty] | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 620.725 | 496.58 | PM | 0.22 | 620.725 | [7 empty] | 0 | 0
Communication plan and Communication activities | T6.1 | 514.315 | 411.452 |  |  | 514.315 | [7 empty] | 0 | 0
Dissemination strategy and Dissemination activities | T6.2 | 0 | 0 |  |  | 0 | [7 empty] | 0 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 106.41 | 85.128 |  |  | 106.41 | [7 empty] | 104474 | 130592.5
Project Management and Coordination | WP7 | 283.76 | 227.008 | PM | 0.05 | 283.76
Project coordination | T7.1 | 0 | 0 |  |  | 0
Project administration & Financial Management | T7.2 | 0 | 0 |  |  | 0
Quality Assurance | T7.3 | 283.76 | 227.008 |  |  | 283.76
TOTAL |  | 14743.6624 | 11794.9299 | PM | 3.37 | 14743.6624

## CKR
TOTAL COSTS
|  | Dir & Indir (EUR) | Dir (EUR) |  | INCLDING IND COST |  | This calculation is done by MNU since CKR have not delivered the contribution to D7.5
|  | ACTUAL |  |  |  |  | Cost is calculated based on PM7,19 delivered for D7.4
GreenOfshoreTech TOTAL (Period M1 to M10) | Task/ | M1-M10 |  |  |  |  | Everyone is informed to calculate 1PM as 143.333 hours.
WP
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 4376.13 | 3500.904 | PM | 1 | 3505.9252 | PM | 3.37
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 1596.86 | 1277.488 |  |  |  | Hourly rate | 24.46 | Per your budget
Assessment of emerging technology trends and solutions | T1.2 | 1350 | 1080 |  |  |  | Total hours |  | 1030.56
Potential new value chains and selection of Call Topics | T1.3 | 1429.27 | 1143.416
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 6573.6097 | 5258.8878 | PM | 1.5 |  | Net cost total |  | 25207.4976
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 |  |  |  | 1PM | 143.333
Establishment of a Survey tool | T2.3 | 6573.61 | 5258.888
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 19720.8291 | 15776.6633 | PM | 4.5
Preparation of the Call for Proposals | T3.1 | 19720.83 | 15776.664
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 | [6 empty] | MCN
Business Support Services to winner SMEs (preparation) | WP4 | 0 | 0 | PM | 0 |  |  |  |  | WP1 | 4376.13 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0 | [6 empty] | WP2 | 6573.6097 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 | [6 empty] | WP3 | 19720.8291 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 | [6 empty] | WP4 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | [6 empty] | WP5 | 438.2406 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | [6 empty] | WP6 | 394.4166 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | [6 empty] | WP7 | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0 | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0
Business Support Service #8 Investor rounds | T4.9 | 0 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 438.2406 | 350.5925 | PM | 0.1
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 438.24 | 350.592
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 394.4166 | 315.5333 | PM | 0.09
Communication plan and Communication activities | T6.1 | 398.1 | 318.48
Dissemination strategy and Dissemination activities | T6.2 | 0 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0
Project Management and Coordination | WP7 | 0 | 0 | PM | 0
Project coordination | T7.1 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0
Quality Assurance | T7.3 | 0 | 0
TOTAL |  | 31503.2261 | 25202.5809 | PM | 7.19