Aurelian Manufacturing

Quality Certification Roadmap

ISO 9001, AS9100, AQAP 2110

VDR 04.05

February 2026

CONFIDENTIAL

1. Overview

Aurelian plans a phased certification approach aligned with customer segment requirements:

| Certification | Standard | Purpose | Planned Timing |
| --- | --- | --- | --- |
| ISO 9001:2015 | Quality management | Fundamental customer requirement | 2027 (production start) |
| AS9100 Rev D | Aerospace/defense | Access to defense/aerospace supply chains | 2028, customer driven |
| AQAP 2110 | NATO quality assurance | NATO supplier qualification | 2028, customer driven |

2. ISO 9001:2015 — Quality Management System

2.1 Scope

ISO 9001 is the foundation. The certification covers:

- CNC machining of precision components

- Order-to-delivery processes

- Procurement and material management

- Quality control and measurement

- Customer satisfaction and continuous improvement

2.2 Implementation Plan

| Phase | Activity | Timeline | Status |
| --- | --- | --- | --- |
| 1 | Documentation development (quality manual, procedures) | Q2–Q3 2026 | Planned |
| 2 | Process mapping and work instructions | Q3–Q4 2026 | Planned |
| 3 | Internal audit (mock audit) | Q1 2027 | Planned |
| 4 | Management review | Q1 2027 | Planned |
| 5 | External certification audit (Stage 1 + Stage 2) | Q3–Q4 2027 | Planned |
| 6 | Certification achieved | Q4 2027 | Target |

2.3 Greenfield Advantage

Documentation can be built before the facility is completed:

- Quality manual written during Seed period

- Procedures designed for autonomous operations from the start

- No legacy systems to document around

- Digital thread integrated into quality system from day one

3. AS9100 Rev D — Aerospace and Defense

3.1 Purpose

AS9100 is the industry requirement for supplying the defense and aerospace sector. Without this certification, access to several Tier 1 customers in the defense segment is limited.

3.2 Additional Requirements Beyond ISO 9001

| Requirement | Description |
| --- | --- |
| Configuration management | Traceability of all design and process changes |
| First Article Inspection (FAI) | Per AS9102 — documented first article approval |
| Process approval | Special processes qualified and approved |
| Risk-based thinking | Formalized risk assessment in all processes |
| Counterfeit parts | Prevention and detection of counterfeit materials |
| Operator competence | Documented qualification per operation |

3.3 Implementation Plan

| Phase | Activity | Timeline |
| --- | --- | --- |
| 1 | Gap analysis against AS9100 (based on ISO 9001 system) | Q4 2027 |
| 2 | Additional procedures and documentation | Q1 2028 |
| 3 | FAI process implemented and tested | Q1 2028 |
| 4 | Internal audit against AS9100 | Q2 2028 |
| 5 | External certification audit | Q3 2028 |
| 6 | Certification achieved | Q3–Q4 2028 |

4. AQAP 2110 — NATO Quality Assurance

4.1 Purpose

AQAP 2110 (Allied Quality Assurance Publication) is the NATO standard for quality assurance in defense deliveries. Certification is a prerequisite for direct deliveries to NATO organizations and many national defense procurements.

4.2 Key Elements

| Element | Description |
| --- | --- |
| Base requirement | ISO 9001 + AS9100 (prerequisite) |
| NATO-specific additions | Configuration management per STANAG |
| Government approval | Defense materiel approval (FMA) |
| Security | Security clearance of personnel and facility |
| Traceability | Complete material certification and process documentation |

4.3 Implementation Plan

| Phase | Activity | Timeline |
| --- | --- | --- |
| 1 | Contact with Defense Materiel Agency (FMA) for requirements | Q1 2028 |
| 2 | AQAP-specific additional procedures | Q2 2028 |
| 3 | Security clearance process (personnel) | Q2–Q3 2028 |
| 4 | Government assessment and approval | Q3–Q4 2028 |
| 5 | AQAP qualification achieved | Q4 2028 |

5. Quality Infrastructure

5.1 Measurement Equipment

| Equipment | Purpose | Timing |
| --- | --- | --- |
| CMM (Coordinate Measuring Machine) | Dimensional control, FAI | Production start 2027 |
| Surface roughness tester | Ra values, surface quality | Production start 2027 |
| Optical measurement system | Complex geometries | 2028 |
| SPC software | Statistical process control, real-time | Integrated from day one |

5.2 Digital Quality Architecture

Aurelian's greenfield approach enables a comprehensive digital quality architecture:

| Component | Function |
| --- | --- |
| MES (Manufacturing Execution System) | Real-time production tracking |
| SPC (Statistical Process Control) | Automatic quality monitoring |
| eDOC | Electronic document management |
| eMRB | Electronic Material Review Board |
| Digital twin | Virtual process validation before production |

6. Certification Timeline — Combined Overview

| Quarter | Milestone |
| --- | --- |
| Q2 2026 | ISO 9001 documentation start |
| Q4 2027 | ISO 9001 certified ← Production start |
| Q1 2028 | AS9100 gap analysis + additional documentation |
| Q3 2028 | AS9100 certified ← Defense supplier access |
| Q4 2028 | AQAP 2110 qualified ← NATO supplier status |

7. Document References

| Document | VDR Location |
| --- | --- |
| 02 Economic Tables & Projections REV6 | VDR 02.04 |
| Autonomous CNC Validation | VDR 04.03 |
| CNC Equipment Specifications | VDR 04.02 |

Aurelian Manufacturing AS | VDR 04.05 | Confidential

Contact: André Tandberg, CEO — andre@aurelian.no

Contact: Tore Ausland, VP Business Development — tore@aurelian.no