Aurelian Manufacturing

Production Timeline

From Seed to Full Scale

VDR 04.06

February 2026

CONFIDENTIAL

All financial figures are sourced from 02 Economic Tables & Projections REV6 (VDR 02.04). The timeline is planned — actual progress depends on financing, suppliers and customer acquisition.

1. Overall Timeline

Key milestones from Pre-Seed through full-scale operations:

| Date | Milestone |
| --- | --- |
| Q4 2025 | Pre-Seed close (5 MNOK) |
| Q1–Q2 2026 | Seed close (51.3 MNOK equity + 29.3 MNOK debt) |
| Q2 2026 | Machine order (5 CNC from MAZAK / DMG MORI) |
| Q3 2026 | Construction start — Norbygg (lease contract) |
| Q3–Q4 2026 | ISO 9001 documentation development |
| Q1 2027 | Facility completed — move-in |
| Q2 2027 | Machine delivery (5 CNC) |
| Q2–Q3 2027 | Installation, commissioning, testing |
| August 2027 | PRODUCTION START (TARGET) |
| Q4 2027 | ISO 9001 certification |
| Q4 2027 | Break-even projected (~24% utilization) |
| 2028 | AS9100 + AQAP 2110 certification |
| 2028 | 37.5% utilization (REV6 target) |
| H1 2029 | Series A close (45 MNOK equity + 105 MNOK debt) |
| Q1 2029 | CNC tranche 1: +5 machines → 10 CNC total |
| Q3 2029 | CNC tranche 2: +5 machines → 15 CNC total |
| Q3 2030 | CNC tranche 3: +5 machines → 20 CNC total |
| 2031+ | Maturity: 52.5–65% utilization (design target) |

2. Detailed Milestone Plan — Seed Phase

| # | Milestone | Timing | Dependencies | Deliverable |
| --- | --- | --- | --- | --- |
| M1 | Seed close | Q1–Q2 2026 | Pre-Seed complete, investor process | 51.3 MNOK + 29.3 MNOK |
| M2 | Machine order | Q2 2026 | M1 (financing secured) | Order confirmation MAZAK/DMG MORI |
| M3 | Norbygg construction start | Q3 2026 | M1 (lease signed) | Active construction site |
| M4 | Key hires (3–4 FTE) | Q3–Q4 2026 | M1 | Operations manager, CNC operators |
| M5 | ISO 9001 documentation | Q2–Q4 2026 | M4 (operations manager) | Quality manual, procedures |
| M6 | Facility completed | Q1 2027 | M3 (construction progress) | Move-in ready facility |
| M7 | Machine delivery | Q2 2027 | M2 + M6 | 5 CNC delivered and placed |
| M8 | Commissioning | Q2–Q3 2027 | M7 | Machines tested and approved |
| M9 | Production start | Aug 2027 | M8 + customers qualified | First customer order delivered |
| M10 | ISO 9001 certified | Q4 2027 | M5 + M9 (operational history) | Certificate |
| M11 | Break-even (model) | Q4 2027/Q1 2028 | M9 + customer acquisition | ~24% utilization |

3. Critical Path

The critical path is:

Seed close → Machine order → Machine delivery → Commissioning → Production start

| Segment | Duration | Risk |
| --- | --- | --- |
| Seed process | 3–6 months | Investor access, terms |
| Machine delivery (MAZAK/DMG MORI) | 9–12 months | Supplier capacity |
| Construction (Norbygg) | 8–10 months | Building permit, weather |
| Commissioning | 2–3 months | Installation capacity |
| Total: Seed close → Production | ~15–18 months |  |

Parallel activities not on critical path:

- ISO 9001 documentation (can start immediately after Seed)

- Customer qualification and LOI work (ongoing)

- Hiring (can start 6–9 months before production start)

4. Series A Scaling Plan

| Tranche | CNC | Timing | Cumulative | Utilization (target) |
| --- | --- | --- | --- | --- |
| Seed | 5 | Aug 2027 | 5 | 20% → 37.5% |
| A-1 | +5 | Q1 2029 | 10 | 42.5% |
| A-2 | +5 | Q3 2029 | 15 | 45% |
| A-3 | +5 | Q3 2030 | 20 | 47.5% → 65% |

Tranches are triggered by documented customer demand — not automatic.

5. Buffer and Risk Margin

| Scenario | Buffer | Consequence |
| --- | --- | --- |
| 3-month delay in machine delivery | Operational buffer (10 MNOK) covers ~12 months | Delayed production start, not critical |
| 6-month delay in construction start | Machines can be temporarily stored | Cost increase, manageable |
| Customer acquisition slower than plan | Break-even at 24% provides headroom | Longer time to maturity |

REV6 includes a 10 MNOK operational buffer in the Seed round, sized to handle delays without need for additional capital.

6. Document References

| Document | VDR Location |
| --- | --- |
| 02 Economic Tables & Projections REV6 | VDR 02.04 |
| Seed Round: Use of Funds | VDR 02.06 |
| Facility Strategy (Norbygg) | VDR 04.04 |
| CNC Equipment Specifications | VDR 04.02 |
| Quality Certification Roadmap | VDR 04.05 |

Aurelian Manufacturing AS | VDR 04.06 | Confidential

Contact: André Tandberg, CEO — andre@aurelian.no

Contact: Tore Ausland, VP Business Development — tore@aurelian.no