Aurelian Manufacturing

Risk Register

Identification, Assessment and Mitigation

VDR 04.07

February 2026

CONFIDENTIAL

1. Purpose

This document identifies and assesses the most significant risks for Aurelian Manufacturing in the period from Seed financing to full scaling (2026–2031). For each risk, probability, consequence and planned mitigations are described.

2. Risk Assessment Framework

Classification

| Probability | Definition |
| --- | --- |
| Low | <20% chance of occurrence |
| Medium | 20–50% chance |
| High | >50% chance |
| Consequence | Definition |
| Low | Limited effect, <3 month delay, <5 MNOK cost |
| Medium | Noticeable effect, 3–6 month delay, 5–15 MNOK cost |
| High | Severe effect, >6 month delay, >15 MNOK cost |

3. Risk Register

3.1 Financial Risks

| # | Risk | Probability | Consequence | Mitigation |
| --- | --- | --- | --- | --- |
| F1 | Seed round takes longer than planned | Medium | Medium | Parallel engagement of multiple investor segments; Pre-Seed buffer covers 6–9 months operations |
| F2 | Bank debt difficult to obtain | Low | High | CNC machines as collateral (50–70% resale value); early bank dialogue; alternative: leasing |
| F3 | Currency risk on machine purchase (EUR/JPY) | Medium | Low | Hedging at order; invoicing in NOK where possible |
| F4 | Cost overruns in construction phase | Medium | Medium | Fixed-price agreement with Norbygg (target); operational buffer of 10 MNOK |

3.2 Technical Risks

| # | Risk | Probability | Consequence | Mitigation |
| --- | --- | --- | --- | --- |
| T1 | Autonomous operations not achieved as planned | Medium | Medium | Gradual ramp-up (manned → evening → night → weekend); fallback to manned operations — still profitable |
| T2 | Machine delivery delayed | Medium | Medium | Early ordering; close supplier contact; 10 MNOK buffer |
| T3 | IT/OT integration more complex than expected | Medium | Medium | Experienced integrators; proven platform (MAZAK SMOOTH); extended testing before production start |
| T4 | IT/OT cyber incident | Low | High | Segmented network architecture; industrial security standards; backup systems |
| T5 | Machine breakdown during unmanned operation | Medium | Low | Multi-machine redundancy; 24/7 remote monitoring; service contracts MAZAK/DMG MORI |
| T6 | Software integration failure | Medium | Medium | Experienced integrators; proven platform; thorough pre-launch testing |

3.3 Market Risks

| # | Risk | Probability | Consequence | Mitigation |
| --- | --- | --- | --- | --- |
| M1 | Customer acquisition slower than plan | Medium | Medium | Founder network; early engagement from Pre-Seed; Physical Robotics LOI as reference |
| M2 | Defense investments delayed | Low | Medium | Diversification across defense, energy, industry; defense alone justifies capacity |
| M3 | Price pressure from competitors | Low | Medium | Differentiation on capacity, traceability and certifications — not price; 50/50 model creates loyalty |
| M4 | Customer concentration risk | Medium | Medium | Target: 5–8 anchor customers, no single customer >30% of revenue |
| M5 | Energy market slowdown | Medium | Low | Defense market provides sufficient demand regardless of energy cycle |

3.4 Operational Risks

| # | Risk | Probability | Consequence | Mitigation |
| --- | --- | --- | --- | --- |
| O1 | Shortage of qualified labor | High | Medium | MAZATROL conversational programming (lowers competence requirements); competitive compensation; training program |
| O2 | Quality issues in startup phase | Medium | Medium | Digital twin validates all programs; CMM control; in-process SPC; gradual ramp-up |
| O3 | Certification delays (ISO/AS9100/AQAP) | Medium | Medium | Early documentation start (Q2 2026); experienced quality manager as key hire |
| O4 | Key person departure | Low | High | 4-year vesting with cliff; competitive terms; documented operations (not person-dependent) |
| O5 | Building permit delayed | Low | Medium | Norbygg partnership; early municipal dialogue; zoning plan clarified |

3.5 Regulatory Risks

| # | Risk | Probability | Consequence | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Export controls limit customer base | Low | Low | Norwegian company, Norwegian production; no foreign ownership |
| R2 | Environmental requirements for production facility | Low | Low | Newbuild (Norbygg)— designed for current requirements from start |
| R3 | NIS2 directive (cybersecurity) | Medium | Low | Planned compliance if classified as critical infrastructure |

4. Risk Prioritization — Top 5

| Priority | Risk | Risk Level | Primary Mitigation |
| --- | --- | --- | --- |
| 1 | O1: Labor shortage | High × Medium | Sub-linear staffing model (design target 0.8 FTE/CNC) reduces dependency |
| 2 | T1: Autonomous operations not achieved | Medium × Medium | Gradual ramp-up + fallback to manned operations |
| 3 | M1: Slow customer acquisition | Medium × Medium | Founder network + early customer dialogue |
| 4 | F1: Delayed Seed | Medium × Medium | Diversified investor access + Pre-Seed buffer |
| 5 | T4: Cyber incident | Low × High | Segmented architecture + backup systems |

5. Financial Risk Dampener

5.1 CNC Resale Value

In a worst-case liquidation scenario, MAZAK/DMG MORI CNC machines have documented residual value:

| Machine Age | Residual Value (% of CAPEX) |
| --- | --- |
| 0–2 years | 65–70% |
| 3–5 years | 55–65% |
| 5–7 years | 50–55% |

Source: CNC Resale Value Analysis (VDR 04.02).

5.2 Break-Even Sensitivity

The model projects break-even at ~24% utilization (5 CNC). For context: observed utilization among Norwegian HMLV workshops ranges 20–45% (CNC Benchmark, VDR 03.02).

6. Document References

| Document | VDR Location |
| --- | --- |
| 02 Economic Tables & Projections REV6 | VDR 02.04 |
| Competitive Analysis: Norwegian CNC Benchmark | VDR 03.02 |
| CNC Resale Value Analysis | VDR 04.02 |
| Autonomous CNC Validation | VDR 04.03 |
| Seed Round: Use of Funds | VDR 02.06 |

Aurelian Manufacturing AS | VDR 04.07 | Confidential

Contact: André Tandberg, CEO — andre@aurelian.no

Contact: Tore Ausland, VP Business Development — tore@aurelian.no