## Dashboard
AURELIAN MANUFACTURING — VDR STATUS REPORT (UPDATED)
Scan Date: 2026-02-13 ¦ Includes REV6 Verification + Draft Documents ¦ CONFIDENTIAL
DOCUMENT STATUS
Total Documents in Register |  | 115
Documents Found in VDR |  | 44 (38%)
Draft Documents Created |  | 4
Documents Missing |  | 65 (56%)
Not Applicable |  | 2
REV6 CONSISTENCY (Verified 2026-02-13)
REV6 Stale — needs update |  | 6 documents
REV6 Unchecked |  | 2 documents
REV6 Consistent (verified) |  | 9 documents
PRE-SEED READINESS
Missing for Pre-Seed |  | 33
Critical Priority Missing |  | 2
TONIGHT'S WORK COMPLETED (2026-02-13)
1. REV6 VERIFICATION | Scanned 5 documents. Found 4 STALE (Model Assumptions, Valuation Methodology, Market Analysis, Facility Strategy). 1 CONSISTENT (Concept Note).
2. EXECUTIVE SUMMARY | Created DRAFT_00_Executive_Summary_2page.docx with all REV6 values. Ready for review.
3. INVESTMENT TEASER | Created DRAFT_00_Investment_Teaser_OnePager.docx with all REV6 values. Ready for review.
NEXT PRIORITY ACTIONS
1. UPDATE | 07_Investor_Pitch_Deck_V3 → V4: Revenue 73→49.3 MNOK (2028), Seed 47→51.3 MNOK, pre-money 140→130 MNOK, founders 53.4→50.6%. All slides need REV6 calibration.
2. UPDATE | 02_Model_Assumptions + 02_Valuation_Methodology: Both contain 8 CNC (→5), 94 MNOK (→101.3), 13% var cost (→8%). Rewrite with REV6 values.
3. UPDATE | 03_Market_Analysis + 04_Facility_Strategy: CAPEX 8→10M, admin 3→4, lease 4→5.2M. Verify and correct specific values.
4. CREATE | Founder CVs for André Tandberg and Henrik Strøm (only Tore's exists). Use team-profiles skill.
5. CREATE | Customer Pipeline Tracker + GTM Strategy — critical Pre-Seed gaps without existing source material.

## Full Status Matrix
Doc # | Cat | Document Name | Expected | VDR Status | Filename / Location | REV6 Sensitive | REV6 Status | Priority | Round | Notes
00-01 | 00 | Executive Summary 2-page | NEED | DRAFT | DRAFT_00_Executive_Summary_2page.docx | No | REV6 Consistent | Critical | Pre-Seed | Draft created 2026-02-13 with REV6 values
00-02 | 00 | Investment Teaser OnePager | NEED | DRAFT | DRAFT_00_Investment_Teaser_OnePager.docx | No | REV6 Consistent | Critical | Pre-Seed | Draft created 2026-02-13 with REV6 values
00-03 | 00 | Company Fact Sheet | NEED | Missing |  | No | N/A | Medium | Pre-Seed
01-01 | 01 | Articles of Incorporation | HAVE | Found | 01_Articles_of_Incorporation.pdf | No | N/A | Critical | Pre-Seed
01-02 | 01 | Registration Certificate Brønnøysund | HAVE | Found | 01_Registration_Certificate_Brønnøysund.pdf | No | N/A | Critical | Pre-Seed
01-03 | 01 | Bylaws / Vedtekter | HAVE | Found | 01_Bylaws_Vedtekter.pdf | No | N/A | Critical | Pre-Seed
01-04 | 01 | Shareholder Agreement | HAVE | Found | 01_Shareholders_Agreement.docx | No | N/A | Critical | Pre-Seed
01-05 | 01 | Side Letters / Amendments | NEED | Missing |  | No | N/A | Low | Seed | If any exist
01-06 | 01 | Board Composition Overview | HAVE | Found | See Vedlegg F | No | N/A | High | Pre-Seed | Embedded in Team/Governance docs
01-07 | 01 | Board Meeting Minutes | NEED | Missing |  | No | N/A | Medium | Seed
01-08 | 01 | Corporate Governance Policy | NEED | Missing |  | No | N/A | Medium | Seed
01-09 | 01 | Cap Table ProForma All Rounds | HAVE | Found | 01_Cap_Table_ProForma_All_Rounds.xlsx | Yes | REV6 Consistent | Critical | Pre-Seed | REV6 calibrated
01-10 | 01 | Cap Table Evolution PreSeed to SeriesA | HAVE | Found | Embedded in Cap Table ProForma | No | N/A | High | Pre-Seed
01-11 | 01 | Share Register Detailed | NEED | Missing |  | No | N/A | Medium | Seed
01-12 | 01 | Org Chart Current | HAVE | Found | 01_Org_Chart_Current.docx | No | N/A | Medium | Pre-Seed
01-13 | 01 | Org Chart 12-Month Roadmap | NEED | Missing |  | No | N/A | Medium | Seed
01-14 | 01 | Vesting Schedule 4yr Cliff | HAVE | Found | 01_Vesting_Schedule_4yr_Cliff.protonsheet | Yes | Unchecked | High | Pre-Seed | 0 bytes — Proton Drive sync issue. Check 53.42%→50.6%
01-15 | 01 | Acceleration Terms Double Trigger | HAVE | Found | 01_Acceleration_Terms_Double_Trigger.docx | No | N/A | Medium | Seed
02-01 | 02 | Financial Model Excel Interactive (FM8) | HAVE | Found | 02_Aurelian_Financial_Model_8.xlsx | Yes | REV6 Master | Critical | Pre-Seed | Primary source of truth
02-02 | 02 | Model Assumptions Grunnlag Verdisetting | HAVE | Found | 02_Model_Assumptions_Grunnlag_Verdisetting.docx | Yes | STALE | Critical | Pre-Seed | Contains: 8 CNC (→5), 94 MNOK (→101.3), 13% var cost (→8%)
02-03 | 02 | Round Structure PreSeed Seed SeriesA | HAVE | Found | See Financing/Valuation docs | No | N/A | High | Pre-Seed
02-04 | 02 | Valuation Methodology Revidert | HAVE | Found | 02_Valuation_Methodology_Revidert.docx | Yes | STALE | Critical | Pre-Seed | Contains: 8 CNC (→5), 94 MNOK (→101.3), 13% var cost (→8%)
02-05 | 02 | Comparable Industrial Transactions | HAVE | Found | Vedlegg C | No | N/A | Medium | Pre-Seed
02-06 | 02 | Economic Tables Projections REV6 | HAVE | Found | 02_Economic_Tables_Projections_REV6.docx/pdf | Yes | REV6 Consistent | Critical | Pre-Seed | REV6 master reference doc — replaces Financing Plan
02-07 | 02 | Monthly Cash Flow Year1 Year2 | NEED | Missing |  | No | N/A | High | Seed | Can be generated from FM8
02-08 | 02 | CAPEX Breakdown By Phase | NEED | Missing |  | No | N/A | High | Pre-Seed | Can be generated from FM8 + REV6
02-09 | 02 | Utilization Scenarios 40/50/65% | HAVE | Found | In FM8 model | No | N/A | Medium | Pre-Seed
02-10 | 02 | Sensitivity Matrix Full Standalone | NEED | Missing |  | No | N/A | High | Pre-Seed | Can be generated from REV6 Section 5
02-11 | 02 | Monte Carlo Downside Scenarios | NEED | Missing |  | No | N/A | Medium | Seed
02-12 | 02 | Use of Funds PreSeed 5MNOK | HAVE | Found | Embedded in REV6/model | No | N/A | Critical | Pre-Seed
02-13 | 02 | Milestone-Based Fund Allocation | NEED | Missing |  | No | N/A | Medium | Pre-Seed
02-14 | 02 | European VC Practice Benchmarks | HAVE | Found | 02_European_VC_Practice_Benchmarks.pdf | No | N/A | Medium | Pre-Seed
02-15 | 02 | Industrial Investment Case Comparison | HAVE | Found | Vedlegg C | No | N/A | Medium | Pre-Seed
02-16 | 02 | CNC Resale Value Downside Protection | HAVE | Found | 04_CNC_Resale_Value_Analysis.pdf | No | N/A | Medium | Pre-Seed
02-17 | 02 | Tax Registration MVA Skatteetaten | NEED | Missing |  | No | N/A | High | Pre-Seed
02-18 | 02 | Audited Financials | N/A | N/A |  | No | N/A | Low | N/A | Pre-revenue
02-19 | 02 | Founder Contribution PreSeed Valuation | HAVE | Found | 02_Founder_Contribution_PreSeed_Valuation_1.docx | No | N/A | High | Pre-Seed
03-01 | 03 | Market Analysis Master Report | HAVE | Found | 03_Market_Analysis_Master_Report.docx | Yes | STALE | High | Pre-Seed | CAPEX 8→10M, admin 3→4, var cost 13%→8%
03-02 | 03 | Defence Market NATO Spending | HAVE | Found | 03_Defence_Market_NATO_Spending.pdf | No | N/A | Medium | Pre-Seed
03-03 | 03 | Energy Market Transition Offshore | HAVE | Found | 03_Energy_Market_Transition_Offshore.pdf | No | N/A | Medium | Pre-Seed
03-04 | 03 | Critical Infrastructure Supply Chain | HAVE | Found | 03_Critical_Infrastructure_Supply_Chain.pdf | No | N/A | Medium | Pre-Seed
03-05 | 03 | TAM SAM SOM Norwegian Nordic | HAVE | Found | Check Market Analysis | Yes | Unchecked | High | Pre-Seed | Verify SOM CAPEX ref 8M→10M
03-06 | 03 | Competitive Analysis 7 Industrial Benchmarks | HAVE | Found | In Market Analysis | No | N/A | Medium | Pre-Seed
03-07 | 03 | Competitive Moat Autonomous CNC | NEED | Missing |  | No | N/A | High | Pre-Seed
03-08 | 03 | Hadrian Comparison US vs Europe | NEED | Missing |  | No | N/A | Medium | Pre-Seed
03-09 | 03 | Customer Pipeline Tracker | NEED | Missing |  | No | N/A | Critical | Pre-Seed
03-10 | 03 | Letters of Intent (LOIs) | HAVE | Found | LETTEROFINTENT_Aurelian_PhysicalRobotics.pdf | No | N/A | Critical | Pre-Seed | LOI with Physical Robotics
03-11 | 03 | Customer Discovery Interview Notes | NEED | Missing |  | No | N/A | Medium | Seed
03-12 | 03 | GTM Strategy Defence Energy Entry | NEED | Missing |  | No | N/A | High | Pre-Seed
04-01 | 04 | Concept Note Strategic Production Node | HAVE | Found | 04_Concept_Note_Strategic_Production_Node.docx | No | REV6 Consistent | High | Pre-Seed | No financial parameters — OK
04-02 | 04 | Technology Stack CNC Automation Digital | NEED | Missing |  | No | N/A | High | Pre-Seed
04-03 | 04 | CNC Equipment Specifications Mazak | NEED | Missing |  | No | N/A | Medium | Pre-Seed
04-04 | 04 | CNC Resale Value Analysis | HAVE | Found | 04_CNC_Resale_Value_Analysis.pdf | No | N/A | Medium | Pre-Seed
04-05 | 04 | Mazak LOI / Purchase Agreement | NEED | Missing |  | No | N/A | High | Pre-Seed
04-06 | 04 | Supplier Backup DMG MORI Strategy | NEED | Missing |  | No | N/A | Medium | Seed
04-07 | 04 | Automation Feasibility Study | HAVE | Found | 04_Automation_Feasibility_Study.pdf | No | N/A | High | Pre-Seed
04-08 | 04 | Lights-Out Manufacturing Evidence | NEED | Missing |  | No | N/A | Medium | Pre-Seed
04-09 | 04 | Digital Twin Siemens NX Validation | NEED | Missing |  | No | N/A | Medium | Seed
04-10 | 04 | Facility Strategy Norbygg Våler | HAVE | Found | 04_Facility_Strategy_Norbygg.docx | Yes | STALE | High | Pre-Seed | Lease ~4 MNOK → should be 5.2 MNOK
04-11 | 04 | Norbygg Lease Agreement | NEED | Missing |  | No | N/A | High | Pre-Seed
04-12 | 04 | Architectural Plans Workshop Layout | NEED | Missing |  | No | N/A | Medium | Seed
04-13 | 04 | Environmental Impact Assessment | NEED | Missing |  | No | N/A | Low | Seed
04-14 | 04 | ISO 9001 Certification Roadmap | NEED | Missing |  | No | N/A | High | Pre-Seed
04-15 | 04 | AS9100 Aerospace Defence Timeline | NEED | Missing |  | No | N/A | Medium | Seed
04-16 | 04 | AQAP NATO Qualification Plan | NEED | Missing |  | No | N/A | Medium | Seed
04-17 | 04 | Gantt Chart Investment to Production | NEED | Missing |  | No | N/A | High | Pre-Seed
04-18 | 04 | Key Milestones Critical Path | NEED | Missing |  | No | N/A | High | Pre-Seed
04-19 | 04 | Risk Register with Mitigations | NEED | Missing |  | No | N/A | High | Pre-Seed
04-20 | 04 | Contingency Plans Supplier Facility | NEED | Missing |  | No | N/A | Medium | Seed
05-01 | 05 | IP Assignment Agreements Founders | HAVE | Found | 05_IP_Assignment_Agreements_Founders.docx | No | N/A | High | Pre-Seed
05-02 | 05 | Trademark Registration Aurelian | NEED | Missing |  | No | N/A | Medium | Seed
05-03 | 05 | Patent Strategy Process Innovation | NEED | Missing |  | No | N/A | Medium | Seed
05-04 | 05 | Employment Agreements Founders | NEED | Missing |  | No | N/A | Critical | Pre-Seed
05-05 | 05 | Advisory Agreements Signed | NEED | Missing |  | No | N/A | Medium | Pre-Seed
05-06 | 05 | Supplier Contracts Mazak Materials | NEED | Missing |  | No | N/A | Medium | Seed
05-07 | 05 | Customer Framework Agreements | N/A | N/A |  | No | N/A | Low | N/A
05-08 | 05 | Export Control Defence Assessment | NEED | Missing |  | No | N/A | High | Pre-Seed
05-09 | 05 | Defence Manufacturing Regulations | NEED | Missing |  | No | N/A | Medium | Pre-Seed
05-10 | 05 | Environmental Compliance Permits | NEED | Missing |  | No | N/A | Low | Seed
05-11 | 05 | Insurance Coverage Plan | NEED | Missing |  | No | N/A | Medium | Pre-Seed
05-12 | 05 | Key Person Insurance | NEED | Missing |  | No | N/A | Medium | Seed
05-13 | 05 | Business Permits Registrations | NEED | Missing |  | No | N/A | Medium | Pre-Seed
05-14 | 05 | Manufacturing Operating Licenses | NEED | Missing |  | No | N/A | Low | Seed
06-01 | 06 | Founder CVs Detailed 3 Profiles | NEED | Partial | 06_ToreAusland_CV.docx | No | N/A | Critical | Pre-Seed | Only Tore — André and Henrik CVs missing
06-02 | 06 | Team Board Governance Overview | HAVE | Found | Vedlegg F | No | N/A | High | Pre-Seed
06-03 | 06 | Professional References Industry | NEED | Missing |  | No | N/A | Medium | Seed
06-04 | 06 | Board Member Bios Experience | HAVE | Found | Vedlegg F | No | N/A | Medium | Pre-Seed
06-05 | 06 | Board Mandate Responsibilities | NEED | Missing |  | No | N/A | Medium | Seed
06-06 | 06 | Advisor Bios Industry Relevance | NEED | Missing |  | No | N/A | Medium | Seed
06-07 | 06 | Advisory Agreements Signed | NEED | Missing |  | No | N/A | Medium | Pre-Seed
06-08 | 06 | Hiring Roadmap 12-24 Months | NEED | Missing |  | No | N/A | High | Pre-Seed
06-09 | 06 | Role Descriptions Critical Hires | NEED | Missing |  | No | N/A | Medium | Seed
06-10 | 06 | ESOP Plan Employee Incentives | NEED | Missing |  | No | N/A | Medium | Seed
06-11 | 06 | Option Pool Allocation 10% | NEED | Missing |  | No | N/A | Medium | Seed
07-01 | 07 | Investor Pitch Deck V3 | HAVE | Found | 07_Investor_Pitch_Deck_V3.pptx | Yes | STALE | Critical | Pre-Seed | Revenue 73→49.3M, cap table, fundraising — needs V4
07-02 | 07 | Pitch Deck Round-Specific Version | NEED | Missing |  | No | N/A | High | Pre-Seed | V4 needed for REV6
07-03 | 07 | Investment Teaser 1-page | NEED | DRAFT | DRAFT_00_Investment_Teaser_OnePager.docx | No | REV6 Consistent | Critical | Pre-Seed | Draft created 2026-02-13
07-04 | 07 | Executive Summary OnePager | NEED | DRAFT | DRAFT_00_Executive_Summary_2page.docx | No | REV6 Consistent | Critical | Pre-Seed | Draft created 2026-02-13
07-05 | 07 | Founder Video Pitch 3min | NEED | Missing |  | No | N/A | Medium | Seed
07-06 | 07 | Press / Media Coverage Collection | NEED | Missing |  | No | N/A | Low | Seed
08-01 | 08 | DD Checklist PreSeed Round | NEED | Missing |  | No | N/A | High | Pre-Seed | Can be generated from DD skill
08-02 | 08 | DD Checklist Seed Round | NEED | Missing |  | No | N/A | Medium | Seed
08-03 | 08 | DD Checklist SeriesA Round | NEED | Missing |  | No | N/A | Low | Serie A
08-04 | 08 | Investor Q&A Database 200+ | NEED | Missing |  | No | N/A | High | Pre-Seed | Can be generated from Q&A skill
08-05 | 08 | Investor Pipeline CRM Tracker | NEED | Missing |  | No | N/A | High | Pre-Seed
08-06 | 08 | Gap Analysis Action Items | NEED | Missing |  | No | N/A | High | Pre-Seed | This report serves as gap analysis
08-07 | 08 | DD Response Templates | NEED | Missing |  | No | N/A | Medium | Seed
08-08 | 08 | Investor Meeting Notes Log | NEED | Missing |  | No | N/A | Medium | Pre-Seed
09-01 | 09 | Vedlegg A — Investment Memorandum | NEED | Missing |  | No | N/A | High | Pre-Seed
09-02 | 09 | Vedlegg B — Economic Tables Projections | HAVE | Found | 02_Economic_Tables_Projections_REV6 | No | REV6 Consistent | Medium | Pre-Seed | Same as Cat 02 REV6
09-03 | 09 | Vedlegg C — Industrial Benchmarks | HAVE | Found | Vedlegg C docx+pdf | No | N/A | Medium | Pre-Seed
09-04 | 09 | Vedlegg D — Automation Feasibility | HAVE | Found | 04_Automation_Feasibility_Study.pdf | No | N/A | Medium | Pre-Seed | Same file as Cat 04
09-05 | 09 | Vedlegg E — CNC Resale Value Analysis | HAVE | Found | 04_CNC_Resale_Value_Analysis.pdf | No | N/A | Medium | Pre-Seed | Same file as Cat 04
09-06 | 09 | Vedlegg F — Team Board Governance | HAVE | Found | Vedlegg F subfolder | No | N/A | Medium | Pre-Seed
09-07 | 09 | Vedlegg G — Facility Strategy Norbygg | HAVE | Found | 04_Facility_Strategy_Norbygg.docx | Yes | STALE | Medium | Pre-Seed | Lease 4→5.2M (same as Cat 04)

## REV6 Verification Results
Document | Priority | Parameter | KOMPLETT Value | REV6 Value | Status | Verified
02_Model_Assumptions | HIGH | Seed CNC count | 8 | 5 | STALE | 2026-02-13
02_Model_Assumptions | HIGH | Total equity | 94 MNOK | 101.3 MNOK | STALE | 2026-02-13
02_Model_Assumptions | HIGH | Variable cost (mature) | 13% flat | 8% curve | STALE | 2026-02-13
02_Valuation_Methodology | HIGH | Seed CNC count | 8 | 5 | STALE | 2026-02-13
02_Valuation_Methodology | HIGH | Total equity | 94 MNOK | 101.3 MNOK | STALE | 2026-02-13
02_Valuation_Methodology | HIGH | Variable cost (mature) | 13% flat | 8% curve | STALE | 2026-02-13
03_Market_Analysis | MEDIUM | CAPEX per CNC | 8 MNOK | 10 MNOK | STALE | 2026-02-13
03_Market_Analysis | MEDIUM | Admin FTEs | 3 | 4 | STALE | 2026-02-13
03_Market_Analysis | MEDIUM | Finance cost basis | 8 MNOK/CNC | 10 MNOK/CNC | STALE | 2026-02-13
03_Market_Analysis | MEDIUM | Variable cost | 13% | 8% | STALE | 2026-02-13
04_Facility_Strategy | MEDIUM | Annual lease | ~4 MNOK | 5.2 MNOK | STALE | 2026-02-13
04_Concept_Note | LOW | Financial parameters | None found | N/A | CONSISTENT | 2026-02-13
02_Economic_Tables_REV6 | MASTER | Admin FTEs | 4 | 4 | CONSISTENT | 2026-02-13
02_Economic_Tables_REV6 | MASTER | Facility lease | 5.2 MNOK/yr | 5.2 MNOK/yr | CONSISTENT | 2026-02-13
02_Economic_Tables_REV6 | MASTER | Variable cost | 8% curve | 8% curve | CONSISTENT | 2026-02-13
01_Vesting_Schedule | LOW | Founders post-Serie A | 53.42%? | 50.6% | UNCHECKED | Proton sync issue — 0 bytes
03_TAM_SAM_SOM | MEDIUM | SOM CAPEX reference | 8 MNOK? | 10 MNOK | UNCHECKED | Embedded in Market Analysis — needs manual check

## Change Log
Date | Event | Document | Details
2026-02-13 | INITIAL SCAN | Full VDR | Baseline: 44 found, 65 missing, 4 drafts, 6 stale
2026-02-13 | REV6 VERIFIED | 5 documents scanned | 4 STALE, 1 CONSISTENT. See REV6 Verification Results sheet
2026-02-13 | DRAFT CREATED | DRAFT_00_Executive_Summary_2page.docx | 2-page exec summary with all REV6 values
2026-02-13 | DRAFT CREATED | DRAFT_00_Investment_Teaser_OnePager.docx | 1-page teaser with all REV6 values
2026-02-13 | REGISTER UPDATED | 02_Financing_Plan_KOMPLETT removed | Per Tore: replaced 100% by Economic Tables REV6
2026-02-13 | NEW FINDING | 01_Articles_of_Incorporation.pdf | Previously listed as NEED, now found in VDR
2026-02-13 | NEW FINDING | 01_Registration_Certificate_Brønnøysund.pdf | Previously listed as NEED, now found
2026-02-13 | NEW FINDING | 01_Bylaws_Vedtekter.pdf | Previously listed as NEED, now found
2026-02-13 | NEW FINDING | 01_Shareholders_Agreement.docx | Previously listed as NEED, now found
2026-02-13 | NEW FINDING | 01_Org_Chart_Current.docx | Previously listed as NEED, now found
2026-02-13 | NEW FINDING | 01_Acceleration_Terms_Double_Trigger.docx | Previously listed as NEED, now found
2026-02-13 | NEW FINDING | 05_IP_Assignment_Agreements_Founders.docx | Previously listed as NEED, now found
2026-02-13 | NEW FINDING | 06_ToreAusland_CV.docx | 1 of 3 founder CVs (André + Henrik still missing)
2026-02-13 | NEW FINDING | LETTEROFINTENT_Aurelian_PhysicalRobotics.pdf | LOI with Physical Robotics found
2026-02-13 | NOTE | 01_Vesting_Schedule_4yr_Cliff.protonsheet | 0 bytes — Proton Drive sync issue

## Category Summary
Cat | Category Name | Total | Found | Draft | Missing | N/A | REV6 Issues | Completion %
00 | Executive Summaries & Teasers | 3 | 0 | 2 | 1 | 0 | 0 | 66%
01 | Corporate & Legal | 15 | 10 | 0 | 5 | 0 | 1 | 66%
02 | Financial Model & Projections | 19 | 12 | 0 | 6 | 1 | 2 | 66%
03 | Market & Commercial | 12 | 7 | 0 | 5 | 0 | 2 | 58%
04 | Technical & Operations | 20 | 4 | 0 | 16 | 0 | 1 | 20%
05 | Legal, IP & Contracts | 14 | 1 | 0 | 12 | 1 | 0 | 7%
06 | Team, Board & Governance | 11 | 3 | 0 | 8 | 0 | 0 | 27%
07 | Presentations & Pitch | 6 | 1 | 2 | 3 | 0 | 1 | 50%
08 | DD Process (Internal) | 8 | 0 | 0 | 8 | 0 | 0 | 0%
09 | Vedlegg / Appendices | 7 | 6 | 0 | 1 | 0 | 1 | 85%
TOTAL | All Categories | 115 | 44 | 4 | 65 | 2 | 8 | 42%