SDRL

Manifold and SDU Fabrication

N041250-E300B, Rev C

Design and manufacturing of components/Manufacturing of GE Oil & Gas designed components/ Raw Material delivery/ P/N

| Title | No | Document | GE Responsible | Document due time | To GE for review | MRB (final doc.) | Include in shipment | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| General documents | 1.1 | Document list | B | 4 WAO |  |  |  |  |
|  | 1.2 | 4w look ahead report (RC/IIP) | B |  |  |  |  |  |
| Bid documentation ( Technical Documents only) | 2.1 | Exceptions from specifications and other requirements in the inquiry | E | BID |  |  |  |  |
|  | 2.2 | Inspection and test plan | Q | BID |  |  |  |  |
|  | 2.3 | Project Quality Plan | Q | BID |  |  |  |  |
| Engineering documentation | 3.1 | Data sheets | E |  |  |  |  |  |
|  | 3.2 | Calculations, curves and tables | E |  |  |  |  |  |
|  | 3.3 | Safe job analysis procedure | E | BID |  |  |  |  |
|  | 3.4 | GA drawings | E |  |  |  |  |  |
|  | 3.5 | Other drawings | E | 2WPM |  |  |  |  |
|  | 3.6 | As- built drawings, mark- ups | E | WFD |  |  |  |  |
|  | 3.7 | Main equipment list | E |  |  |  |  |  |
| Documentation for dispatch, receipt, storage and installation | 4.1 | Packing and preservation procedure | E | BID |  |  |  |  |
|  | 4.2 | Packing list | L | WED |  |  |  |  |
|  | 4.3 | Inspection report for free issued materials | Q |  |  |  |  | As available |
|  | 4.4 | Delivery schedule report/Production plan | B |  |  |  |  | To be included in the progress / status report |
| User manual | 5.1 | User manual | E |  |  |  |  |  |
|  | 5.2 | Index for user manual | E |  |  |  |  |  |
| Manufacturing and verifying (Certificates) | 6.1 | Material certificate | Q | WED |  |  |  |  |
|  | 6.2 | Lifting certificates | Q | WED |  |  |  |  |
|  | 6.3 | Weight certificate | Q | WED |  |  |  |  |
|  | 6.4 | Balancing certificate | Q | WED |  |  |  |  |
|  | 6.5 | Pressure test certificate | Q | WED |  |  |  |  |
|  | 6.6 | Electrical continuity certificate | Q | WED |  |  |  |  |
|  | 6.7 | Welders certificates | Q | WED |  |  |  |  |
|  | 6.8 | NDE operator certificate | Q | WED |  |  |  |  |
|  | 6.9 | PMI operators certificate | Q | WED |  |  |  |  |
| Manufacturing and verifying (Procedures) | 7.1 | WPS/WPQR/PWHT | E | BID |  |  |  | Previously qualified WPSs can be supplied for review |
|  | 7.2 | Non- conformance procedure | Q | 6WAO |  |  |  |  |
|  | 7.3 | Heat treatment procedure | E |  |  |  |  |  |
|  | 7.4 | Fabrication procedure | E | 8WAO |  |  |  |  |
|  | 7.5 | Non- destructive ferrite content program | E |  |  |  |  |  |
|  | 7.6 | PMI procedure/ program | E | 8WPM |  |  |  |  |
|  | 7.7 | Traceability procedure/ Matrix | Q | 6WAO |  |  |  |  |
|  | 7.8 | Weld log | Q | WAT |  |  |  |  |
|  | 7.9 | NDE procedure | Q | 6WAO |  |  |  |  |
|  | 7.10 | Welders repair procedure | E | BID |  |  |  | Previously qualified WPSs can be supplied for review |
|  | 7.11 | Coating procedure | E | 8WPM |  |  |  |  |
|  | 7.12 | Qualification procedure | E |  |  |  |  |  |
|  | 7.13 | Handling welding consumables procedure | E | 6WAO |  |  |  |  |
| Manufacturing and verifying (Reports) | 8.1 | Certificate of conformance | Q | WED |  |  |  |  |
|  | 8.2 | Non- destructive ferrite content report | Q | WAT |  |  |  |  |
|  | 8.3 | PMI report | Q | WAT |  |  |  |  |
|  | 8.4 | Surface treatment report | Q | WAT |  |  |  |  |
|  | 8.5 | Photos of equipment/ testing | Q | WED |  |  |  |  |
|  | 8.6 | NDE reports | Q | WAT |  |  |  |  |
|  | 8.7 | FAT/ EFAT/ SIT reports | Q | WAT |  |  |  |  |
|  | 8.8 | Third party verification | Q | WED |  |  |  |  |
|  | 8.9 | Traceability records/ list | Q | WED |  |  |  |  |
|  | 8.10 | Visual inspection report | Q | WAT |  |  |  |  |
|  | 8.11 | Dimension inspection report | Q | WAT |  |  |  |  |
|  | 8.12 | Non- conformance report | Q | WED |  |  |  |  |
|  | 8.13 | Mechanical completion dossier (MCD) | Q | WED |  |  |  |  |
|  | 8.14 | Manufacturing Record book (MRB) standard index (Ref appendix 1 in this document) | Q | 10 WAO |  |  |  |  |
|  | 8.15 | Manufacturing Record book (MRB) | Q | WED |  |  |  |  |
| Product specific | 9.1 |  |  |  |  |  |  |  |

| Abbreviations |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| E= | Engineering | L= | Logistics | MRB= | Manufacturing record book | WEE= | (1) Weekly (2) Biweekly |
| Q= | Quality | M= | Material | MCD= | Mechanical completion dossier | WAO= | Weeks after order |
| B= | Buyer | SP= | Special request | WED= | With each delivery | WAT= | Week after testing |
| P= | Planning | BID= | Included in Bid | WPM= | Weeks prior to manufacturing | WFD= | With final delivery |

# MRB standard Index

To be filled out by the suppliers (ref 8.14).

|  |  | In Use | N/A |
| --- | --- | --- | --- |
| 1 | Material Traceability List/Record |  |  |
| 2 | Material Certificates/ PMI reports |  |  |
| 3 | NDT/ Weld log |  |  |
| 4 | WPS /WPQR |  |  |
| 5 | Welders certificate |  |  |
| 6 | Visual inspection report |  |  |
| 7 | NDE Report |  |  |
| 8 | NDE Operators Certificate |  |  |
| 9 | Surface Treatment Inspection Report |  |  |
| 10 | Dimensional Inspection Record |  |  |
| 11 | Weighting Certificate |  |  |
| 12 | Lifting Certificate |  |  |
| 13 | Pressure Test Traceability Certificate |  |  |
| 14 | Pressure Test Certificate / FAT Reports |  |  |
| 15 | Documentation from Sub-suppliers |  |  |
| 16 | Non-conformance / Concession Reports |  |  |
| 17 | Certificate of Conformity |  |  |
| 18 | As Built Drawings / Mark-ups |  |  |
| 19 | Photos of equipment / testing |  |  |
| 20 | Mechanical Completion Dossier |  |  |