Recovery plan for Ferdocean Shipping:

1. Clarify the Financial Situation

Cash Flow Analysis

  - Prepare an up-to-date cash flow/liquidity overview.

  - How long current resources will last under different scenarios (worst vs. best case).

Bridge Financing including Swiss opportunity

  - Alisting and overview of the  short-term funding: Shareholder loans, funding rounds executed.

  - Map out the timelines and requirements for fulfilling the FOS obligations, e.g settling the loans or converting it to shares.

  - Update the progress of the Swiss NOTE structure funding.

### 2. Mobilize Existing Shareholders & Board

Shareholder Task Force

  - Convene a small task force (2–3 resourceful shareholders/board members) willing to dedicate time.

  - Assign each member clear responsibilities (e.g., introductions to potential investors, client outreach, cost-control initiatives).

Board Sanity and strength Check

  - Have an emergency board meeting (if not already scheduled) to confirm alignment on immediate priorities and next steps.

  - Strengthen the “Board of FOS”,

  - Document clear, time-bound action items.

### 3. Strengthen Management Capacity

Temporary Executive Support

  - Recruit a part-time COO or CFO from the shareholder network, or hire an external consultant on a short-term contract.

  - Focus on areas where the CEO is most overwhelmed (finances, operations, etc.).

Task and Role Clarity

  - Delegate day-to-day operational tasks to an appointed manager or project lead so the CEO can focus on strategic moves and fundraising.

  - Ensure key responsibilities are documented and assigned with deadlines (e.g., cost-cutting, vendor negotiations).

### 4. Streamline Operations

Cost Reduction & Efficiency

  - Immediately review major expenses and defer non-critical spending (e.g., marketing, new hires).

  - Negotiate payment terms with suppliers and employees to extend runway.

Prioritize Core Activities

  - Identify which products/services or R&D projects are critical for near-term revenue or milestones.

  - Pause or drop non-essential projects and communicate changes clearly to the team and board.

### 5. Prepare for Potential Contracts/Deals

Contract Readiness Checklist

  - Identify what is missing to be “contract ready”: e.g., financial stability, compliance documents, or specialized staff.

  - Allocate board/shareholder resources to fill these gaps quickly (legal counsel, bridging funds, advisory support).

Potential Partnerships

  - Explore collaborations (including with strategic partners or larger companies) to share costs or expertise.

  - Encourage the resourceful shareholders to leverage their networks for possible JV agreements or outsourcing.

### 6. Develop a Medium-Term Fundraising & Growth Plan

Investor Outreach Strategy

  - Shortlist potential investors (VCs, private equity, angel groups). Do not enter negotiations with potential investors without discussing with the board and shareholder taskforce.

  - Assign each contact to a board member or experienced shareholder for a warm introduction.

Updated Pitch Deck & Financial Model

  - Work out and create a compelling story around the company’s future.

  - Use a well-vetted financial model that shows how short-term infusions bridge the company to sustainable growth or a major milestone.

Executive Summary for Stakeholders

  - Prepare a concise one-pager summarizing the situation, the plan, and how recentand or new shareholder loans new will be deployed.

  - Ensure consistent communication with existing shareholders, potential investors, and key partners.

Monitor & Adapt

- Weekly Check-Ins for the CEO: Have short, structured calls or meetings with the Board and the shareholder task force to track progress on all action items.

- Agile Approach: Reassess the plan regularly and pivot fast if certain funding or contract opportunities do not materialize.

- Make the priorities right and keep the processes transparent and goal focused.