## %Cost vs Budget
Partner | Used of Budget
GOT | 20.4981
MNU | 29.3344
SCA | 22.228
FOC | 23.3291
CLTV | 15.3444
MAI | 10.4211
BIN | 7.6098
IOC | 6.7957
HIE | 22.4682
BAL | 45.7808
MEERI | 23.914
MCN | 11.2897
CKR | 33.1177

## WP Cost vs Budget
Task/WP | TOTAL COST | TOTAL BUDGET
WP1 | 104301.9925 | 226991.17
T1.1 | 41306.53 | 88440.74
T1.2 | 29037.419 | 53116.01
T1.3 | 30982.7711 | 85434.42
Task/WP | TOTAL COST | TOTAL BUDGET
WP2 | 67811.8909 | 153493.81
T2.1 | 19605.4587 | 67887.51
T2.2 | 5204.3416 | 3343.75
T2.3 | 10794.0294 | 12525
T2.4 | 32291.6467 | 69737.55
Task/WP | TOTAL COST | TOTAL BUDGET
WP3 | 84177.4616 | 3434125.12
T3.1 | 47109.1197 | 68475.03
T3.2 | 14557.7603 | 18562.5
T3.3 | 15885.025 | 121637.57
T3.4 | 0 | 26750
T3.5 | 0 | 3026750
T3.6 | 6187.5 | 171950.02
Task/WP | TOTAL COST | TOTAL BUDGET
WP4 | 21789.2283 | 701740.32
T4.1 | 8330.8886 | 24218.75
T4.2 | 5322.8375 | 170550.08
T4.3 | 261.4 | 113875.05
T4.4 | 0 | 70268.81
T4.5 | 359.9075 | 114196.76
T4.6 | 230.555 | 6925
T4.7 | 798.075 | 54018.33
T4.8 | 595.1947 | 53087.47
T4.9 | 5748.05 | 94600.07
Task/WP | TOTAL COST | TOTAL BUDGET
WP5 | 42546.3243 | 148095.23
T5.1 | 40961.1874 | 55221.35
T5.2 | 771.5 | 55221.35
T5.3 | 796.2062 | 37652.53
Task/WP | TOTAL COST | TOTAL BUDGET
WP6 | 56406.8404 | 231218.95
T6.1 | 39381.405 | 55825.06
T6.2 | 10860.0632 | 108168.84
T6.3 | 1066.5956 | 67225.05
Task/WP | TOTAL COST | TOTAL BUDGET
WP7 | 115933.4329 | 214000
T7.1 | 42675.2639 | 147125
T7.2 | 50402.5615 | 46812.5
T7.3 | 22782.0887 | 20062.5

## PM Efforth per Task
[5 empty] | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9 | B10 | B11 | B12
No | Work Packages (WP) & Tasks (T) | Lead | Start | End | MNU | FOC | CTLV | CKR | MAI | BIN | IOC | HIE | MCN | MEERI | SCA | BAL | TOTAL PMs | 100%
WP1 | Assessment of potential new value chains and selection of Topics for Call of Proposals | MEERI | 1 | 6 | 1.5 | 2.25 | 2.25 | 3.25 | 3.25 | 3.25 | 1.5 | 2.25 | 1.5 | 3.75 | 1 | 1 | 26.75 | 12.02%
T1.1 | Sustainable challenges, needs and trends of four industrial offshore sectors | HIE | 1 | 3 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 1.75 | 1 | 0 | 0.5 | 0.5 | 7.75
T1.2 | Assessment of emerging technology trends and solutions | MEERI | 1 | 4 | 0.25 | 0.25 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0.25 | 1.75 | 0.25 | 0.25 | 7.5
T1.3 | Potential new value chains and selection of Call Topics | MEERI | 3 | 6 | 0.25 | 1 | 1 | 2 | 2 | 2 | 0.25 | 0.25 | 0.25 | 2 | 0.25 | 0.25 | 11.5
WP2 | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | HIE | 1 | 36 | 0.5 | 2.5 | 2.5 | 2 | 0.5 | 0.5 | 0.5 | 3.5 | 0.5 | 0.5 | 0.5 | 3.75 | 17.75 | 7.978%
T2.1 | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | HIE | 1 | 36 | 0.25 | 1.25 | 1.25 | 0.75 | 0.25 | 0.25 | 0.25 | 3.25 | 0.25 | 0.25 | 0.25 | 0 | 8.25
T2.2 | Establishment of a Collaborative Virtual Environment | MNU | 1 | 36 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
T2.3 | Establishment of a Survey tool | CKR | 1 | 36 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
T2.4 | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | BAL | 1 | 36 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 3.75 | 6.25
WP3 | Direct financial support to SMEs through a competitive Call for Proposals | CKR | 1 | 36 | 7 | 2.5 | 3.5 | 6 | 3.5 | 3.5 | 2.5 | 2.5 | 2.5 | 3.5 | 4.5 | 4 | 45.5 | 20.45%
T3.1 | Preparation of the Call for Proposals | CKR | 1 | 7 | 0.5 | 0.5 | 0.5 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 8.5
T3.2 | Publication of the Call for Proposals and Proposal reception. | BAL | 8 | 18 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.5
T3.3 | Evaluation and Selection of SMEs Proposals | BAL | 11 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 12.5
T3.4 | Contracting with winner SMEs Projects | MNU | 13 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
T3.5 | Payments and financial monitoring of winner SMEs Projects | MNU | 13 | 36 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
T3.6 | Technical monitoring of winner SMEs Projects | SCA | 13 | 36 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 19
WP4 | Business Support Services to winner SMEs | MAI | 1 | 36 | 5.5 | 8.5 | 7 | 3 | 8 | 9 | 3 | 7 | 6 | 2.5 | 12.75 | 2.5 | 74.75 | 33.6%
T4.1 | Programme of Business Support Services to winner SMEs | MAI | 1 | 36 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
T4.2 | Business Support Service #1 Business & Tech Academy | MAI | 1 | 24 | 1 | 1 | 1 | 1 | 3 | 3.5 | 1 | 1 | 1 | 1.5 | 1 | 1.5 | 17.5
T4.3 | Business Support Service #2 Brokerage & B2B matchmaking events | CMAB | 1 | 24 | 0.5 | 4 | 0.5 | 0.5 | 1 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 13.5
T4.4 | Business Support Service #3 Access to Finance | HIE | 1 | 24 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 0.5 | 0 | 0 | 0 | 7
T4.5 | Business Support Service #4 One-to-One Mentoring and Coaching | SCA | 1 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75
T4.6 | Business Support Service #5 Branding | FOC | 1 | 32 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
T4.7 | Business Support Service #6 Internationalisation | MCN | 1 | 32 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0 | 0 | 0 | 6
T4.8 | Business Support Service #7 Investor pitching | CTLV | 1 | 32 | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1 | 0 | 7
T4.9 | Business Support Service #8 Investor rounds | MNU | 1 | 32 | 2.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 0.5 | 0.5 | 9.5
WP5 | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | SCA | 1 | 36 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 6 | 0.75 | 14.25 | 6.404%
T5.1 | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | SCA | 1 | 36 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 2.5 | 0.25 | 5.25
T5.2 | Validation & Impact assessment of GreenOffshoreTech LSD | SCA | 1 | 36 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 2.5 | 0.25 | 5.25
T5.3 | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | SCA | 35 | 36 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 0.25 | 3.75
WP6 | Communication, Dissemination, Exploitation & Sustainability | FOC | 1 | 36 | 2 | 7.5 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 27.5 | 12.36%
T6.1 | Communication plan and Communication activities | FOC | 1 | 36 | 0.5 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 8
T6.2 | Dissemination strategy and Dissemination activities | FOC | 1 | 36 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 12.5
T6.3 | Exploitation strategy, IPR and Sustainability | MAI | 1 | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 7
WP7 | Project Management and Coordination | MNU | 1 | 36 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 7.191%
T7.1 | Project coordination | MNU | 1 | 36 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
T7.2 | Project administration & Financial Management | MNU | 1 | 36 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
T7.3 | Quality Assurance | MNU | 1 | 36 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
|  | Lead | Start | End | 33.25 | 24 | 18 | 17 | 19 | 19 | 10.25 | 18 | 13.25 | 12 | 25.75 | 13 | 222.5
|  |  |  | No | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9 | B10 | B11 | B12
|  |  |  | Partner | MNU | FOC | CTLV | CKR | MAI | BIN | IOC | HIE | MCN | MEERI | SCA | BAL | TOTAL
|  |  |  | WP1 | 1.5 | 2.25 | 2.25 | 3.25 | 3.25 | 3.25 | 1.5 | 2.25 | 1.5 | 3.75 | 1 | 1 | 26.75 | 12.02%
|  |  |  | WP2 | 0.5 | 2.5 | 2.5 | 2 | 0.5 | 0.5 | 0.5 | 3.5 | 0.5 | 0.5 | 0.5 | 3.75 | 17.75 | 7.978%
|  |  |  | WP3 | 7 | 2.5 | 3.5 | 6 | 3.5 | 3.5 | 2.5 | 2.5 | 2.5 | 3.5 | 4.5 | 4 | 45.5 | 20.45%
|  |  |  | WP4 | 5.5 | 8.5 | 7 | 3 | 8 | 9 | 3 | 7 | 6 | 2.5 | 12.75 | 2.5 | 74.75 | 33.6%
|  |  |  | WP5 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 6 | 0.75 | 14.25 | 6.404%
|  |  |  | WP6 | 2 | 7.5 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 27.5 | 12.36%
|  |  |  | WP7 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 7.191%
|  |  |  | SUM | 33.25 | 24 | 18 | 17 | 19 | 19 | 10.25 | 18 | 13.25 | 12 | 25.75 | 13 | 222.5 | 100%
AS PER BUDGET

## Efforth per task PM
[5 empty] | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9 | B10 | B11 | B12
No | Work Packages (WP) & Tasks (T) | Lead | Start | End | MNU | FOC | CTLV | CKR | MAI | BIN | IOC | HIE | MCN | MEERI | SCA | BAL | TOTAL PMs | 100%
WP1 | Assessment of potential new value chains and selection of Topics for Call of Proposals | MEERI | 1 | 6 | 1.5 | 2.25 | 2.25 | 3.25 | 3.25 | 3.25 | 1.5 | 2.25 | 1.5 | 3.75 | 1 | 1 | 26.75 | 12.02%
T1.1 | Sustainable challenges, needs and trends of four industrial offshore sectors | HIE | 1 | 3 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 1.75 | 1 | 0 | 0.5 | 0.5 | 7.75
T1.2 | Assessment of emerging technology trends and solutions | MEERI | 1 | 4 | 0.25 | 0.25 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0.25 | 1.75 | 0.25 | 0.25 | 7.5
T1.3 | Potential new value chains and selection of Call Topics | MEERI | 3 | 6 | 0.25 | 1 | 1 | 2 | 2 | 2 | 0.25 | 0.25 | 0.25 | 2 | 0.25 | 0.25 | 11.5
WP2 | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | HIE | 1 | 36 | 0.5 | 2.5 | 2.5 | 2 | 0.5 | 0.5 | 0.5 | 3.5 | 0.5 | 0.5 | 0.5 | 3.75 | 17.75 | 7.978%
T2.1 | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | HIE | 1 | 36 | 0.25 | 1.25 | 1.25 | 0.75 | 0.25 | 0.25 | 0.25 | 3.25 | 0.25 | 0.25 | 0.25 | 0 | 8.25
T2.2 | Establishment of a Collaborative Virtual Environment | MNU | 1 | 36 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
T2.3 | Establishment of a Survey tool | CKR | 1 | 36 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
T2.4 | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | BAL | 1 | 36 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 3.75 | 6.25
WP3 | Direct financial support to SMEs through a competitive Call for Proposals | CKR | 1 | 36 | 7 | 2.5 | 3.5 | 6 | 3.5 | 3.5 | 2.5 | 2.5 | 2.5 | 3.5 | 4.5 | 4 | 45.5 | 20.45%
T3.1 | Preparation of the Call for Proposals | CKR | 1 | 7 | 0.5 | 0.5 | 0.5 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 8.5
T3.2 | Publication of the Call for Proposals and Proposal reception. | BAL | 8 | 18 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.5
T3.3 | Evaluation and Selection of SMEs Proposals | BAL | 11 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 12.5
T3.4 | Contracting with winner SMEs Projects | MNU | 13 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
T3.5 | Payments and financial monitoring of winner SMEs Projects | MNU | 13 | 36 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
T3.6 | Technical monitoring of winner SMEs Projects | SCA | 13 | 36 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 19
WP4 | Business Support Services to winner SMEs | MAI | 1 | 36 | 5.5 | 8.5 | 7 | 3 | 8 | 9 | 3 | 7 | 6 | 2.5 | 12.75 | 2.5 | 74.75 | 33.6%
T4.1 | Programme of Business Support Services to winner SMEs | MAI | 1 | 36 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
T4.2 | Business Support Service #1 Business & Tech Academy | MAI | 1 | 24 | 1 | 1 | 1 | 1 | 3 | 3.5 | 1 | 1 | 1 | 1.5 | 1 | 1.5 | 17.5
T4.3 | Business Support Service #2 Brokerage & B2B matchmaking events | CMAB | 1 | 24 | 0.5 | 4 | 0.5 | 0.5 | 1 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 13.5
T4.4 | Business Support Service #3 Access to Finance | HIE | 1 | 24 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 0.5 | 0 | 0 | 0 | 7
T4.5 | Business Support Service #4 One-to-One Mentoring and Coaching | SCA | 1 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.75 | 0 | 9.75
T4.6 | Business Support Service #5 Branding | FOC | 1 | 32 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
T4.7 | Business Support Service #6 Internationalisation | MCN | 1 | 32 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0 | 0 | 0 | 6
T4.8 | Business Support Service #7 Investor pitching | CTLV | 1 | 32 | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1 | 0 | 7
T4.9 | Business Support Service #8 Investor rounds | MNU | 1 | 32 | 2.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 0.5 | 0.5 | 9.5
WP5 | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | SCA | 1 | 36 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 6 | 0.75 | 14.25 | 6.404%
T5.1 | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | SCA | 1 | 36 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 2.5 | 0.25 | 5.25
T5.2 | Validation & Impact assessment of GreenOffshoreTech LSD | SCA | 1 | 36 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 2.5 | 0.25 | 5.25
T5.3 | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | SCA | 35 | 36 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 0.25 | 3.75
WP6 | Communication, Dissemination, Exploitation & Sustainability | FOC | 1 | 36 | 2 | 7.5 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 27.5 | 12.36%
T6.1 | Communication plan and Communication activities | FOC | 1 | 36 | 0.5 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 8
T6.2 | Dissemination strategy and Dissemination activities | FOC | 1 | 36 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 12.5
T6.3 | Exploitation strategy, IPR and Sustainability | MAI | 1 | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 7
WP7 | Project Management and Coordination | MNU | 1 | 36 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 7.191%
T7.1 | Project coordination | MNU | 1 | 36 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
T7.2 | Project administration & Financial Management | MNU | 1 | 36 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
T7.3 | Quality Assurance | MNU | 1 | 36 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
|  | Lead | Start | End | 33.25 | 24 | 18 | 17 | 19 | 19 | 10.25 | 18 | 13.25 | 12 | 25.75 | 13 | 222.5
|  |  |  | No | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9 | B10 | B11 | B12
|  |  |  | Partner | MNU | FOC | CTLV | CKR | MAI | BIN | IOC | HIE | MCN | MEERI | SCA | BAL | TOTAL
|  |  |  | WP1 | 1.5 | 2.25 | 2.25 | 3.25 | 3.25 | 3.25 | 1.5 | 2.25 | 1.5 | 3.75 | 1 | 1 | 26.75 | 12.02%
|  |  |  | WP2 | 0.5 | 2.5 | 2.5 | 2 | 0.5 | 0.5 | 0.5 | 3.5 | 0.5 | 0.5 | 0.5 | 3.75 | 17.75 | 7.978%
|  |  |  | WP3 | 7 | 2.5 | 3.5 | 6 | 3.5 | 3.5 | 2.5 | 2.5 | 2.5 | 3.5 | 4.5 | 4 | 45.5 | 20.45%
|  |  |  | WP4 | 5.5 | 8.5 | 7 | 3 | 8 | 9 | 3 | 7 | 6 | 2.5 | 12.75 | 2.5 | 74.75 | 33.6%
|  |  |  | WP5 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 6 | 0.75 | 14.25 | 6.404%
|  |  |  | WP6 | 2 | 7.5 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 27.5 | 12.36%
|  |  |  | WP7 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 7.191%
|  |  |  | SUM | 33.25 | 24 | 18 | 17 | 19 | 19 | 10.25 | 18 | 13.25 | 12 | 25.75 | 13 | 222.5 | 100%

## MONITORING TABLE 75%
INNOSUP 1: Monitoring Table 75% requirement
version 23/03/2018
Project: GreenOffshoreTech - GA 101005541
Period covered: from project start date (01/09/2021) to 31/05/2022 - M1-M9 | Deliverable D7.5
***Please read the instructions in Sheet 2 and look at the example in Sheet 3 before completing the table*** | [8 empty] | automatic filling
Section 1 - Direct financial support to SMEs to support innovation | Related WP task | N° of beneficiary SMEs for country 1: (specify country) for period covered | N° of beneficiary SMEs for country 2: (specify country) for period covered | N° of beneficiary SMEs for country 3: (specify country) for period covered | N° of beneficiary SMEs for country 4: (specify country) for period covered | N° of beneficiary SMEs for country 5: (specify country) for period covered | TOTAL n° of beneficiary SMEs for period covered | TOTAL n° of beneficiary SMEs for whole project duration (target) | (Average) cost per individual service (in €) | Total costs for all beneficiary SMEs for period covered | Total budget for all beneficiary SMEs for whole project duration (target) | Beneficiaries: country distribution (for period covered) | Partners involved (in period covered) | Additional information
CALL - cutoff 1: | --- | [5 empty] | --- | --- | --- | --- | --- | --- | --- | ---
Direct funding (lump sums) - PHASE 1 | T3.5 | [5 empty] | 0 | 50 | 5000 | 0 | 250000 | xx SMEs: 10x NO, 8x PL, 6x UK, etc | MNU | Payments done to SMEs.
Direct funding (lump sums) - PHASE 2 | T3.5 | [5 empty] | 0 | 25 | 45000 | 0 | 1125000 | xx SMEs: 5x NO, 4x PL, 3x UK, etc | MNU | Payments done to SMEs.
Direct funding (lump sums) - PHASE 3 | T3.5 | [5 empty] | 0 | 12 | 10000 | 0 | 120000 | xx SMEs: 1x NO, 1x PL, 1x UK, etc | MNU | Payments done to SMEs.
CALL - cutoff 2: | --- | [5 empty] | --- | --- | --- | --- | --- | --- | --- | ---
Direct funding (lump sums) - PHASE 1 | T3.5 | [5 empty] | 0 | 50 | 5000 | 0 | 250000 | xx SMEs: 8x NO, 6x PL, 4x UK, etc | MNU | Payments done to SMEs.
Direct funding (lump sums) - PHASE 2 | T3.5 | [5 empty] | 0 | 25 | 45000 | 0 | 1125000 | xx SMEs: 4x NO, 3x PL, 2x UK, etc | MNU | Payments done to SMEs.
Direct funding (lump sums) - PHASE 3 | T3.5 | [5 empty] | 0 | 13 | 10000 | 0 | 130000 | xx SMEs: 1x NO, 1x PL, 1x UK, etc | MNU | Payments done to SMEs.
Total amounts - section 1 | [6 empty] | 0 | 100 |  | 0 | 3000000
Total of unique SMEs directly assisted (section 1) | [6 empty] | 0 | 100 |  |  |  | xx SMEs: 18x NO, 14x PL, 10x UK, etc.
Section 2 - Direct innovation support (non financial) to individual SMEs | Related WP task | N° of beneficiary SMEs for country 1: (specify country) for period covered | N° of beneficiary SMEs for country 2: (specify country) for period covered | N° of beneficiary SMEs for country 3: (specify country) for period covered | N° of beneficiary SMEs for country 4: (specify country) for period covered | N° of beneficiary SMEs for country 5: (specify country) for period covered | TOTAL n° of beneficiary SMEs for period covered | TOTAL n° of beneficiary SMEs for whole project duration (target) | (Average) cost per individual service (in €) | Total costs for all beneficiary SMEs for period covered | Total budget for all beneficiary SMEs for whole project duration (target) | Beneficiaries: country distribution (for period covered) | Partners involved (in period covered) | Additional information
CALL - cutoff 1+2: | --- | [5 empty] | --- | --- | --- | --- | --- | --- | --- | ---
Delivery of Business Support Service #1 Business & Tech Academy | T4.2 | [5 empty] | 0 | 100 |  | 0 | 104189 | xx SMEs: 18x NO, 14x PL, 10x UK, etc. | MAI (lead), MNU, FOC, CTLV, CKR, CMAB, IOC, HIE, MCN, MEERI, SCA, BAL | Staff costs (direct + indirect)
Delivery of Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | [5 empty] | 0 | 100 |  | 0 | 81036 | xx SMEs: 18x NO, 14x PL, 10x UK, etc. | CMAB (lead), MNU, FOC, CTLV, CKR, CMAB, IOC, HIE, MCN, MEERI, SCA, BAL | Staff costs (direct + indirect)
Delivery of Business Support Service #3 Access to Finance | T4.4 | [5 empty] | 0 | 100 |  | 0 | 43412 | xx SMEs: 18x NO, 14x PL, 10x UK, etc. | HIE (lead), MNU, FOC, CTLV, CKR, MAI, CMAB, IOC, HIE, MCN | Staff costs (direct + indirect)
Delivery of Business Support Service #4 One-to-One Mentoring and Coaching | T4.5 | [5 empty] | 0 | 50 |  | 0 | 59330 | xx SMEs: 9x NO, 7x PL, 5x UK, etc. | SCA (lead) | Staff costs (direct + indirect)
Delivery of Business Support Service #5 Branding | T4.6 | [5 empty] | 0 | 50 |  | 0 | 14471 | xx SMEs: 9x NO, 7x PL, 5x UK, etc. | FOC (lead) | Staff costs (direct + indirect)
Delivery of Business Support Service #6 Internationalisation | T4.7 | [5 empty] | 0 | 50 |  | 0 | 34730 | xx SMEs: 9x NO, 7x PL, 5x UK, etc. | MCN (lead), MNU, FOC, CTLV, CKR, MAI, CMAB, IOC, HIE | Staff costs (direct + indirect)
Delivery of Business Support Service #7 Investor pitching | T4.8 | [5 empty] | 0 | 50 |  | 0 | 40518 | xx SMEs: 9x NO, 7x PL, 5x UK, etc. | CTLV (lead), MNU, HIE, SCA | Staff costs (direct + indirect)
Delivery of Business Support Service #8 Investor rounds | T4.9 | [5 empty] | 0 | 50 |  | 0 | 54989 | xx SMEs: 9x NO, 7x PL, 5x UK, etc. | MNU (lead), FOC, CTLV, CKR, MAI, CMAB, IOC, HIE, MCN, MEERI, SCA, BAL | Staff costs (direct + indirect)
Total amounts - section 2 | [6 empty] | 0 | 100 |  | 0 | 432675
Total of unique SMEs directly assisted (section 2) | [6 empty] | 0 | 100 |  |  |  | xx SMEs: 18x NO, 14x PL, 10x UK, etc.
Total of unique SMEs directly assisted (sections 1 + 2) | [6 empty] | 0 | 100 |  |  |  | xx SMEs: 18x NO, 14x PL, 10x UK, etc.
Section 3 - other innovation services provided to SMEs | Related WP task | [5 empty] | TOTAL n° of SMEs for period covered | TOTAL n° of SMEs for whole project duration (target) |  | Total costs for period covered | Total budget for whole project duration (target) | Number of services (for period covered) | Partners involved (in period covered) | Additional information
Virtual Brockerage Event (?) | T6.2 | [5 empty] | 0 | 100 | --- | 0 | 0 | 1x virtual brockerage event | FOC (lead), MNU, CTLV, CKR, MAI, CMAB, IOC, HIE, MCN, MEERI, SCA, BAL | ---
--- | --- | [5 empty] | --- | --- | --- | --- | --- | --- | --- | ---
--- | --- | [5 empty] | --- | --- | --- | --- | --- | --- | --- | ---
Total amounts - section 3 | [6 empty] | 0 | 100 |  | 0 | 0
Section 4 - costs for preparation / management / monitoring of services in other sections | Related WP task | [5 empty] | --- | --- | --- | Total costs for period covered | Total budget for whole project duration (target) | --- | Partners involved (in period covered) | Additional information
Costs for preparation/ management/ monitoring of services in Section 1+2: | --- | [5 empty] | --- | --- | --- | --- | --- | --- | --- | ---
Costs for preparation of the Topics for the Call for Proposals | T1.1, T1.2, T1.3 | [5 empty] | --- | --- | --- | 110616 | 213716 | --- | MEERI (lead), HIE (lead), MNU, FOC, CTLV, CKR, MAI, CMAB, IOC, MCN, SCA, BAL | Staff costs (direct + indirect)
Cost for preparation of the Cluster Collaboration Platform for managing the open Call, the development of the new Virtual Matchmaking tool, and the estbalishment of a Virtual Collaboration Environment | T2.1, T2.2, T2.3, T2.4 | [5 empty] | --- | --- | --- | 67975 | 145038 | --- | HIE (lead), BAL (lead), CKR (lead), MNU, FOC, CTLV, MAI, CMAB, IOC, MCN, SCA | Staff costs (direct + indirect)
Costs for preparation, evaluation and monitoring of the Call for Proposals and the winner SMEs Projects | T3.1, T3.2, T3.3, T3.4, T3.5, T3.6 | [5 empty] | --- | --- | --- | 87880 | 423719 | --- | CKR (lead), BAL (lead), MNU (lead), SCA (lead), FOC, CTLV, MAI, CMAB, ICO, HIE, MCN, MEERI | Staff costs (direct + indirect)
Costs for preparation and monitoring of the Business Support Services | T4.1, T4.2, T4.3, T4.4, T4.5, T4.6, T4.7, T4.8, T4.9 | [5 empty] | --- | --- | --- | 21953 | 332827 | --- | MAI (lead), MNU (lead), FOC (lead), CTLV(lead), CMAB (lead), HIE (lead), MCN (lead), SCA (lead), IOC, CKR, MEERI, BAL | Staff costs (direct + indirect)
Costs for preparation and monitoring of the Large-scale Demonstrator | T5.1, T5.2, T5.3 | [5 empty] | --- | --- | --- | 42546 | 136613 | --- | SCA (lead), MNU, FOC, CTLV, CKR, MAI, CMAB, IOC, HIE, MCN, MEERI, BAL | Staff costs (direct + indirect)
Total amounts - section 4 | [9 empty] | 330970 | 1251913
Section 5 - costs of SME partners in the consortium not declared in sections 1,2, 3 and 4 | Related WP task | [5 empty] | --- | --- | --- | Total costs for period covered | Total budget for whole project duration (target) | --- | Partners involved (in period covered) | Additional information
Partner 7 - IOC | T6.1 | [5 empty] | --- | --- | --- | 4821 | 4685 | Reviews, workshop support. | FOC, IOC
Partner 11 - SCA | T7.1, T7.2,T7.3, T6.1 | [5 empty] | --- | --- | --- | 6548 | 0 | Reviews, workshop support. | FOC, SCA, MNU | No Allocated budget for T6.1, T7.1, T7.2 and T7.3 (spending of 6548 Euro without prior clarification from WP owners).
Partner 12 - BAL | --- | [5 empty] | --- | --- | --- | 0 | 0 | --- | --- | ---
Total amounts - section 5 | [9 empty] | 11369 | 4685
GRAND TOTAL | [9 empty] | Total innovation support costs for period covered | Total innovation support budget for whole project duration (target) |  |  | Additional information
sections 1 to 5 | [9 empty] | 342339 | 4689273
Total budget of the project (in €): | 5253231.25
Total budget of the project to be allocated to support innovation in SMEs (in €): | 4689273 |  | € |  |  |  | imported from GRAND TOTAL
% of costs to be allocated to support innovation in SMEs vs total costs: | 89.26% |  | #VALUE! |  |  |  | minimum 75% of total budget
% of costs allocated to support innovation in SMEs in the period covered vs total budget: | 6.517% | [5 empty] | Total innovation support costs for period covered from GRAND TOTAL divided by total budget of the project
#REF!

## Direct &Indirect Personnal Cost
ALL DIRECT & INDIRECT COST CALCULATIONS PER PARTNER | [25 empty] | 7266
TOTAL BUDGET IS NOT EQUAL TO EC CONTRIBUTION DUE TO THE SME PARTNERS
70%. Delivered Hourly cost estimate and Budget allocation.
GreenOfshoreTech TOTAL (Period M1 to M9) | Task/ WP | TOTAL COST | Other Dir. Cost Budget | TOTAL BUDGET | % spend | MNU COST | Other Dir. Cost Budget |  | % spend | SCA COST | Other Dir. Cost Budget | SCA BUDGET | % spend | FOC COST | Other Dir. Cost Budget | FOC BUDGET | % spend | CTLV COST | Other Dir. Cost Budget | CTLV BUDGET | % spend | MAI COST | Other Dir. Cost | Revised MAI BUDGET | MAI BUDGET | % spend | BIN COST | Other Dir. Cost | BIN BUDGET | % spend | IOC COST | Other Dir. Cost | IOC BUDGET | % spend | HIE COST | Other Dir. Cost | HIE BUDGET | % spend | BAL COST | Other Dir. Cost | BAL BUDGET | % spend | MEERI COST | Other Dir. Cost | MEERI BUDGET | % spend | MCN COST | Other Dir. Cost | MCN BUDGET | % spend | CKR COST | Other Dir. Cost | CKR BUDGET | % spend
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ODC | 5763.75 |  | 343929 | 1.6759 | 0 |  | 39500 | 0 | 0 |  | 20750 | 0 | 0 |  | 42500 | 0 | 0 |  | 20750 | 0 | 0 |  | 20750 | 20750 | 0 | 0 |  | 56429 | 0 | 0 |  | 20750 | 0 | 5763.75 |  | 20750 | 27.7771 | 0 |  | 20750 | 0 | 0 |  | 20750 | 0 | 0 |  | 39500 | 0 | 0 |  | 20750 | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 104301.9925 | 31600 | 226991.17 | 45.9498 | 8024.875 | 31600 | 20062.5 | 39.9994 | 13497.1651 | 0 | 11712.46 | 115.2377 | 1875.625 | 0 | 7790.62 | 24.0754 | 6823.4177 | 0 | 10546.88 | 64.6961 | 12627.3375 | 0 | 31484.38 | 31484.38 | 40.1067 | 13000.7375 | 0 | 36562.5 | 35.5576 | 2402.5312 | 0 | 17306.54 | 13.8822 | 12255.2459 | 0 | 23906.25 | 51.2638 | 13402.8875 | 0 | 12375 | 108.3062 | 8319.05 | 0 | 13406.25 | 62.0535 | 7696.99 | 0 | 10312.5 | 74.6375 | 4376.13 | 0 | 14218.75 | 30.7772
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 41306.53 | 31600 | 88440.74 | 46.7053 | 3265.9375 | 31600 | 13375 | 24.4182 | 6648.4552 |  | 5856.22 | 113.5281 | 780.13 |  | 3462.5 | 22.5308 | 508.6807 |  | 4687.5 | 10.8519 | 0 |  | 2421.88 | 2421.88 | 0 | 2578.095 |  | 2812.5 | 91.6656 | 310.5312 |  | 11537.57 | 2.6915 | 11586.2678 |  | 18593.75 | 62.3127 | 7215.3875 |  | 6187.5 | 116.6123 | 307.44 |  | 0 | #DIV/0! | 6508.745 |  | 6875 | 94.6727 | 1596.86 |  | 1093.75 | 145.9986
Assessment of emerging technology trends and solutions | T1.2 | 29037.419 | 0 | 53116.01 | 54.6679 | 1399.6875 |  | 3343.75 | 41.8598 | 3484.4313 |  | 2928.12 | 118.9989 | 194.2 |  | 865.62 | 22.4348 | 2541.4263 |  | 1171.88 | 216.8675 | 5070.8375 |  | 9687.5 | 9687.5 | 52.3441 | 5960.02 |  | 11250 | 52.978 | 1470.9375 |  | 2884.57 | 50.9933 | 411.6788 |  | 2656.25 | 15.4985 | 3093.75 |  | 3093.75 | 100 | 4060.45 |  | 6256.25 | 64.9023 | 0 |  | 1718.75 | 0 | 1350 |  | 4375 | 30.8571
Potential new value chains and selection of Call Topics | T1.3 | 30982.7711 | 0 | 85434.42 | 36.265 | 3359.25 |  | 3343.75 | 100.4636 | 3364.2785 |  | 2928.12 | 114.8955 | 526.17 |  | 3462.5 | 15.1962 | 3773.3108 |  | 4687.5 | 80.4973 | 7556.5 |  | 19375 | 19375 | 39.0013 | 1862.475 |  | 22500 | 8.2777 | 621.0625 |  | 2884.4 | 21.5318 | 257.2993 |  | 2656.25 | 9.6866 | 3093.75 |  | 3093.75 | 100 | 3951.16 |  | 7150 | 55.261 | 1188.245 |  | 1718.75 | 69.1343 | 1429.27 |  | 8750 | 16.3345
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 67811.8909 | 0 | 153493.81 | 44.1789 | 5346.8063 | 0 | 6687.5 | 79.9522 | 3123.9729 | 0 | 5856.22 | 53.3445 | 174.2875 | 0 | 8656.24 | 2.0134 | 3711.9305 | 0 | 11718.76 | 31.6751 | 0 | 0 | 4843.76 | 4843.76 | 0 | 653.5 | 0 | 5625 | 11.6178 | 555.6875 | 0 | 5768.79 | 9.6327 | 15281.059 | 0 | 37187.5 | 41.0919 | 30049.1875 | 0 | 47406.25 | 63.3866 | 1776.61 | 0 | 1787.5 | 99.3908 | 565.24 | 0 | 3437.5 | 16.4433 | 6573.6097 | 0 | 8750 | 75.127
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 19605.4587 | 0 | 67887.51 | 28.8793 | 1306.375 |  | 3343.75 | 39.0692 | 40.0509 |  | 2928.1 | 1.3678 | 0 |  | 4328.12 | 0 | 1816.2619 |  | 5859.38 | 30.9975 | 0 |  | 2421.88 | 2421.88 | 0 | 130.7 |  | 2812.5 | 4.6471 | 0 |  | 2884.39 | 0 | 14637.8109 |  | 34531.25 | 42.39 | 0 |  | 0 | #DIV/0! | 1115.02 |  | 893.75 | 124.7575 | 559.24 |  | 1718.75 | 32.5376 | 0 |  | 3281.25 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 5204.3416 | 0 | 3343.75 | 155.6439 | 4040.4313 |  | 3343.75 | 120.8353 | 520.6622 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 643.2482 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Establishment of a Survey tool | T2.3 | 10794.0294 | 0 | 12525 | 86.1799 | 0 |  | 0 | #DIV/0! | 1321.6809 |  | 0 | #DIV/0! | 139.43 |  | 3462.5 | 4.0269 | 1895.6686 |  | 4687.5 | 40.4409 | 0 |  | 0 | 0 | #DIV/0! | 196.05 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 661.59 |  | 0 | #DIV/0! | 6 |  | 0 | #DIV/0! | 6573.61 |  | 4375 | 150.2539
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 32291.6467 | 0 | 69737.55 | 46.3045 | 0 |  | 0 | #DIV/0! | 1241.579 |  | 2928.12 | 42.4019 | 0 |  | 865.62 | 0 | 249.1427 |  | 1171.88 | 21.2601 | 0 |  | 2421.88 | 2421.88 | 0 | 196.05 |  | 2812.5 | 6.9707 | 555.6875 |  | 2884.4 | 19.2653 | 0 |  | 2656.25 | 0 | 30049.1875 |  | 47406.25 | 63.3866 | 0 |  | 893.75 | 0 | 0 |  | 1718.75 | 0 | 0 |  | 1093.75 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 84177.4616 | 91428.57 | 3434125.12 | 2.4512 | 1306.375 | 0 | 3094375 | 0.042218 | 11374.4655 | 8000 | 52706.11 | 21.5809 | 2002.375 | 8000 | 8656.25 | 23.1321 | 962.4105 | 8000 | 16406.25 | 5.8661 | 0 | 8000 | 33906.25 | 33906.25 | 0 | 1364.2125 | 11428.57 | 39375 | 3.4647 | 1307.5 | 8000 | 28843.88 | 4.533 | 6539.2514 | 8000 | 26562.5 | 24.6184 | 34570.4875 | 8000 | 48500 | 71.2794 | 2131.5 | 8000 | 12512.5 | 17.035 | 2898.055 | 8000 | 17187.5 | 16.8614 | 19720.8291 | 8000 | 26250 | 75.127
Preparation of the Call for Proposals | T3.1 | 47109.1197 | 19000 | 68475.03 | 68.7975 | 559.875 | 0 | 6687.5 | 8.372 | 10613.4978 | 1000 | 5856.22 | 181.2346 | 1601.9 | 2000 | 1731.25 | 92.5285 | 962.4105 | 1000 | 2343.75 | 41.0628 | 0 | 1000 | 4843.75 | 4843.75 | 0 | 653.5 | 2000 | 5625 | 11.6178 | 1046 | 2000 | 5768.78 | 18.1321 | 1628.0514 | 2000 | 5312.5 | 30.6457 | 6187.5 | 1000 | 6187.5 | 100 | 2131.5 | 2000 | 1787.5 | 119.2448 | 2004.055 | 2000 | 3437.5 | 58.2998 | 19720.83 | 3000 | 13125 | 150.2539
Publication of the Call for Proposals and Proposal reception. | T3.2 | 14557.7603 | 2000 | 18562.5 | 78.4256 | 466.5625 | 0 | 6687.5 | 6.9766 | 760.9678 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | 0 | #DIV/0! | 673.13 |  | 0 | #DIV/0! | 261.5 |  | 0 | #DIV/0! | 4911.2 |  | 0 | #DIV/0! | 7484.4 | 2000 | 11875 | 63.0265 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Evaluation and Selection of SMEs Proposals | T3.3 | 15885.025 | 33000 | 121637.57 | 13.0593 | 279.9375 | 0 | 13750 | 2.0359 | 0 | 2000 | 11712.47 | 0 | 0 | 3000 | 3462.5 | 0 | 0 | 3000 | 4687.5 | 0 | 0 | 3000 | 9687.5 | 9687.5 | 0 | 0 | 5000 | 11250 | 0 | 0 | 3000 | 11537.55 | 0 | 0 | 3000 | 10625 | 0 | 14711.0875 | 3000 | 18562.5 | 79.2516 | 0 | 3000 | 3575 | 0 | 894 | 3000 | 6875 | 13.0036 | 0 | 2000 | 4375 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 26750 | 0 | 0 | 0 | 26750 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 3026750 | 0 | 0 | 0 | 3026750 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Technical monitoring of winner SMEs Projects | T3.6 | 6187.5 | 37428.57 | 171950.02 | 3.5984 | 0 | 0 | 13750 | 0 | 0 | 5000 | 35137.42 | 0 | 0 | 3000 | 3462.5 | 0 | 0 | 4000 | 9375 | 0 | 0 | 4000 | 19375 | 19375 | 0 | 0 | 4428.57 | 22500 | 0 | 0 | 3000 | 11537.55 | 0 | 0 | 3000 | 10625 | 0 | 6187.5 | 2000 | 11875 | 52.1053 | 0 | 3000 | 7150 | 0 | 0 | 3000 | 6875 | 0 | 0 | 3000 | 8750 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 21789.2283 | 151514.29 | 701740.32 | 3.105 | 6681.175 | 0 | 73562.5 | 9.0823 | 2723.4636 | 8000 | 149334.17 | 1.8237 | 58.1 | 26000 | 29431.25 | 0.19741 | 595.1947 | 8600 | 32812.5 | 1.8139 | 4120.2875 | 8600 | 77500 | 77500 | 5.3165 | 653.5 | 33714.29 | 101250 | 0.64543 | 0 | 8600 | 34612.7 | 0 | 0 | 8600 | 74374.5 | 0 | 5126.7875 | 8600 | 30937.5 | 16.5714 | 661.59 | 8600 | 8937.5 | 7.4024 | 1169.13 | 23600 | 41250 | 2.8343 | 0 | 8600 | 13125 | 0
Programme of Business Support Services to winner SMEs | T4.1 | 8330.8886 | 1000 | 24218.75 | 34.3985 | 933.125 | 0 | 0 | #DIV/0! | 2403.0561 |  | 0 | #DIV/0! | 46.48 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 4120.2875 | 1000 | 24218.75 | 24218.75 | 17.0128 | 65.35 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 661.59 |  | 0 | #DIV/0! | 101 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Business Support Service #1 Business & Tech Academy | T4.2 | 5322.8375 | 44600 | 170550.08 | 3.121 | 0 | 0 | 13375 | 0 | 0 | 1000 | 11712.46 | 0 | 0 | 5000 | 3462.5 | 0 | 0 | 2000 | 4687.5 | 0 | 0 | 5000 | 29062.5 | 29062.5 | 0 | 196.05 | 10000 | 39375 | 0.4979 | 0 | 3000 | 11537.56 | 0 | 0 | 1000 | 10625 | 0 | 5126.7875 | 4600 | 18562.5 | 27.6191 | 0 | 6000 | 5362.5 | 0 | 0 | 5000 | 6875 | 0 | 0 | 2000 | 4375 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 261.4 | 34100 | 113875.05 | 0.22955 | 0 | 0 | 6687.5 | 0 | 0 | 1000 | 5856.24 | 0 | 0 | 10000 | 13850 | 0 | 0 | 2000 | 2343.75 | 0 | 0 | 500 | 9687.5 | 9687.5 | 0 | 261.4 | 10000 | 45000 | 0.58089 | 0 | 1500 | 5768.78 | 0 | 0 | 1000 | 5312.5 | 0 | 0 | 2000 | 6187.5 | 0 | 0 | 1600 | 1787.5 | 0 | 0 | 2500 | 3437.5 | 0 | 0 | 2000 | 2187.5 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 10700 | 70268.81 | 0 | 0 | 0 | 6687.5 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 1731.25 | 0 | 0 |  | 2343.75 | 0 | 0 | 100 | 4843.75 | 4843.75 | 0 | 0 | 4000 | 5625 | 0 | 0 | 1500 | 5768.78 | 0 | 0 | 2600 | 31875 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 | 2500 | 3437.5 | 0 | 0 |  | 2187.5 | 0
Business Support Service #4 One-to-One Mentoring and Coaching | T4.5 | 359.9075 | 6000 | 114196.76 | 0.31516 | 0 | 0 | 0 | #DIV/0! | 320.4075 | 6000 | 114196.76 | 0.28057 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 39.5 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Business Support Service #5 Branding | T4.6 | 230.555 | 4000 | 6925 | 3.3293 | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 | 4000 | 6925 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 230.555 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Business Support Service #6 Internationalisation | T4.7 | 798.075 | 19800 | 54018.33 | 1.4774 | 0 | 0 | 6687.5 | 0 | 0 |  | 0 | #DIV/0! | 0 | 3000 | 1731.25 | 0 | 0 | 1000 | 2343.75 | 0 | 0 | 1000 | 4843.75 | 4843.75 | 0 | 0 | 4000 | 5625 | 0 | 0 | 1800 | 5768.79 | 0 | 0 | 1000 | 5312 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 798.075 | 6000 | 13750 | 5.8042 | 0 | 2000 | 2187.5 | 0
Business Support Service #7 Investor pitching | T4.8 | 595.1947 | 5000 | 53087.47 | 1.1212 | 0 | 0 | 6687.5 | 0 | 0 |  | 11712.47 | 0 | 0 |  | 0 | #DIV/0! | 595.1947 | 3000 | 18750 | 3.1744 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 | 2000 | 15937.5 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Business Support Service #8 Investor rounds | T4.9 | 5748.05 | 26314.29 | 94600.07 | 6.0762 | 5748.05 | 0 | 33437.5 | 17.1904 | 0 |  | 5856.24 | 0 | 0 | 4000 | 1731.25 | 0 | 0 | 600 | 2343.75 | 0 | 0 | 1000 | 4843.75 | 4843.75 | 0 | 0 | 5714.29 | 5625 | 0 | 0 | 800 | 5768.79 | 0 | 0 | 1000 | 5312.5 | 0 | 0 | 2000 | 6187.5 | 0 | 0 | 1000 | 1787.5 | 0 | 0 | 7600 | 13750 | 0 | 0 | 2600 | 2187.5 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 42546.3243 | 0 | 148095.23 | 28.729 | 4189.7313 | 0 | 10331.25 | 40.554 | 33402.4798 | 0 | 70274.73 | 47.5313 | 87.15 | 0 | 2596.86 | 3.356 | 700.0901 | 0 | 3515.64 | 19.9136 | 0 | 0 | 7265.64 | 7265.64 | 0 | 0 | 0 | 8436 | 0 | 359.5625 | 0 | 8653.18 | 4.1553 | 0 | 0 | 7968.75 | 0 | 0 | 0 | 9281.25 | 0 | 1742.07 | 0 | 2681.25 | 64.9723 | 1627 | 0 | 5156.25 | 31.5539 | 438.2406 | 0 | 3281.25 | 13.3559
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 40961.1874 | 0 | 55221.35 | 74.1764 | 2874.025 |  | 3443.75 | 83.4563 | 33402.4798 |  | 29281.19 | 114.0749 | 69.72 |  | 865.62 | 8.0543 | 700.0901 |  | 1171.88 | 59.7408 | 0 |  | 2421.88 | 2421.88 | 0 | 0 |  | 2812 | 0 | 359.5625 |  | 2884.39 | 12.4658 | 0 |  | 2656.25 | 0 | 0 |  | 3093.75 | 0 | 1742.07 |  | 893.75 | 194.9169 | 1375 |  | 1718.75 | 80 | 438.24 |  | 1093.75 | 40.0677
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 771.5 | 0 | 55221.35 | 1.3971 | 746.5 |  | 3443.75 | 21.677 | 0 |  | 29281.19 | 0 | 0 |  | 865.62 | 0 | 0 |  | 1171.88 | 0 | 0 |  | 2421.88 | 2421.88 | 0 | 0 |  | 2812 | 0 | 0 |  | 2884.39 | 0 | 0 |  | 2656.25 | 0 | 0 |  | 3093.75 | 0 | 0 |  | 893.75 | 0 | 25 |  | 1718.75 | 1.4545 | 0 |  | 1093.75 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 796.2062 | 0 | 37652.53 | 2.1146 | 569.2062 |  | 3443.75 | 16.5287 | 0 |  | 11712.35 | 0 | 0 |  | 865.62 | 0 | 0 |  | 1171.88 | 0 | 0 |  | 2421.88 | 2421.88 | 0 | 0 |  | 2812 | 0 | 0 |  | 2884.4 | 0 | 0 |  | 2656.25 | 0 | 0 |  | 3093.75 | 0 | 0 |  | 893.75 | 0 | 227 |  | 1718.75 | 13.2073 | 0 |  | 1093.75 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 56406.8404 | 0 | 231218.95 | 24.3954 | 8425.1856 | 0 | 26750 | 31.496 | 5847.4365 | 0 | 11712.44 | 49.925 | 25103.8625 | 0 | 25968.75 | 96.6695 | 3337.7579 | 0 | 9375 | 35.6028 | 4596 | 0 | 29062.5 | 29062.5 | 15.8142 | 408.4375 | 0 | 22500 | 1.8153 | 4821.4062 | 0 | 23075.13 | 20.8944 | 2261.1825 | 0 | 21250 | 10.6409 | 0 | 0 | 12375 | 0 | 590.43 | 0 | 3575 | 16.5155 | 620.725 | 0 | 13750 | 4.5144 | 394.4166 | 0 | 8750 | 4.5076
Communication plan and Communication activities | T6.1 | 39381.405 | 0 | 55825.06 | 70.5443 | 6531.875 |  | 6687.5 | 97.6729 | 4886.2141 |  | 0 | #DIV/0! | 16847.5 |  | 13850 | 121.6426 | 459.2447 |  | 2343.75 | 19.5944 | 4596 |  | 4843.75 | 4843.75 | 94.8852 | 326.75 |  | 5625 | 5.8089 | 4821.4062 |  | 5768.78 | 83.5776 | 0 |  | 5312.5 | 0 | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 514.315 |  | 3437.5 | 14.9619 | 398.1 |  | 2187.5 | 18.1989
Dissemination strategy and Dissemination activities | T6.2 | 10860.0632 | 0 | 108168.84 | 10.0399 | 933.125 |  | 13375 | 6.9766 | 961.2224 |  | 5856.22 | 16.4137 | 3235.59 |  | 10387.5 | 31.1489 | 2878.5132 |  | 4687.5 | 61.4083 | 0 |  | 9687.5 | 9687.5 | 0 | 0 |  | 11250 | 0 | 0 |  | 11537.56 | 0 | 2261.1825 |  | 10625 | 21.2817 | 0 |  | 6187.5 | 0 | 590.43 |  | 1787.5 | 33.031 | 0 |  | 6875 | 0 | 0 |  | 4375 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 1066.5956 | 0 | 67225.05 | 1.5866 | 960.1856 |  | 6687.5 | 14.3579 | 0 |  | 5856.22 | 0 | 0 |  | 1731.25 | 0 | 0 |  | 2343.75 | 0 | 0 |  | 14531.25 | 14531.25 | 0 | 0 |  | 5625 | 0 | 0 |  | 5768.79 | 0 | 0 |  | 5312.5 | 0 | 0 |  | 6187.5 | 0 | 0 |  | 1787.5 | 0 | 106.41 |  | 3437.5 | 3.0956 | 0 |  | 2187.5 | 0
Project Management and Coordination | WP7 | 115933.4329 | 0 | 214000 | 54.1745 | 108068.0056 | 0 | 214000 | 50.4991 | 1682.1393 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 367.5938 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 5531.9342 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 283.76 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Project coordination | T7.1 | 42675.2639 | 0 | 147125 | 29.0061 | 37674.9219 |  | 147125 | 25.6074 | 240.3056 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 4760.0364 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Project administration & Financial Management | T7.2 | 50402.5615 | 0 | 46812.5 | 107.669 | 48909.7469 |  | 46812.5 | 104.4801 | 720.9168 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 771.8978 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
Quality Assurance | T7.3 | 22782.0887 | 0 | 20062.5 | 113.5556 | 21483.3369 |  | 20062.5 | 107.0821 | 720.9168 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | 0 | #DIV/0! | 294.075 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0! | 283.76 |  | 0 | #DIV/0! | 0 |  | 0 | #DIV/0!
TOTAL |  | 498613.6832 | 274542.86 | 5453593.6 | 9.1428 | 142042.1538 | 31600 | 3485268.75 | 4.0755 | 71651.1227 | 16000 | 322346.13 | 22.228 | 29301.4 | 34000 | 125599.97 | 23.3291 | 16130.8013 | 16600 | 105125.03 | 15.3444 | 21343.625 | 16600 | 204812.53 | 204812.53 | 10.4211 | 16447.9812 | 45142.86 | 270177.5 | 6.0878 | 9446.6875 | 16600 | 139010.22 | 6.7957 | 47632.4232 | 16600 | 211999.5 | 22.4682 | 83149.35 | 16600 | 181625 | 45.7808 | 15221.25 | 16600 | 63650 | 23.914 | 14743.6624 | 31600 | 130593.75 | 11.2897 | 31503.2261 | 16600 | 95125 | 33.1177
Total budget of the project |  |  |  | 5253231
Budget WP1-5 |  |  |  | 4664445.65 | Without travel cost
% Cost Allocated to the SMEs |  | 88.79%
FOC
BAL
MCN
HIE
IOC
MAI
CTLV
MNU
SCA
MEERI
CKR
BIN
TOTAL
All Direct & Indirect Cost (EUR)
ACTUAL & BUDGET

## MNU
TOTAL COSTS
|  | Dir & Indir (EUR) | [14 empty] | 81 | 101
|  | ACTUAL | [14 empty] | AMD2 | AMD2
GreenOfshoreTech MNU (Period M1 to M10) | Task/ | M1-M10 | [14 empty] | For BUDGET | For 75% RULE
| WP | [10 empty] | ORG = | ORG = |  |  |  | Direct monthly rate | Direct monthly rate
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | [11 empty] | AMD1 | AMD1 | AMD2 | AMD2 | AMD2 | 11610 | 11610 | Confirmed rate | 81 Euro per hour
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 8024.875 | [9 empty] | BUDGET | BUDGET | REVISION | REVISION |  | REVISION | REVISION
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 3265.9375 | [8 empty] | Task/ |  |  | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT)
Assessment of emerging technology trends and solutions | T1.2 | 1399.6875 | Budget rate |  | Actual |  |  | 1PM iequals to | 143.333 |  | WP | PM | hours | PMs | Hours |  | EUR | EUR
Potential new value chains and selection of Call Topics | T1.3 | 3359.25 | Project manager |  | Project manager |  |  |  |  | Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 1.5 | 215 | 0.7 | 100.3333 | minus 0.8 PM | 8025 | 10031.25
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 5346.8063 | hrs | Salery rate | hrs | Salery rate |  |  |  | Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 1 | 143.3333 | 0.29 | 41.5667 | minus 0.71 PM | 3266 | 4082.5
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1306.375 |  | 74.65 |  | 82 |  |  |  | Assessment of emerging technology trends and solutions | T1.2 | 0.25 | 35.8333 | 0.12 | 17.2 | minus 0.13 PM | 1400 | 1750
Establishment of a Collaborative Virtual Environment | T2.2 | 4040.4313 | 86 | 6419.9 | 0 | 0 | PM | 0.6 |  | Potential new value chains and selection of Call Topics | T1.3 | 0.25 | 35.8333 | 0.29 | 41.5667 | plus 0.04 PM | 3359 | 4198.75
Establishment of a Survey tool | T2.3 | 0 | 35 | 2612.75 | 0 | 0 |  |  |  | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 0.5 | 71.6667 | 0.46 | 65.9333 | minus 0.04 PM | 5346 | 6682.5
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 15 | 1119.75 | 0 | 0 |  |  |  | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0.25 | 35.8333 | 0.11 | 15.7667 | minus 0.14 PM | 1306 | 1632.5
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 1306.375 | 36 | 2687.4 | 0 | 0 |  |  |  | Establishment of a Collaborative Virtual Environment | T2.2 | 0.25 | 35.8333 | 0.35 | 50.1667 | plus 0.1 0PM | 4040 | 5050
Preparation of the Call for Proposals | T3.1 | 559.875 | 57.3 | 4277.445 |  | 0 | PM | 0.4 |  | Establishment of a Survey tool | T2.3 | 0 | 0 | 0 | 0 | OK | 0 | 0
Publication of the Call for Proposals and Proposal reception. | T3.2 | 466.5625 | 14 | 1045.1 | 0 | 0 |  |  |  | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 0 | 0 | 0 | OK | 0 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 279.9375 | 43.3 | 3232.345 | 0 | 0 |  |  |  | Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 7 | 1003.3333 | 7 | 1003.3333 |  | 94376 | 117970
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 | 0 |  |  |  | Preparation of the Call for Proposals | T3.1 | 0.5 | 71.6667 | 0.5 | 71.6667 | OK | 6688 | 8360
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 | 0 |  |  |  | Publication of the Call for Proposals and Proposal reception. | T3.2 | 0.5 | 71.6667 | 0.5 | 71.6667 | OK | 6688 | 8360
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 14 | 1045.1 | 0 | 0 | PM | 0.1 |  | Evaluation and Selection of SMEs Proposals | T3.3 | 1 | 143.3333 | 1 | 143.3333 | OK | 13750 | 17187.5
Business Support Services to winner SMEs (preparation) | WP4 | 6681.175 | 6 | 447.9 | 0 | 0 |  |  |  | Contracting with winner SMEs Projects | T3.4 | 2 | 286.6667 | 2 | 286.6667 | Ok. | 26750 | 33437.5
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 933.125 | 5 | 373.25 | 0 | 0 |  |  |  | Payments and financial monitoring of winner SMEs Projects | T3.5 | 2 | 286.6667 | 2 | 286.6667 | Ok. | 26750 | 33437.5
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 3 | 223.95 | 0 | 0 |  |  |  | Technical monitoring of winner SMEs Projects | T3.6 | 1 | 143.3333 | 1 | 143.3333 | Ok | 13750 | 17187.5
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 | 0 | 0 | 0 |  |  |  | Business Support Services to winner SMEs | WP4 | 5.5 | 788.3333 | 4.36 | 624.9333 | minus 0.66 PM | 56059 | 70073.75
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 0 | 0 | 0 |  |  |  | Programme of Business Support Services to winner SMEs | T4.1 | 0 | 0 | 0.08 | 11.4667 | plus 0,08 PM | 933 | 1166.25
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | 0 | 0 | 0 |  |  |  | Business Support Service #1 Business & Tech Academy | T4.2 | 1 | 143.3333 | 0.17 | 24.3667 | minus 0,83 PM | 2000 | 2500
Business Support Service #5 Branding | T4.6 | 0 | 71.6 | 5344.94 |  | 0 | PM | 0.5 |  | Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0.5 | 71.6667 | 0.34 | 48.7333 | minus 0.16 PM | 4000 | 5000
Business Support Service #6 Internationalisation | T4.7 | 0 | 10 | 746.5 | 0 | 0 |  |  |  | Business Support Service #3 Access to Finance | T4.4 | 0.5 | 71.6667 | 0.17 | 24.3667 | minus 0.33 PM | 2000 | 2500
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0 | 0 | 0 |  |  |  | Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 0 | 0 | 0.17 | 24.3667 | plus 0.17 PM | 2000 | 2500
Business Support Service #8 Investor rounds | T4.9 | 5748.05 | 0 | 0 | 0 | 0 |  |  |  | Business Support Service #5 Branding | T4.6 | 0 | 0 | 0.17 | 24.3667 | plus 0.17 PM | 2000 | 2500
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 4189.7313 | 0 | 0 | 0 | 0 |  |  |  | Business Support Service #6 Internationalisation | T4.7 | 0.5 | 71.6667 | 0.26 | 37.2667 | plus 0.24 PM | 3000 | 3750
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 2874.025 | 0 | 0 | 0 | 0 |  |  |  | Business Support Service #7 Investor pitching | T4.8 | 0.5 | 71.6667 | 0.5 | 71.6667 | OK | 6688 | 8360
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 746.5 | 0 | 0 | 0 | 0 |  |  |  | Business Support Service #8 Investor rounds | T4.9 | 2.5 | 358.3333 | 2.5 | 358.3333 | OK | 33438 | 41797.5
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 569.2062 | 0 | 0 | 0 | 0 |  |  |  | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0.75 | 107.5 | 0.3465 | 49.665 | minus 0,4 PM | 4190 | 5237.5 |  |  | Verify below this line.
Communication, Dissemination, Exploitation & Sustainability | WP6 | 8425.1856 | 0 | 0 | 0 | 0 |  |  |  | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0.25 | 35.8333 | 0.2475 | 35.475 | OK | 2874 | 3592.5
Communication plan and Communication activities | T6.1 | 6531.875 | 61.6 | 4598.44 | 0 | 0 |  |  |  | Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 0.25 | 35.8333 | 0.05 | 7.1667 | minus 0.20 PM | 747 | 933.75
Dissemination strategy and Dissemination activities | T6.2 | 933.125 | 44.9 | 3351.785 |  | 0 | PM | 0.31 |  | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0.25 | 35.8333 | 0.049 | 7.0233 | minus 0.20 PM | 569 | 711.25
Exploitation strategy, IPR and Sustainability | T6.3 | 960.1856 | 30.8 | 2299.22 | 0 | 0 |  |  |  | Communication, Dissemination, Exploitation & Sustainability | WP6 | 2 | 286.6667 | 1.506 | 215.86 | minus 0,65 PM | 17492 | 21865
Project Management and Coordination | WP7 | 108068.0056 | 8 | 597.2 | 0 | 0 |  |  |  | Communication plan and Communication activities | T6.1 | 0.5 | 71.6667 | 0.562 | 80.5533 | plus 0,01 PM | 6532 | 8165
Project coordination | T7.1 | 37674.9219 | 6.1 | 455.365 | 0 | 0 |  |  |  | Dissemination strategy and Dissemination activities | T6.2 | 1 | 143.3333 | 0.8613 | 123.453 | minus 0.24 PM | 10000 | 12500
Project administration & Financial Management | T7.2 | 48909.7469 | 90.29 | 6740.1485 |  | 0 | PM | 0.63 |  | Exploitation strategy, IPR and Sustainability | T6.3 | 0.5 | 71.6667 | 0.0827 | 11.8537 | minus 0.42 PM | 960 | 1200
Quality Assurance | T7.3 | 21483.3369 | 70 | 5225.5 | 0 | 0 |  |  |  | Project Management and Coordination | WP7 | 16 | 2293.3333 | 17.0624 | 2445.6107 | plus 1,06 PM | 198093 | 247616.25
TOTAL |  | 142042.1538 | 10 | 746.5 | 0 | 0 |  |  |  | Project coordination | T7.1 | 11 | 1576.6667 | 10.9992 | 1576.552 | OK | 127700 | 159625
|  |  | 10.29 | 768.1485 | 0 | 0 |  |  |  | Project administration & Financial Management | T7.2 | 3.5 | 501.6667 | 4.2128 | 603.8347 | plus 0,71 PM | 48910 | 61137.5
|  |  | 1158.13 | 86454.4045 |  | 0 | PM | 8.08 |  | Quality Assurance | T7.3 | 1.5 | 215 | 1.8504 | 265.224 | plus 0,35 PM | 21483 | 26853.75
|  |  | 403.75 | 30139.9375 | 0 | 0 |  |  |  | NOTE: Key Tasks are marked light green |  | 33.25 | 4765.8333 | 31.4349 | 4505.669 |  | 383581 | 479476.25
|  |  | 524.15 | 39127.7975 | 0 | 0
|  |  | 230.23 | 17186.6695 | 0 | 0
|  |  | 1522.22 | 113633.723 | 0 | 0 | PM | 10.62
Table to the left is active as partner input to sheet Direct & Indirect Personnal Cost
Column C is budgeted PM, column D is hours is assuming 1720 or 1 PM=143.333
COMPLETE COLUMN E TIL I for the AMD2
According to your re-allocation and salary cost.

## SCA
0 | [10 empty] | TOTAL COSTS
[7 empty] | Hourly rate 65,37 | Hourly rate 81,71
[7 empty] | AMD2 | AMD2
[7 empty] | For BUDGET | For 75% RULE
|  | ORG = | ORG = |  |  |  | Direct monthly rate | Direct monthly rate
|  | AMD1 | AMD1 | AMD2 | AMD2 | AMD2 | 9369.9806 | 9369.9806 |  |  | TOTAL COSTS
|  | BUDGET | BUDGET | REVISION | REVISION |  | REVISION | REVISION |  |  | Dir & Indir (EUR)
| Task/ |  |  | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT) |  |  | ACTUAL
| WP | PM | hours | PMs | Hours |  | EUR | EUR | SCABERIA AS | Task/ | M1-M9
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 1 | 143.3333 | 1.2 | 172 | plus 0.2 PM | 11243.976 | 14054.97 |  | WP
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 0.5 | 71.6667 | 0.6 | 86 | plus 0.1 PM | 5621.988 | 7027.485 | Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 13497.1651
Assessment of emerging technology trends and solutions | T1.2 | 0.25 | 35.8333 | 0.3 | 43 | plus 0.05 PM | 2810.994 | 3513.7425 | Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 6648.4552
Potential new value chains and selection of Call Topics | T1.3 | 0.25 | 35.8333 | 0.3 | 43 | plus 0.05 PM | 2810.994 | 3513.7425 | Assessment of emerging technology trends and solutions | T1.2 | 3484.4313
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 0.5 | 71.6667 | 0.4 | 57.3333 | minus 0.1 PM | 3747.992 | 4684.99 | Potential new value chains and selection of Call Topics | T1.3 | 3364.2785
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0.25 | 35.8333 | 0.1 | 14.3333 | minus 0.15 PM | 936.998 | 1171.2475 | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 3123.9729
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0.1 | 14.3333 | plus 0.1 PM | 936.998 | 1171.2475 | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 40.0509
Establishment of a Survey tool | T2.3 | 0 | 0 | 0.1 | 14.3333 | plus 0.1 PM | 936.998 | 1171.2475 | Establishment of a Collaborative Virtual Environment | T2.2 | 520.6622
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0.25 | 35.8333 | 0.1 | 14.3333 | minus 0.15 PM | 936.998 | 1171.2475 | Establishment of a Survey tool | T2.3 | 1321.6809
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 4.5 | 645 | 4.2 | 602 | minus 0.3 PM | 39353.916 | 49192.395 | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 1241.579
Preparation of the Call for Proposals | T3.1 | 0.5 | 71.6667 | 1 | 143.3333 | plus 0.5 PM (support with Call docs) | 9369.98 | 11712.475 | Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 11374.4655
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 | 0.1 | 14.3333 | plus 0.1 PM (support with Call announcement doc) | 936.998 | 1171.2475 | Preparation of the Call for Proposals | T3.1 | 10613.4978
Evaluation and Selection of SMEs Proposals | T3.3 | 1 | 143.3333 | 0.1 | 14.3333 | minus 0.9 PM: SCA cannot be evaluator due to conflict of intrest. | 936.998 | 1171.2475 | Publication of the Call for Proposals and Proposal reception. | T3.2 | 760.9678
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Evaluation and Selection of SMEs Proposals | T3.3 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Contracting with winner SMEs Projects | T3.4 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 3 | 430 | 3 | 430 | Ok | 28109.94 | 35137.425 | Payments and financial monitoring of winner SMEs Projects | T3.5 | 0
Business Support Services to winner SMEs | WP4 | 12.75 | 1827.5 | 11.85 | 1698.5 | minus 0.9 PM (shift to WP7) | 111034.263 | 138792.8287 | Technical monitoring of winner SMEs Projects | T3.6 | 0
Programme of Business Support Services to winner SMEs | T4.1 | 0 | 0 | 0.2 | 28.6667 | plus 0.2 PM (input to definition of all BSSs) | 1873.996 | 2342.495 | Business Support Services to winner SMEs (preparation) | WP4 | 2723.4636
Business Support Service #1 Business & Tech Academy | T4.2 | 1 | 143.3333 | 1 | 143.3333 | Ok. | 9369.98 | 11712.475 | Programme of Business Support Services to winner SMEs (prep) | T4.1 | 2403.0561
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0.5 | 71.6667 | 0.1 | 14.3333 | minus 0.4 PM (virtual instead of F2F) | 936.998 | 1171.2475 | Business Support Service #1 Business & Tech Academy | T4.2 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 9.75 | 1397.5 | 9.75 | 1397.5 | Ok. | 91357.305 | 114196.6312 | Business Support Service #3 Access to Finance | T4.4 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 320.4075
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Business Support Service #5 Branding | T4.6 | 0
Business Support Service #7 Investor pitching | T4.8 | 1 | 143.3333 | 0.5 | 71.6667 | minus 0.5 PM | 4684.99 | 5856.2375 | Business Support Service #6 Internationalisation | T4.7 | 0
Business Support Service #8 Investor rounds | T4.9 | 0.5 | 71.6667 | 0.3 | 43 | minus 0.2 PM | 2810.994 | 3513.7425 | Business Support Service #7 Investor pitching | T4.8 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 6 | 860 | 6 | 860 | OK, but internal shift. | 56219.88 | 70274.85 | Business Support Service #8 Investor rounds | T4.9 | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 2.5 | 358.3333 | 3 | 430 | plus 0.5 PM (from T5.3) | 28109.94 | 35137.425 | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 33402.4798
Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 2.5 | 358.3333 | 2.5 | 358.3333 |  | 23424.95 | 29281.1875 | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 33402.4798
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 1 | 143.3333 | 0.5 | 71.6667 | minus 0.5 PM (no INNOSUP comparison) | 4684.99 | 5856.2375 | Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 1 | 143.3333 | 1 | 143.3333 | OK, but internal shift. | 9369.98 | 11712.475 | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0
Communication plan and Communication activities | T6.1 | 0 | 0 | 0.4 | 57.3333 | plus 0.4 PM (support with first com kit) | 3747.992 | 4684.99 | Communication, Dissemination, Exploitation & Sustainability | WP6 | 5847.4365
Dissemination strategy and Dissemination activities | T6.2 | 0.5 | 71.6667 | 0.3 | 43 | minus 0.2 PM (being SME less relevant) | 2810.994 | 3513.7425 | Communication plan and Communication activities | T6.1 | 4886.2141
Exploitation strategy, IPR and Sustainability | T6.3 | 0.5 | 71.6667 | 0.3 | 43 | minus 0.2 PM | 2810.994 | 3513.7425 | Dissemination strategy and Dissemination activities | T6.2 | 961.2224
Project Management and Coordination | WP7 | 0 | 0 | 1.1 | 157.6667 | plus 1.1 PM | 10306.978 | 12883.7225 | Exploitation strategy, IPR and Sustainability | T6.3 | 0
Project coordination | T7.1 | 0 | 0 | 0.5 | 71.6667 | plus 0.5 PM (participation GA meets) | 4684.99 | 5856.2375 | Project Management and Coordination | WP7 | 1682.1393
Project administration & Financial Management | T7.2 | 0 | 0 | 0.5 | 71.6667 | plus 0.5 PM (cost statements, 75% prep) | 4684.99 | 5856.2375 | Project coordination | T7.1 | 240.3056
Quality Assurance | T7.3 | 0 | 0 | 0.1 | 14.3333 | plus 0.1 (review work) | 936.998 | 1171.2475 | Project administration & Financial Management | T7.2 | 720.9168
NOTE: Key Tasks are marked light green |  | 25.75 | 3690.8333 | 25.75 | 3690.8333 |  | 241276.985 | 301596.2312 | Quality Assurance | T7.3 | 720.9168
71651.1227
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost

## FOC
TOTAL COSTS
Indir & DIR (EUR)
ACTUAL
GreenOffshoreTech - FÓRUM OCEANO | Task/ | M1-M9
WP
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ALL | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 1875.625
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 780.13
Assessment of emerging technology trends and solutions | T1.2 | 194.2
Potential new value chains and selection of Call Topics | T1.3 | 526.17
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 174.2875
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0
Establishment of a Survey tool | T2.3 | 139.43
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 2002.375
Preparation of the Call for Proposals | T3.1 | 1601.9
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 0
Contracting with winner SMEs Projects | T3.4 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 58.1
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 46.48
Business Support Service #1 Business & Tech Academy | T4.2 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0
Business Support Service #3 Access to Finance | T4.4 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0
Business Support Service #5 Branding | T4.6 | 0
Business Support Service #6 Internationalisation | T4.7 | 0
Business Support Service #7 Investor pitching | T4.8 | 0
Business Support Service #8 Investor rounds | T4.9 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 87.15
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 69.72
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 25103.8625
Communication plan and Communication activities | T6.1 | 16847.5
Dissemination strategy and Dissemination activities | T6.2 | 3235.59
Exploitation strategy, IPR and Sustainability | T6.3 | 0
Project Management and Coordination | WP7 | 0
Project coordination | T7.1 | 0
Project administration & Financial Management | T7.2 | 0
Quality Assurance | T7.3 | 0
TOTAL |  | 29301.4
[8 empty] | AMD2 | AMD2
[8 empty] | For BUDGET | For 75% RULE
|  | ORG = | ORG = |  |  |  |  | Direct monthly rate | Direct monthly rate
|  | AMD1 | AMD1 |  | AMD2 | AMD2 | AMD2 | 3020 | 3020 | Confirmed rate
|  | BUDGET | BUDGET |  | REVISION | REVISION |  | REVISION | REVISION
| Task/ |  |  | Execution | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT)
| WP | PM | hours |  | PMs | Hours |  | EUR | EUR
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 2.25 | 322.5 | 0.3279 | 0.3279 | 46.999 |  | 990.258 | 1237.8225
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 1 | 143.3333 | 0.1744 | 0.1744 | 24.9973 |  | 526.688 | 658.36
Assessment of emerging technology trends and solutions | T1.2 | 0.25 | 35.8333 | 0.0419 | 0.0419 | 6.0057 |  | 126.538 | 158.1725
Potential new value chains and selection of Call Topics | T1.3 | 1 | 143.3333 | 0.1116 | 0.1116 | 15.996 |  | 337.032 | 421.29
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 2.5 | 358.3333 | 0.0419 | 1.5419 | 221.0057 |  | 4656.538 | 5820.6725
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1.25 | 179.1667 |  | 1.25 | 179.1667 |  | 3775 | 4718.75
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 |  | 0 | 0 |  | 0 | 0
Establishment of a Survey tool | T2.3 | 1 | 143.3333 | 0.0419 | 0.0419 | 6.0057 |  | 126.538 | 158.1725
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0.25 | 35.8333 |  | 0.25 | 35.8333 |  | 755 | 943.75
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 2.5 | 358.3333 | 0.5302 | 2.6302 | 376.9953 |  | 7943.204 | 9929.005
Preparation of the Call for Proposals | T3.1 | 0.5 | 71.6667 | 0.5302 | 0.5302 | 75.9953 |  | 1601.204 | 2001.505
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 |  | 0 | 0 |  | 0 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 1 | 143.3333 |  | 2 | 286.6667 |  | 6040 | 7550
Contracting with winner SMEs Projects | T3.4 | 0 | 0 |  | 0 | 0 |  | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 |  | 0 | 0 |  | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 1 | 143.3333 |  | 0.1 | 14.3333 |  | 302 | 377.5
Business Support Services to winner SMEs | WP4 | 8.5 | 1218.3333 | 0.014 | 6.25 | 895.8333 |  | 18875 | 23593.75
Programme of Business Support Services to winner SMEs | T4.1 | 0 | 0 | 0.014 | 0.014 | 2.0067 |  | 42.28 | 52.85
Business Support Service #1 Business & Tech Academy | T4.2 | 1 | 143.3333 |  | 0.3 | 43 |  | 906 | 1132.5
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 4 | 573.3333 |  | 2.236 | 320.4933 |  | 6752.72 | 8440.9
Business Support Service #3 Access to Finance | T4.4 | 0.5 | 71.6667 |  | 0.5 | 71.6667 |  | 1510 | 1887.5
Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 0 | 0 |  | 0.2 | 28.6667 |  | 604 | 755
Business Support Service #5 Branding | T4.6 | 2 | 286.6667 |  | 2 | 286.6667 |  | 6040 | 7550
Business Support Service #6 Internationalisation | T4.7 | 0.5 | 71.6667 |  | 0.5 | 71.6667 |  | 1510 | 1887.5
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 |  | 0 | 0 |  | 0 | 0
Business Support Service #8 Investor rounds | T4.9 | 0.5 | 71.6667 |  | 0.5 | 71.6667 |  | 1510 | 1887.5
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0.75 | 107.5 | 0.0209 | 0.75 | 107.5 |  | 2265 | 2831.25
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0.25 | 35.8333 | 0.0209 | 0.25 | 35.8333 |  | 755 | 943.75
Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 0.25 | 35.8333 |  | 0.25 | 35.8333 |  | 755 | 943.75
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0.25 | 35.8333 |  | 0.25 | 35.8333 |  | 755 | 943.75
Communication, Dissemination, Exploitation & Sustainability | WP6 | 7.5 | 1075 | 3.5023 | 10.5 | 1505 |  | 31710 | 39637.5
Communication plan and Communication activities | T6.1 | 4 | 573.3333 | 2.4837 | 4 | 573.3333 |  | 12080 | 15100
Dissemination strategy and Dissemination activities | T6.2 | 3 | 430 | 1.0186 | 6 | 860 |  | 18120 | 22650
Exploitation strategy, IPR and Sustainability | T6.3 | 0.5 | 71.6667 |  | 0.5 | 71.6667 |  | 1510 | 1887.5
Project Management and Coordination | WP7 | 0 | 0 | 0 | 2 | 286.6667 |  | 6040 | 7550
Project coordination | T7.1 | 0 | 0 |  | 0.5 | 71.6667 |  | 1510 | 1887.5
Project administration & Financial Management | T7.2 | 0 | 0 |  | 1.4 | 200.6667 |  | 4228 | 5285
Quality Assurance | T7.3 | 0 | 0 |  | 0.1 | 14.3333 |  | 302 | 377.5
NOTE: Key Tasks are marked light green |  | 24 | 3440 | 4.4372 | 24 | 3440 |  | 72480 | 90600
Table to the left is active as partner input to sheet Direct & Indirect Personnal Cost

## CLTV
|  | ORG = | ORG = |  |  |  | Direct monthly rate | Direct monthly rate
|  | AMD1 | AMD1 | AMD2 | AMD2 | AMD2 | 3750 | 3750 | Retrieved from budget |  |  | TOTAL COSTS | TOTAL COSTS
|  | BUDGET | BUDGET | REVISION | REVISION |  | REVISION | REVISION |  |  |  | DIR | Indir & DIR
| Task/ |  |  | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT) |  |  |  | ACTUAL | ACTUAL
| WP | PM | hours | PMs | Hours |  | EUR | EUR |  | GreenOfshoreTech PARTNER NAME | Task/ | M1-M9 | M1-M9
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 2.25 | 322.5 | 1.7163 | 246.0057 | minus 0,53 PM ( shift to WP6) | 16081.8746 | 20102.3432 |  |  | WP
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 0.25 | 35.8333 | 0.13954 | 20 | minus 0,11 PM | 1307.4695 | 1634.3368 |  | Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ALL | 0 | 0
Assessment of emerging technology trends and solutions | T1.2 | 1 | 143.3333 | 0.57908 | 83 | pminus 0,42 PM | 5425.9983 | 6782.4979 |  | Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 5458.7342 | 6823.4177
Potential new value chains and selection of Call Topics | T1.3 | 1 | 143.3333 | 0.9977 | 143 | ok | 9348.4068 | 11685.5084 |  | Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 406.9445 | 508.6807
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 2.5 | 358.3333 | 2.5 | 358.3333 | ok | 23424.95 | 29281.1875 |  | Assessment of emerging technology trends and solutions | T1.2 | 2033.141 | 2541.4263
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1.25 | 179.1667 | 1.25 | 179.1667 |  | 11712.475 | 14640.5937 |  | Potential new value chains and selection of Call Topics | T1.3 | 3018.6486 | 3773.3108
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 2969.5444 | 3711.9305
Establishment of a Survey tool | T2.3 | 1 | 143.3333 | 1 | 143.3333 |  | 9369.98 | 11712.475 |  | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1453.0095 | 1816.2619
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2342.495 | 2928.1187 |  | Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 3.5 | 501.6667 | 3.5 | 501.6667 | ok | 32794.93 | 40993.6625 |  | Establishment of a Survey tool | T2.3 | 1516.5348 | 1895.6686
Preparation of the Call for Proposals | T3.1 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4684.99 | 5856.2375 |  | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 199.3141 | 249.1427
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 769.9284 | 962.4105
Evaluation and Selection of SMEs Proposals | T3.3 | 1 | 143.3333 | 1 | 143.3333 |  | 9369.98 | 11712.475 |  | Preparation of the Call for Proposals | T3.1 | 769.9284 | 962.4105
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 2 | 286.6667 | 2 | 286.6667 |  | 18739.96 | 23424.95 |  | Contracting with winner SMEs Projects | T3.4 | 0 | 0
Business Support Services to winner SMEs | WP4 | 7 | 1003.3333 | 7 | 1003.3333 | ok | 65589.86 | 81987.325 |  | Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0
Programme of Business Support Services to winner SMEs | T4.1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 1 | 143.3333 | 1 | 143.3333 |  | 9369.98 | 11712.475 |  | Business Support Services to winner SMEs (preparation) | WP4 | 476.1557 | 595.1947
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4684.99 | 5856.2375 |  | Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4684.99 | 5856.2375 |  | Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Business Support Service #3 Access to Finance | T4.4 | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4684.99 | 5856.2375 |  | Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0
Business Support Service #7 Investor pitching | T4.8 | 4 | 573.3333 | 4 | 573.3333 | We would like to add 8000 EUR to this (allocate money from our travel budget). Under this Task not only one persone will be working. The main thing is that one part is coordination, planning, but other thing is - planned staff who will be making B2B meeting, making plans to teach and educate SMEs about investor pitching. When we elaborated deliverable and description for this task, we understood that staff who could make quality training, that will be specially aimed to winner SME's, needs more hours for work. Work includes planning, communication with SMEs, B2B meetings, getting to understend SMEs and what they need and what they want. | 37479.92 | 46849.9 |  | Business Support Service #5 Branding | T4.6 | 0 | 0
Business Support Service #8 Investor rounds | T4.9 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4684.99 | 5856.2375 |  | Business Support Service #6 Internationalisation | T4.7 | 0 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0.75 | 107.5 | 0.75 | 107.5 | ok | 7027.485 | 8784.3562 |  | Business Support Service #7 Investor pitching | T4.8 | 476.1557 | 595.1947
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2342.495 | 2928.1187 |  | Business Support Service #8 Investor rounds | T4.9 | 0 | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2342.495 | 2928.1187 |  | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 560.0721 | 700.0901
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2342.495 | 2928.1187 |  | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 560.0721 | 700.0901
Communication, Dissemination, Exploitation & Sustainability | WP6 | 2 | 286.6667 | 2.53 | 362.6333 | Plus 0,53 PM | 23706.0494 | 29632.5617 |  | Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0
Communication plan and Communication activities | T6.1 | 0.5 | 71.6667 | 0.85 | 121.8333 | plus 0.35 PM | 7964.483 | 9955.6037 |  | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0
Dissemination strategy and Dissemination activities | T6.2 | 1 | 143.3333 | 1.18 | 169.1333 | plus 0.18 PM | 11056.5764 | 13820.7205 |  | Communication, Dissemination, Exploitation & Sustainability | WP6 | 2670.2063 | 3337.7579
Exploitation strategy, IPR and Sustainability | T6.3 | 0.5 | 71.6667 | 0.5 | 71.6667 | ok | 4684.99 | 5856.2375 |  | Communication plan and Communication activities | T6.1 | 367.3957 | 459.2447
Project Management and Coordination | WP7 | 0 | 0 | 0 | 0 | ok | 0 | 0 |  | Dissemination strategy and Dissemination activities | T6.2 | 2302.8105 | 2878.5132
Project coordination | T7.1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Project Management and Coordination | WP7 | 0 | 0
Quality Assurance | T7.3 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Project coordination | T7.1 | 0 | 0
NOTE: Key Tasks to be marked light green |  | 18 | 2580 | 17.9963 | 2579.4724 |  | 168625.149 | 210781.4362 |  | Project administration & Financial Management | T7.2 | 0 | 0
[10 empty] | Quality Assurance | T7.3 | 0 | 0
[10 empty] | TOTAL |  | 12904.6411 | 16130.8013
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost

## MAI
TOTAL COSTS
[7 empty] | AMD2 | AMD2 | [6 empty] | 1.25
[7 empty] | For BUDGET | For 75% RULE | [5 empty] | INCLDING IND COST
|  | ORG = | ORG = |  |  |  | Direct monthly rate | Direct monthly rate
|  | AMD1 | AMD1 | AMD2 | AMD2 | AMD2 | 8500 | 8500 | Confirmed rate |  |  | TOTAL COSTS
|  | BUDGET | BUDGET | REVISION | REVISION |  | REVISION | REVISION |  |  |  | Dir & Indir (EUR)
| Task/ |  |  | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT) |  |  |  | ACTUAL
| WP | PM | hours | PMs | Hours |  | EUR | EUR |  | MAI Carbon | Task/ | M1-M8 | DELIVERABLE
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 3.25 | 465.8333 | 1.2 | 172 | plus 0.2 PM | 10200 | 12750 |  |  | WP |  | D7.5
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 0.25 | 35.8333 | 0.1 | 14.3333 | plus 0.1 PM | 850 | 1062.5 |  | Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 12627.3375 | SECTION 4 |  | 12627.3375
Assessment of emerging technology trends and solutions | T1.2 | 1 | 143.3333 | 0.6 | 86 | plus 0.05 PM | 5100 | 6375 |  | Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 0 | SECTION 4 |  | 0
Potential new value chains and selection of Call Topics | T1.3 | 2 | 286.6667 | 0.5 | 71.6667 | plus 0.05 PM | 4250 | 5312.5 |  | Assessment of emerging technology trends and solutions | T1.2 | 4056.67 | SECTION 4 |  | 5070.8375
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 0.5 | 71.6667 | 0.5 | 71.6667 | minus 0.1 PM | 4250 | 5312.5 |  | Potential new value chains and selection of Call Topics | T1.3 | 6045.2 | SECTION 4 |  | 7556.5
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0.25 | 35.8333 | 0.25 | 35.8333 | no Change | 2125 | 2656.25 |  | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 0 | SECTION 4 |  | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 | 0 | no Change | 0 | 0 |  | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0 | SECTION 4 |  | 0
Establishment of a Survey tool | T2.3 | 0 | 0 | 0 | 0 | no Change | 0 | 0 |  | Establishment of a Collaborative Virtual Environment | T2.2 | 0 | SECTION 4 |  | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0.25 | 35.8333 | 0.25 | 35.8333 | no Change | 2125 | 2656.25 |  | Establishment of a Survey tool | T2.3 | 0 | SECTION 4 |  | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 3.5 | 501.6667 | 3.5 | 501.6667 | minus 0.3 PM | 29750 | 37187.5 |  | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | SECTION 4 |  | 0
Preparation of the Call for Proposals | T3.1 | 0.5 | 71.6667 | 0.5 | 71.6667 | no Change | 4250 | 5312.5 |  | Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 0 | SECTION 4 |  | 0
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 | 0 | 0 | no Change | 0 | 0 |  | Preparation of the Call for Proposals | T3.1 | 0 | SECTION 4 |  | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 1 | 143.3333 | 1 | 143.3333 | no Change | 8500 | 10625 |  | Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | SECTION 4 |  | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 | no Change | 0 | 0 |  | Evaluation and Selection of SMEs Proposals | T3.3 | 0 | SECTION 4 |  | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 | no Change | 0 | 0 |  | Contracting with winner SMEs Projects | T3.4 | 0 | SECTION 4 |  | 0 | WP1 | 12627.3375
Technical monitoring of winner SMEs Projects | T3.6 | 2 | 286.6667 | 2 | 286.6667 | no Change | 17000 | 21250 |  | Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | SECTION 4 |  | 0 | WP2 | 0
Business Support Services to winner SMEs | WP4 | 8 | 1146.6667 | 8 | 1146.6667 | minus 0.9 PM (shift to WP7) | 68000 | 85000 |  | Technical monitoring of winner SMEs Projects | T3.6 | 0 | SECTION 4 |  | 0 | WP3 | 0
Programme of Business Support Services to winner SMEs | T4.1 | 2.5 | 358.3333 | 2.5 | 358.3333 | no Change | 21250 | 26562.5 |  | Business Support Services to winner SMEs (preparation) | WP4 | 4120.2875 | SECTION 4 |  | 4120.2875 | WP4 | 4120.2875
Business Support Service #1 Business & Tech Academy | T4.2 | 3 | 430 | 3 | 430 | no Change | 25500 | 31875 |  | Programme of Business Support Services to winner SMEs (prep) | T4.1 | 3296.23 | SECTION 4 |  | 4120.2875 | WP5 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 1 | 143.3333 | 1 | 143.3333 | no Change | 8500 | 10625 |  | Business Support Service #1 Business & Tech Academy | T4.2 | 0 | SECTION 4 |  | 0 | WP6 | 4596
Business Support Service #3 Access to Finance | T4.4 | 0.5 | 71.6667 | 0.5 | 71.6667 | no Change | 4250 | 5312.5 |  | Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | SECTION 4 |  | 0 | WP7 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 0 | 0 | 0 | 0 | no Change | 0 | 0 |  | Business Support Service #3 Access to Finance | T4.4 | 0 | SECTION 4 |  | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0 | 0 | no Change | 0 | 0 |  | Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | SECTION 4 |  | 0
Business Support Service #6 Internationalisation | T4.7 | 0.5 | 71.6667 | 0.5 | 71.6667 | no Change | 4250 | 5312.5 |  | Business Support Service #5 Branding | T4.6 | 0 | SECTION 4 |  | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0 | 0 | no Change | 0 | 0 |  | Business Support Service #6 Internationalisation | T4.7 | 0 | SECTION 4 |  | 0
Business Support Service #8 Investor rounds | T4.9 | 0.5 | 71.6667 | 0.5 | 71.6667 | no Change | 4250 | 5312.5 |  | Business Support Service #7 Investor pitching | T4.8 | 0 | SECTION 4 |  | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0.75 | 107.5 | 0.75 | 107.5 | OK, but internal shift. | 6375 | 7968.75 |  | Business Support Service #8 Investor rounds | T4.9 | 0 | SECTION 4 |  | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0.25 | 35.8333 | 0.25 | 35.8333 | no Change | 2125 | 2656.25 |  | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0 | SECTION 4 |  | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 0.25 | 35.8333 | 0.25 | 35.8333 | no Change | 2125 | 2656.25 |  | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0 | SECTION 4 |  | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0.25 | 35.8333 | 0.25 | 35.8333 | no Change | 2125 | 2656.25 |  | Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | SECTION 4 |  | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 3 | 430 | 3 | 430 | OK, but internal shift. | 25500 | 31875 |  | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | SECTION 4 |  | 0
Communication plan and Communication activities | T6.1 | 0.5 | 71.6667 | 0.5 | 71.6667 | no Change | 4250 | 5312.5 |  | Communication, Dissemination, Exploitation & Sustainability | WP6 | 4596 | SECTION 5 |  | 4596
Dissemination strategy and Dissemination activities | T6.2 | 1 | 143.3333 | 1 | 143.3333 | no Change | 8500 | 10625 |  | Communication plan and Communication activities | T6.1 | 3676.8 | SECTION 5 |  | 4596
Exploitation strategy, IPR and Sustainability | T6.3 | 1.5 | 215 | 1.5 | 215 | no Change | 12750 | 15937.5 |  | Dissemination strategy and Dissemination activities | T6.2 | 0 | SECTION 5 |  | 0
Project Management and Coordination | WP7 | 0 | 0 | 2.05 | 293.8333 | plus 1.1 PM | 17425 | 21781.25 |  | Exploitation strategy, IPR and Sustainability | T6.3 | 0 | SECTION 5 |  | 0
Project coordination | T7.1 | 0 | 0 | 1.05 | 150.5 | plus 1,05 PM (participation GA meets) | 8925 | 11156.25 |  | Project Management and Coordination | WP7 | 0 | SECTION 5 |  | 0
Project administration & Financial Management | T7.2 | 0 | 0 | 1 | 143.3333 | plus 1 PM (cost statements) | 8500 | 10625 |  | Project coordination | T7.1 | 0 | SECTION 5 |  | 0
Quality Assurance | T7.3 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Project administration & Financial Management | T7.2 | 0 | SECTION 5 |  | 0
NOTE: Key Tasks to be marked light green |  | 19 | 2723.3333 | 19 | 2723.3333 |  | 161500 | 201875 |  | Quality Assurance | T7.3 | 0 | SECTION 5 |  | 0
[10 empty] | TOTAL |  | 21343.625 |  |  | 21343.625
1720 h/year and 143,333 h/month
1) 2 PM from WP 1 to WP2. With this, we would have hit our then remaining
PM in WP1 sufficiently accurately and could accommodate 2 PM in WP7
as agreed.
2) Adjustment of the salary rate. I have not found the salary rate in the GA
directly, but come to 7,750 €/PM. However, we are currently landing more
at 8,500 €/PM. I.e. here should also be an adjustment when the salary rate
is specified. (Or do you need the information in €/hour ?).
Hourly rate will with 8,500 Euro /PM be 59,3 Euro
2PM Cost moved from WP1 till WP2 = 17000 Euro
2PM Cost moved from WP1 till WP7 = 17000 Euro
For this exercice we will use 8,500 Euro
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost
YOUR BUDGETE NUMBERS: Column C is budgeted PM, column D is hours is assuming 1720 or 1 PM=143.333
COMPLETE COLUMN E TIL I for the AMD2
According to your re-allocation and salary cost.

## BIN
TOTAL COSTS
[7 empty] | AMD2 | AMD2 |  |  |  | Dir & Indir (EUR) | Ind. Costs flat rate
[7 empty] | For BUDGET | For 75% RULE |  |  |  | ACTUAL | Project manager |  | Assistant
|  | ORG = | ORG = |  |  |  | Direct monthly rate | Direct monthly rate |  | GreenOfshoreTech BIN (Periode1, 09/21-06/22) | Task/ | M1-M9 | hrs | Salery rate | hrs | Salery rate
|  | AMD1 | AMD1 | AMD2 | AMD2 | AMD2 | 8600 | 8600 | Estimated to 60 EURO per hour |  | WP |  |  | 65.35 |  | 50.11
|  | BUDGET | BUDGET | REVISION | REVISION |  | REVISION | REVISION |  | Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | ALL | 0
| Task/ |  |  | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT) |  | Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 13000.7375 | 146.5 | 9573.775 | 16.5 | 826.815
| WP | PM | hours | PMs | Hours |  | EUR | EUR |  | Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 2578.095 | 36 | 2352.6 | 4.5 | 225.495
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 3.25 | 465.8333 | 1.2 | 172 | Shift 2,05; Shift 2PM to WP7, Shift 0,5 to WP4 | 10320 | 12900 |  | Assessment of emerging technology trends and solutions | T1.2 | 5960.02 | 82 | 5358.7 | 12 | 601.32
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 0.25 | 35.8333 | 0.3 | 43 |  | 2580 | 3225 |  | Potential new value chains and selection of Call Topics | T1.3 | 1862.475 | 28.5 | 1862.475 | 0 | 0
Assessment of emerging technology trends and solutions | T1.2 | 1 | 143.3333 | 0.7 | 100.3333 |  | 6020 | 7525 |  | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 653.5 | 8 | 522.8 |  | 0
Potential new value chains and selection of Call Topics | T1.3 | 2 | 286.6667 | 0.2 | 28.6667 |  | 1720 | 2150 |  | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 130.7 | 2 | 130.7 | 0 | 0
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 0.5 | 71.6667 | 0.5 | 71.6667 | no changes | 4300 | 5375 |  | Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 | 0 | 0
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2150 | 2687.5 |  | Establishment of a Survey tool | T2.3 | 196.05 | 3 | 196.05 | 0 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 196.05 | 3 | 196.05 | 0 | 0
Establishment of a Survey tool | T2.3 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 1364.2125 | 18 | 1176.3 | 3 | 150.33
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2150 | 2687.5 |  | Preparation of the Call for Proposals | T3.1 | 653.5 | 10 | 653.5 | 0 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 3.5 | 501.6667 | 3.5 | 501.6667 | no changes (WP is extended as discussed) | 30100 | 37625 |  | Publication of the Call for Proposals and Proposal reception. | T3.2 | 673.13 | 8 | 522.8 | 3 | 150.33
Preparation of the Call for Proposals | T3.1 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4300 | 5375 |  | Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0 | 0 | 0 | 0
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 1 | 143.3333 | 1 | 143.3333 |  | 8600 | 10750 |  | Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 | 0 | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Business Support Services to winner SMEs (preparation) | WP4 | 653.5 | 8 | 522.8 |  | 0
Technical monitoring of winner SMEs Projects | T3.6 | 2 | 286.6667 | 2 | 286.6667 |  | 17200 | 21500 |  | Programme of Business Support Services to winner SMEs (prep) | T4.1 | 65.35 | 1 | 65.35 | 0 | 0
Business Support Services to winner SMEs | WP4 | 9 | 1290 | 9.05 | 1297.1667 | plus 0,05 from WP 1 | 77830 | 97287.5 |  | Business Support Service #1 Business & Tech Academy | T4.2 | 196.05 | 3 | 196.05 | 0 | 0
Programme of Business Support Services to winner SMEs | T4.1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 261.4 | 4 | 261.4 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 3.5 | 501.6667 | 3.5 | 501.6667 |  | 30100 | 37625 |  | Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 0 | 0 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 4 | 573.3333 | 4.05 | 580.5 | plus 0,05 from WP 1 | 34830 | 43537.5 |  | Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | 0 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4300 | 5375 |  | Business Support Service #5 Branding | T4.6 | 0 | 0 | 0 | 0 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Business Support Service #6 Internationalisation | T4.7 | 0 | 0 | 0 | 0 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0 | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4300 | 5375 |  | Business Support Service #8 Investor rounds | T4.9 | 0 | 0 | 0 | 0 | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0 | 0 | 0 |  | 0
Business Support Service #8 Investor rounds | T4.9 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4300 | 5375 |  | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0 | 0 | 0 | 0 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0.75 | 107.5 | 0.75 | 107.5 | no changes | 6450 | 8062.5 |  | Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 | 0 | 0 | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2150 | 2687.5 |  | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 | 0 | 0 | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2150 | 2687.5 |  | Communication, Dissemination, Exploitation & Sustainability | WP6 | 408.4375 | 5 | 326.75 |  | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0.25 | 35.8333 | 0.25 | 35.8333 |  | 2150 | 2687.5 |  | Communication plan and Communication activities | T6.1 | 326.75 | 5 | 326.75 | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 2 | 286.6667 | 2 | 286.6667 | no changes | 17200 | 21500 |  | Dissemination strategy and Dissemination activities | T6.2 | 0 | 0 | 0 | 0 | 0
Communication plan and Communication activities | T6.1 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4300 | 5375 |  | Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0 | 0 | 0 | 0
Dissemination strategy and Dissemination activities | T6.2 | 1 | 143.3333 | 1 | 143.3333 |  | 8600 | 10750 |  | Project Management and Coordination | WP7 | 367.5938 | 4.5 | 294.075 |  | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0.5 | 71.6667 | 0.5 | 71.6667 |  | 4300 | 5375 |  | Project coordination | T7.1 | 0 | 0 | 0 | 0 | 0
Project Management and Coordination | WP7 | 0 | 0 | 2 | 286.6667 | plus 2 PM from WP 1 | 17200 | 21500 |  | Project administration & Financial Management | T7.2 | 0 | 0 | 0 | 0 | 0
Project coordination | T7.1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Quality Assurance | T7.3 | 294.075 | 4.5 | 294.075 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0 | 1.5 | 215 | the shifted 2PM are split between 7.2 and 7.3 | 12900 | 16125 |  | TOTAL |  | 16447.9812 | 190 | 12416.5 | 19.5 | 977.145
Quality Assurance | T7.3 | 0 | 0 | 0.5 | 71.6667 | the shifted 2PM are split between 7.2 and 7.4 | 4300 | 5375
NOTE: Key Tasks are marked light green |  | 19 | 2723.3333 | 19 | 2723.3333 |  | 163400 | 204250
Column C&D is for MAI, budgeted PM, hours is assuming 1720 annual hours
COMPLETE COLUMN E TIL I
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost

## IOC
|  | (to May) |  | (to May)
|  | TOTAL COSTS |  | TOTAL COSTS
|  | Dir & Indir (EUR) |  | Dir & Indir (EUR)
|  | ACTUAL |  | ACTUAL
GreenOfshoreTech Iceland Ocean Cluster | Task/ | M1-M9 |  | M1-M9
| WP |  | Hours/task
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) |  |  |  | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 2402.5312 | 36.75 | 2402.5312
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 248.425 | 4.75 | 310.5312
Assessment of emerging technology trends and solutions | T1.2 | 1176.75 | 22.5 | 1470.9375
Potential new value chains and selection of Call Topics | T1.3 | 496.85 | 9.5 | 621.0625
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 555.6875 | 8.5 | 555.6875
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0 | 0 | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0
Establishment of a Survey tool | T2.3 | 0 | 0 | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 444.55 | 8.5 | 555.6875
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 1307.5 | 20 | 1307.5
Preparation of the Call for Proposals | T3.1 | 836.8 | 16 | 1046
Publication of the Call for Proposals and Proposal reception. | T3.2 | 209.2 | 4 | 261.5
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 0 | 0 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 359.5625 | 5.5 | 359.5625
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 287.65 | 5.5 | 359.5625
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 4821.4062 | 73.75 | 4821.4062
Communication plan and Communication activities | T6.1 | 3857.125 | 73.75 | 4821.4062
Dissemination strategy and Dissemination activities | T6.2 | 0 | 0 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0 | 0
Project Management and Coordination | WP7 | 0 | 0 | 0
Project coordination | T7.1 | 0 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0 | 0
Quality Assurance | T7.3 | 0 | 0 | 0
TOTAL |  | 9446.6875 | 144.5 | 9446.6875
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost

## HIE
HIE
INCLDING IND COST
|  | TOTAL COSTS | TOTAL COSTS |  |  | TOTAL COSTS
|  | Dir & Indir (EUR) | Dir (EUR) |  |  | Dir & Indir (EUR)
|  | ACTUAL | ACTUAL |  |  | ACTUAL
GreenOfshoreTech PARTNER NAME | Task/ | M1-M9 | M1-M9 |  |  | M1-M9
WP
Otherdirect Cost ( travel, equipment & Other goods and services)(ODC) | All | 4611 | 4611 |  |  | 5763.75
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 15319.0574 | 15319.0574 |  |  | 12255.2459
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 11586.2678 | 14482.8348 |  |  | 11586.2678
Assessment of emerging technology trends and solutions | T1.2 | 411.6788 | 514.5985 |  |  | 411.6788
Potential new value chains and selection of Call Topics | T1.3 | 257.2993 | 321.6241 |  |  | 257.2993
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 15281.059 | 21820.3105 |  |  | 15281.059
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 11710.2487 | 14637.8109 |  |  | 14637.8109
Establishment of a Collaborative Virtual Environment | T2.2 | 514.5985 | 643.2482 |  |  | 643.2482
Establishment of a Survey tool | T2.3 | 0 | 0 |  |  | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 0 |  |  | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 6539.2514 | 6539.2514 |  |  | 6539.2514
Preparation of the Call for Proposals | T3.1 | 1302.4411 | 1628.0514 |  |  | 1628.0514
Publication of the Call for Proposals and Proposal reception. | T3.2 | 3928.96 | 4911.2 | Travel costs 4611 euro added to T3.2 | 0 | 4911.2
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0 |  |  | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 |  |  | 0 | WP1 | 15319.0574
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 |  |  | 0 | WP2 | 15281.059
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 |  |  | 0 | WP3 | 6539.2514
Business Support Services to winner SMEs (preparation) | WP4 | 0 | 0 |  |  | 0 | WP4 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0 |  |  | 0 | WP5 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 |  |  | 0 | WP6 | 2261.1825
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 |  |  | 0 | WP7 | 5531.9342
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 |  |  | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 |  |  | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 |  |  | 0
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 |  |  | 0
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 |  |  | 0
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 |  |  | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0 | 0 |  |  | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0 | 0 |  |  | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 |  |  | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 |  |  | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 2261.1825 | 2261.1825 |  |  | 2261.1825
Communication plan and Communication activities | T6.1 | 0 | 0 |  |  | 0
Dissemination strategy and Dissemination activities | T6.2 | 1808.946 | 2261.1825 |  |  | 2261.1825
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0 |  |  | 0
Project Management and Coordination | WP7 | 5531.9342 | 5531.9342 |  |  | 5531.9342
Project coordination | T7.1 | 3808.0292 | 4760.0364 |  |  | 4760.0364
Project administration & Financial Management | T7.2 | 617.5182 | 771.8978 |  |  | 771.8978
Quality Assurance | T7.3 | 0 | 0 |  |  | 0
TOTAL |  | 49543.4847 | 56082.7361 |  |  | 47632.4232
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost

## BAL
[15 empty] | 12375 |  |  | 16600 | 1.25
[7 empty] | AMD2 | AMD2 | [6 empty] | 6187.5 |  |  | 9900
[7 empty] | For BUDGET | For 75% RULE | [6 empty] | 3093.75 |  |  | 4950
|  | ORG = | ORG = |  |  |  | Direct monthly rate | Direct monthly rate |  |  | TOTAL COSTS |  | Hourly cost | 83.952 | 3093.75 |  |  | 2475
|  | AMD1 | AMD1 | AMD2 | AMD2 | AMD2 | 9900 | 9900 |  |  | Dir & Indir (EUR) |  |  |  | 47406.25 |  |  | 2475
|  | BUDGET | BUDGET | REVISION | REVISION |  | REVISION | REVISION |  |  | ACTUAL |  |  |  | 0 |  |  | 37925
| Task/ |  |  | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT) | GreenOfshoreTech PARTNER NAME | Task/ | M1-M9 |  |  |  | 0 |  |  | 0
| WP | PM | hours | PMs | Hours |  | EUR | EUR |  | WP |  |  |  |  | 0 |  |  | 0
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 1 | 140 | 1 | 140 | OK | 9900 | 12375 | Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 13402.8875 | 10722.31 |  |  | 47406.25 |  |  | 0
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 0.5 | 70 | 0.5 | 70 | OK | 4950 | 6187.5 | Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 7215.3875 | 5772.31 |  |  | 58500 |  |  | 37925
Assessment of emerging technology trends and solutions | T1.2 | 0.25 | 35 | 0.25 | 35 | OK | 2475 | 3093.75 | Assessment of emerging technology trends and solutions | T1.2 | 3093.75 | 2475 |  |  | 7437.5 |  |  | 46800
Potential new value chains and selection of Call Topics | T1.3 | 0.25 | 35 | 0.25 | 35 | OK | 2475 | 3093.75 | Potential new value chains and selection of Call Topics | T1.3 | 3093.75 | 2475 |  |  | 14375 |  |  | 5950
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 3.75 | 525 | 3.75 | 525 | OK | 37125 | 46406.25 | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 30049.1875 | 24039.35 |  |  | 22312.5 |  |  | 11500
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0 | 0 |  |  | 0 |  |  | 17850
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 |  |  | 0 |  |  | 0
Establishment of a Survey tool | T2.3 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Establishment of a Survey tool | T2.3 | 0 | 0 |  |  | 14375 |  |  | 0
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 3.75 | 525 | 3.75 | 525 | OK | 37125 | 46406.25 | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 30049.1875 | 24039.35 |  |  | 41687.5 |  |  | 11500
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 4 | 560 | 4 | 560 | OK | 39600 | 49500 | Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 34570.4875 | 27656.39 |  |  | 0 |  |  | 33350
Preparation of the Call for Proposals | T3.1 | 0.5 | 70 | 0.5 | 70 | OK | 4950 | 6187.5 | Preparation of the Call for Proposals | T3.1 | 6187.5 | 4950 |  |  | 24312.5 |  |  | 0
Publication of the Call for Proposals and Proposal reception. | T3.2 | 1 | 140 | 1 | 140 | OK | 9900 | 12375 | Publication of the Call for Proposals and Proposal reception. | T3.2 | 7484.4 | 5987.52 |  |  | 8687.5 |  |  | 19450
Evaluation and Selection of SMEs Proposals | T3.3 | 1.5 | 210 | 1.5 | 210 | OK | 14850 | 18562.5 | Evaluation and Selection of SMEs Proposals | T3.3 | 14711.0875 | 11768.87 |  |  | 0 |  |  | 6950
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Contracting with winner SMEs Projects | T3.4 | 0 | 0 |  |  | 0 | WP1 | 13402.8875 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 |  |  | 0 | WP2 | 30049.1875 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 1 | 140 | 1 | 140 | Ok | 9900 | 12375 | Technical monitoring of winner SMEs Projects | T3.6 | 6187.5 | 4950 |  |  | 0 | WP3 | 34570.4875 | 0
Business Support Services to winner SMEs | WP4 | 2.5 | 350 | 2.5 | 350 | OK | 24750 | 30937.5 | Business Support Services to winner SMEs (preparation) | WP4 | 5126.7875 | 4101.43 |  |  | 0 | WP4 | 5126.7875 | 0
Programme of Business Support Services to winner SMEs | T4.1 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 | 0 |  |  | 8687.5 | WP5 | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 1.5 | 210 | 1.5 | 210 | Ok. | 14850 | 18562.5 | Business Support Service #1 Business & Tech Academy | T4.2 | 5126.7875 | 4101.43 |  |  | 9281.25 | WP6 | 0 | 6950
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0.5 | 70 | 0.5 | 70 | OK | 4950 | 6187.5 | Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 |  |  | 3093.75 | WP7 | 0 | 7425
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Business Support Service #3 Access to Finance | T4.4 | 0 | 0 |  |  | 3093.75 |  |  | 2475
Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 |  |  | 3093.75 |  |  | 2475
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Business Support Service #5 Branding | T4.6 | 0 | 0 |  |  | 12375 |  |  | 2475
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 | 0 | 0 | Ok. | 0 | 0 | Business Support Service #6 Internationalisation | T4.7 | 0 | 0 |  |  | 0 |  |  | 9900
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Business Support Service #7 Investor pitching | T4.8 | 0 | 0 |  |  | 6187.5 |  |  | 0
Business Support Service #8 Investor rounds | T4.9 | 0.5 | 70 | 0.5 | 70 | OK | 4950 | 6187.5 | Business Support Service #8 Investor rounds | T4.9 | 0 | 0 |  |  | 6187.5 |  |  | 4950
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0.75 | 105 | 0.75 | 105 | OK | 7425 | 9281.25 | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0 | 0 |  |  | 0 |  |  | 4950
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0.25 | 35 | 0.25 | 35 | OK | 2475 | 3093.75 | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0 | 0 |  |  | 0 |  |  | 0
Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 0.25 | 35 | 0.25 | 35 | OK | 2475 | 3093.75 | Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 |  |  | 0 |  |  | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0.25 | 35 | 0.25 | 35 | OK | 2475 | 3093.75 | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 |  |  | 0 |  |  | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 1 | 140 | 1 | 140 | OK | 9900 | 12375 | Communication, Dissemination, Exploitation & Sustainability | WP6 | 0 | 0 |  |  | 181625 |  |  | 0
Communication plan and Communication activities | T6.1 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Communication plan and Communication activities | T6.1 | 0 | 0 | [5 empty] | 145300
Dissemination strategy and Dissemination activities | T6.2 | 0.5 | 70 | 0.5 | 70 | OK | 4950 | 6187.5 | Dissemination strategy and Dissemination activities | T6.2 | 0 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0.5 | 70 | 0.5 | 70 | OK | 4950 | 6187.5 | Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0
Project Management and Coordination | WP7 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Project Management and Coordination | WP7 | 0 | 0
Project coordination | T7.1 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Project coordination | T7.1 | 0 | 0
Project administration & Financial Management | T7.2 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Project administration & Financial Management | T7.2 | 0 | 0
Quality Assurance | T7.3 | 0 | 0 | 0 | 0 | OK | 0 | 0 | Quality Assurance | T7.3 | 0 | 0
NOTE: Key Tasks to be marked light green |  | 13 | 1820 | 13 | 1820 |  | 128700 | 160875 | TOTAL |  | 83149.35 | 66519.48
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost

## MEERI
|  |  |  | 16600 | 1.25
|  |  |  | 10725 |  |  | 13406.25 | GreenOfshoreTech PARTNER NAME: MEERI
|  |  |  | 0 |  |  | 0 |  | WP/Task | Duration (M) | BUDGET |  |  | PM | Proposal of changes of PM (12.2022)
|  |  |  | 5005 |  |  | 6256.25 |  |  |  | Personnel Direct and Indirect | Proposal of changes (12.2022)
|  | TOTAL COSTS |  | 5720 |  |  | 7150 | Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 1-19 | 13406 | 13310.65 |  | 3.75 | 3.95
|  | Dir & Indir (EUR) |  | 1430 |  |  | 1787.5 | Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 1-6 | 0 | 384.3 |  | 0 | 0.1
|  | ACTUAL |  | 715 |  |  | 893.75 | Assessment of emerging technology trends and solutions | T1.2 | 1-6 | 6256 | 4373.14 |  | 1.75 | 1.9
GreenOfshoreTech PARTNER NAME: MEERI | Task/ | M1-M9 |  | 0 |  |  | 0 | Potential new value chains and selection of Call Topics | T1.3 | 1-19 | 7150 | 8553.21 |  | 2 | 1.95
| WP |  |  | 0 |  |  | 0 | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 1-36 | 1788 | 1110 |  | 0.5 | 0.35
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 8319.05 | 6655.24 | 715 |  |  | 893.75 | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1-36 | 894 | 760 |  | 0.25 | 0.25
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 307.44 | 245.952 | 18010 |  |  | 22512.5 | Establishment of a Collaborative Virtual Environment | T2.2 | 1-36 | 0
Assessment of emerging technology trends and solutions | T1.2 | 4060.45 | 3248.36 | 3430 |  |  | 4287.5 | Establishment of a Survey tool | T2.3 | 1-36 | 0
Potential new value chains and selection of Call Topics | T1.3 | 3951.16 | 3160.928 | 0 |  |  | 0 | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 1-36 | 894 | 350 |  | 0.25 | 0.1
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 1776.61 | 1421.288 | 5860 |  |  | 7325 | Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 1-36 | 12513 | 10105 |  | 3.5 | 2.8
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 1115.02 | 892.016 | 0 |  |  | 0 | Preparation of the Call for Proposals | T3.1 | 1-7 | 1788 | 1170 | -715 | 0.5 | 0.5
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 |  |  | 0 | Publication of the Call for Proposals and Proposal reception. | T3.2 | 8-18 | 0
Establishment of a Survey tool | T2.3 | 661.59 | 529.272 | 8720 |  |  | 10900 | Evaluation and Selection of SMEs Proposals | T3.3 | 11-20 | 3575 | 7865 |  | 1 | 2
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 0 | 15750 |  |  | 19687.5 | Contracting with winner SMEs Projects | T3.4 | 13-22 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 2131.5 | 1705.2 | 0 |  |  | 0 | Payments and financial monitoring of winner SMEs Projects | T3.5 | 13-36 | 0
Preparation of the Call for Proposals | T3.1 | 2131.5 | 1705.2 | 10290 |  |  | 12862.5 | Technical monitoring of winner SMEs Projects | T3.6 | 13-36 | 7150 | 1070 |  | 2 | 0.3
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 | 3030 |  |  | 3787.5 | Business Support Services to winner SMEs (preparation) | WP4 | 1-36 | 8938 | 5400 |  | 2.5 | 1.4
Evaluation and Selection of SMEs Proposals | T3.3 | 0 | 0 | 0 |  |  | 0 | Programme of Business Support Services to winner SMEs (prep) | T4.1 | 1-36 | 0 | 760 |  |  | 0.1
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | WP1 | 8319.05 | 0 | Business Support Service #1 Business & Tech Academy | T4.2 | 1-24 | 5363 | 2500 |  | 1.5 | 0.7
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | WP2 | 1776.61 | 0 | Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 1-24 | 1788 | 1070 |  | 0.5 | 0.3
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 | 0 | WP3 | 2131.5 | 0 | Business Support Service #3 Access to Finance | T4.4 | 1-24 | 0
Business Support Services to winner SMEs (preparation) | WP4 | 661.59 | 529.272 | 0 | WP4 | 661.59 | 0 | Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 1-32 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 661.59 | 529.272 | 2430 | WP5 | 1742.07 | 3037.5 | Business Support Service #5 Branding | T4.6 | 1-32 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 | 2145 | WP6 | 590.43 | 2681.25 | Business Support Service #6 Internationalisation | T4.7 | 1-32 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 | 715 | WP7 | 0 | 893.75 | Business Support Service #7 Investor pitching | T4.8 | 1-32 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 | 715 |  |  | 893.75 | Business Support Service #8 Investor rounds | T4.9 | 1-32 | 1787 | 1070 |  | 0.5 | 0.3
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 | 0 | 715 |  |  | 893.75 | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 1-36 | 2680 | 1772 |  | 0.75 | 0.5
Business Support Service #5 Branding | T4.6 | 0 | 0 | 2860 |  |  | 3575 | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 1-36 | 893 | 1072 |  | 0.25 | 0.3
Business Support Service #6 Internationalisation | T4.7 | 0 | 0 | 0 |  |  | 0 | Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 1-36 | 893 | 350 |  | 0.25 | 0.1
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 1430 |  |  | 1787.5 | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 35-36 | 894 | 350 |  | 0.25 | 0.1
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 | 1430 |  |  | 1787.5 | Communication, Dissemination, Exploitation & Sustainability | WP6 | 1-36 | 3575 | 2715 |  | 1 | 1
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 1742.07 | 1393.656 | 0 |  |  | 0 | Communication plan and Communication activities | T6.1 | 1-36 | 0
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 1742.07 | 1393.656 | 0 |  |  | 0 | Dissemination strategy and Dissemination activities | T6.2 | 1-36 | 1787.5 | 2000 |  | 0.5 | 0.8
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 | 0 | 0 |  |  | 0 | Exploitation strategy, IPR and Sustainability | T6.3 | 1-36 | 1787.5 | 715 |  | 0.5 | 0.2
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 | 0 | 0 |  |  | 0 | Project Management and Coordination | WP7 | 1-36 | 0 | 8487.35 |  | 0 | 2
Communication, Dissemination, Exploitation & Sustainability | WP6 | 590.43 | 472.344 | 50920 |  |  | 63650 | Project coordination | T7.1 | 1-36 | 0 | 3575 |  |  | 0.8
Communication plan and Communication activities | T6.1 | 0 | 0 |  |  |  |  | Project administration & Financial Management | T7.2 | 1-36 | 0 | 4912.35 |  |  | 1.2
Dissemination strategy and Dissemination activities | T6.2 | 590.43 | 472.344 |  |  |  |  | Quality Assurance | T7.3 | 1-36 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0 | 0 |  |  |  |  | TOTAL |  |  | 42900 | 42900 |  | 12 | 12
Project Management and Coordination | WP7 | 0 | 0
Project coordination | T7.1 | 0 | 0 |  |  |  |  | Other direct costs & Other goods and services including Indirect costs |  |  | 20750
Project administration & Financial Management | T7.2 | 0 | 0 |  |  |  |  | Budget total |  |  | 63650
Quality Assurance | T7.3 | 0 | 0
TOTAL |  | 15221.25 | 12177
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost

## MCN
[16 empty] | 1.25 | 31600
|  | TOTAL COSTS | [14 empty] | 8250 | 10312.5
|  | Dir & Indir (EUR) | Dir (EUR) |  | INCLDING IND COST |  | This calculation is done by MNU since MCN have not delivered the contribution to D7.5 | [9 empty] | 5500 | 6875
|  | ACTUAL |  |  |  |  | Cost is calculated based on PM3,37 delivered for D7.4 | [9 empty] | 1375 | 1718.75
GreenOfshoreTech TOTAL (Period M1 to M10) | Task/ | M1-M10 |  |  |  |  | Evsaryone is informed to calculate 1PM as 143.333 hours. | [9 empty] | 1375 | 1718.75
| WP | [5 empty] | Your budgeted hourly cost is than 35,47 Euro per hour. | [9 empty] | 2750 | 3437.5
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 7696.99 | 6157.592 | PM | 1.5 | 7696.99 | PM | 3.37 | [8 empty] | 1375 | 1718.75
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 6508.745 | 5206.996 |  |  | 6508.745 | Hourly rate | 35.47 | [8 empty] | 0 | 0
Assessment of emerging technology trends and solutions | T1.2 | 0 | 0 |  |  | 0 | Total hours |  | 483.03 | [7 empty] | 0 | 0
Potential new value chains and selection of Call Topics | T1.3 | 1188.245 | 950.596 |  |  | 1188.245 | [10 empty] | 1375 | 1718.75
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 565.24 | 452.192 | PM | 0.11 | 565.24 | Net cost total |  | 17133.0741 | [7 empty] | 21749 | 27186.25
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 559.24 | 447.392 |  |  | 559.24 | [10 empty] | 4649 | 5811.25
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 |  |  | 0 | 1PM | 143.333 | [8 empty] | 0 | 0
Establishment of a Survey tool | T2.3 | 6 | 4.8 |  |  | 6 | [10 empty] | 8550 | 10687.5
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 | 0 |  |  | 0 | In d7.4 it is reported PM3,37 and a cost of 22,402.00 and this is impossible for me to evaluate without your actual calculation. | [9 empty] | 0 | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 2898.055 | 2318.444 | PM | 0.45 | 2898.055 | [10 empty] | 0 | 0
Preparation of the Call for Proposals | T3.1 | 2004.055 | 1603.244 |  |  | 2004.055 | [10 empty] | 8550 | 10687.5
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 |  |  | 0 | [10 empty] | 56600 | 70750
Evaluation and Selection of SMEs Proposals | T3.3 | 894 | 715.2 |  |  | 894 | [10 empty] | 0 | 0
Contracting with winner SMEs Projects | T3.4 | 0 | 0 |  |  | 0 | [10 empty] | 10500 | 13125
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 |  |  | 0 | [10 empty] | 5250 | 6562.5
Technical monitoring of winner SMEs Projects | T3.6 | 0 | 0 |  |  | 0 | [5 empty] | MCN |  |  |  |  | 5250 | 6562.5
Business Support Services to winner SMEs (preparation) | WP4 | 1169.13 | 935.304 | PM | 0.22 | 1169.13 | [5 empty] | WP1 | 7696.99 | #REF! |  |  | 0 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 101 | 80.8 |  |  | 101 | [5 empty] | WP2 | 565.24 | #REF! |  |  | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 | 0 |  |  | 0 | [5 empty] | WP3 | 2898.055 | #REF! |  |  | 17000 | 21250
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 | 0 |  |  | 0 | [5 empty] | WP4 | 1169.13 | #REF! |  |  | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 | 0 |  |  | 0 | [5 empty] | WP5 | 1627 | #REF! |  |  | 18600 | 23250
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 39.5 | 31.6 |  |  | 39.5 | [5 empty] | WP6 | 620.725 | #REF! |  |  | 4125 | 5156.25
Business Support Service #5 Branding | T4.6 | 230.555 | 184.444 |  |  | 230.555 | [5 empty] | WP7 | 283.76 | #REF! |  |  | 1375 | 1718.75
Business Support Service #6 Internationalisation | T4.7 | 798.075 | 638.46 |  |  | 798.075 | [10 empty] | 1375 | 1718.75
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 |  |  | 0 | [10 empty] | 1375 | 1718.75
Business Support Service #8 Investor rounds | T4.9 | 0 | 0 |  |  | 0 | [10 empty] | 11000 | 13750
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 1627 | 1301.6 | PM | 0.82 | 1627 | [10 empty] | 2750 | 3437.5
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 1375 | 1100 |  |  | 1375 | [10 empty] | 5500 | 6875
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 25 | 20 |  |  | 25 | [10 empty] | 2750 | 3437.5
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 227 | 181.6 |  |  | 227 | [10 empty] | 0 | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 620.725 | 496.58 | PM | 0.22 | 620.725 | [10 empty] | 0 | 0
Communication plan and Communication activities | T6.1 | 514.315 | 411.452 |  |  | 514.315 | [10 empty] | 0 | 0
Dissemination strategy and Dissemination activities | T6.2 | 0 | 0 |  |  | 0 | [10 empty] | 0 | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 106.41 | 85.128 |  |  | 106.41 | [10 empty] | 104474 | 130592.5
Project Management and Coordination | WP7 | 283.76 | 227.008 | PM | 0.05 | 283.76
Project coordination | T7.1 | 0 | 0 |  |  | 0
Project administration & Financial Management | T7.2 | 0 | 0 |  |  | 0
Quality Assurance | T7.3 | 283.76 | 227.008 |  |  | 283.76
TOTAL |  | 14743.6624 | 11794.9299 | PM | 3.37 | 14743.6624
[14 empty] | AMD2 | AMD2
[14 empty] | For BUDGET | For 75% RULE
[9 empty] | ORG = | ORG = |  |  |  | Direct monthly rate | Direct monthly rate
[9 empty] | AMD1 | AMD1 | AMD2 | AMD2 | AMD2 | 9369.9806 | 9369.9806
[9 empty] | BUDGET | BUDGET | REVISION | REVISION |  | REVISION | REVISION
[8 empty] | Task/ |  |  | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT)
[8 empty] | WP | PM | hours | PMs | Hours |  | EUR | EUR
[7 empty] | Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 1.5 | 215 | 0 | 0 | OK | 0 | 0
[7 empty] | Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 1 | 143.3333 |  | 0 |  | 0 | 0
[7 empty] | Assessment of emerging technology trends and solutions | T1.2 | 0.25 | 35.8333 |  | 0 |  | 0 | 0
[7 empty] | Potential new value chains and selection of Call Topics | T1.3 | 0.25 | 35.8333 |  | 0 |  | 0 | 0
[7 empty] | Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 0.5 | 71.6667 | 0 | 0 | Ok | 0 | 0
[7 empty] | Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0.25 | 35.8333 |  | 0 |  | 0 | 0
[7 empty] | Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Establishment of a Survey tool | T2.3 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0.25 | 35.8333 |  | 0 |  | 0 | 0
[7 empty] | Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 2.5 | 358.3333 | 0 | 0 | ok | 0 | 0
[7 empty] | Preparation of the Call for Proposals | T3.1 | 0.5 | 71.6667 |  | 0 |  | 0 | 0
[7 empty] | Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Evaluation and Selection of SMEs Proposals | T3.3 | 1 | 143.3333 |  | 0 |  | 0 | 0
[7 empty] | Contracting with winner SMEs Projects | T3.4 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Technical monitoring of winner SMEs Projects | T3.6 | 1 | 143.3333 |  | 0 |  | 0 | 0
[7 empty] | Business Support Services to winner SMEs | WP4 | 6 | 860 | -0.1 | -14.3333 | minus 0,1 PM | -936.998 | -1171.2475
[7 empty] | Programme of Business Support Services to winner SMEs | T4.1 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Business Support Service #1 Business & Tech Academy | T4.2 | 1 | 143.3333 |  | 0 |  | 0 | 0
[7 empty] | Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0.5 | 71.6667 |  | 0 |  | 0 | 0
[7 empty] | Business Support Service #3 Access to Finance | T4.4 | 0.5 | 71.6667 |  | 0 |  | 0 | 0
[7 empty] | Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Business Support Service #5 Branding | T4.6 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Business Support Service #6 Internationalisation | T4.7 | 2 | 286.6667 | -0.1 | -14.3333 | minus 0,1 PM | -936.998 | -1171.2475
[7 empty] | Business Support Service #7 Investor pitching | T4.8 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Business Support Service #8 Investor rounds | T4.9 | 2 | 286.6667 |  | 0 |  | 0 | 0
[7 empty] | Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0.75 | 107.5 | 0 | 0 | OK | 0 | 0
[7 empty] | Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0.25 | 35.8333 |  | 0 |  | 0 | 0
[7 empty] | Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 0.25 | 35.8333 |  | 0 |  | 0 | 0
[7 empty] | Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0.25 | 35.8333 |  | 0 |  | 0 | 0
[7 empty] | Communication, Dissemination, Exploitation & Sustainability | WP6 | 2 | 286.6667 | 0 | 0 | ok | 0 | 0
[7 empty] | Communication plan and Communication activities | T6.1 | 0.5 | 71.6667 |  | 0 |  | 0 | 0
[7 empty] | Dissemination strategy and Dissemination activities | T6.2 | 1 | 143.3333 |  | 0 |  | 0 | 0
[7 empty] | Exploitation strategy, IPR and Sustainability | T6.3 | 0.5 | 71.6667 |  | 0 |  | 0 | 0
[7 empty] | Project Management and Coordination | WP7 | 0 | 0 | 0.1 | 14.3333 | plus 0.1 PM | 936.998 | 1171.2475
[7 empty] | Project coordination | T7.1 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Project administration & Financial Management | T7.2 | 0 | 0 |  | 0 |  | 0 | 0
[7 empty] | Quality Assurance | T7.3 | 0 | 0 | 0.1 | 14.3333 | plus 0,1 PM | 936.998 | 1171.2475
[7 empty] | NOTE: Key Tasks to be marked light green |  | 13.25 | 1899.1667 | 0 | 0 |  | 0 | 0
See below.

## CKR
TOTAL COSTS
|  | Dir & Indir (EUR) |  | Dir (EUR) |  | INCLDING IND COST |  |  | This calculation is done by MNU since CKR have not delivered the contribution to D7.5
|  | ACTUAL | [6 empty] | Cost is calculated based on PM7,19 delivered for D7.4
GreenOfshoreTech TOTAL (Period M1 to M10) | Task/ | M1-M10 | [6 empty] | Everyone is informed to calculate 1PM as 143.333 hours.
WP
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 4376.13 |  | 3500.904 | PM | 1 | 3505.9252 |  | PM | 3.37
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 1596.86 |  | 1277.488 |  |  |  |  | Hourly rate | 24.46 | Per your budget
Assessment of emerging technology trends and solutions | T1.2 | 1350 |  | 1080 |  |  |  |  | Total hours |  | 1030.56
Potential new value chains and selection of Call Topics | T1.3 | 1429.27 |  | 1143.416
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 6573.6097 |  | 5258.8878 | PM | 1.5 |  |  | Net cost total |  | 25207.4976
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0 |  | 0
Establishment of a Collaborative Virtual Environment | T2.2 | 0 |  | 0 |  |  |  |  | 1PM | 143.333
Establishment of a Survey tool | T2.3 | 6573.61 |  | 5258.888
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0 |  | 0
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 19720.8291 |  | 15776.6633 | PM | 4.5
Preparation of the Call for Proposals | T3.1 | 19720.83 |  | 15776.664
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 |  | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 0 |  | 0
Contracting with winner SMEs Projects | T3.4 | 0 |  | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 |  | 0
Technical monitoring of winner SMEs Projects | T3.6 | 0 |  | 0 | [7 empty] | MCN
Business Support Services to winner SMEs (preparation) | WP4 | 0 |  | 0 | PM | 0 | [5 empty] | WP1 | 4376.13 | 0
Programme of Business Support Services to winner SMEs (prep) | T4.1 | 0 |  | 0 | [7 empty] | WP2 | 6573.6097 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 0 |  | 0 | [7 empty] | WP3 | 19720.8291 | 0
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0 |  | 0 | [7 empty] | WP4 | 0 | 0
Business Support Service #3 Access to Finance | T4.4 | 0 |  | 0 | [7 empty] | WP5 | 438.2406 | 0
Business Support Service #4 One-to-One Mentoring and Coaching (prep) | T4.5 | 0 |  | 0 | [7 empty] | WP6 | 394.4166 | 0
Business Support Service #5 Branding | T4.6 | 0 |  | 0 | [7 empty] | WP7 | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0 |  | 0
Business Support Service #7 Investor pitching | T4.8 | 0 |  | 0
Business Support Service #8 Investor rounds | T4.9 | 0 |  | 0
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 438.2406 |  | 350.5925 | PM | 0.1
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 438.24 |  | 350.592
Validation & Impact assessment of GreenOffshoreTech LSD (data collection) | T5.2 | 0 |  | 0
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0 |  | 0
Communication, Dissemination, Exploitation & Sustainability | WP6 | 394.4166 |  | 315.5333 | PM | 0.09
Communication plan and Communication activities | T6.1 | 398.1 |  | 318.48
Dissemination strategy and Dissemination activities | T6.2 | 0 |  | 0
Exploitation strategy, IPR and Sustainability | T6.3 | 0 |  | 0
Project Management and Coordination | WP7 | 0 |  | 0 | PM | 0
Project coordination | T7.1 | 0 |  | 0
Project administration & Financial Management | T7.2 | 0 |  | 0
Quality Assurance | T7.3 | 0 |  | 0
TOTAL |  | 31503.2261 |  | 25202.5809 | PM | 7.19
[7 empty] | AMD2 | AMD2
[7 empty] | For BUDGET | For 75% RULE
|  | ORG = | ORG = |  |  |  | Direct monthly rate | Direct monthly rate
|  | AMD1 | AMD1 | AMD2 | AMD2 | AMD2 | 3498.6 | 3498.5
|  | BUDGET | BUDGET | REVISION | REVISION |  | REVISION | REVISION
| Task/ |  |  | TOTAL | TOTAL | COMMENT | Personnel costs (DIRECT only) | Personnel costs (DIRECT & INDIRECT)
| WP | PM | hours | PMs | Hours |  | EUR | EUR
Assessment of potential new value chains and selection of Topics for Call of Proposals | WP1 | 3.25 | 465.8333 | 2.25 | 322.5 | Minus 1 PM | 7871.85 | 9839.8125
Sustainable challenges, needs and trends of four industrial offshore sectors | T1.1 | 0.25 | 35.8333 | 0.25 | 35.8333 | Ok. | 874.65 | 1093.3125
Assessment of emerging technology trends and solutions | T1.2 | 1 | 143.3333 | 1 | 143.3333 | Ok. | 3498.6 | 4373.25
Potential new value chains and selection of Call Topics | T1.3 | 2 | 286.6667 | 1 | 143.3333 | minus 1 PM (shift to WP7) | 3498.6 | 4373.25
Methodologies and tools for cross-sectoral/-border collaboration and technology transfer | WP2 | 2 | 286.6667 | 1.5 | 215 | minus 0,5 PM | 5249.75 | 6562.1875
Methologies and tools for cross-sectoral/-border collaboration and technology transfer | T2.1 | 0.75 | 107.5 | 0.5 | 71.6667 | minus 0,25 PM (SHIFT to WP7) | 1749.3 | 2186.625
Establishment of a Collaborative Virtual Environment | T2.2 | 0 | 0 | 0 | 0 | ok | 0 | 0
Establishment of a Survey tool | T2.3 | 1 | 143.3333 | 0.75 | 107.5 | minus 0,25 PM (SHIFT to WP7) | 2623.95 | 3279.9375
Establishment of the GreenOffshoreTech Cluster Collaboration Platform | T2.4 | 0.25 | 35.8333 | 0.25 | 35.8333 | ok | 876.5 | 1095.625
Direct financial support to SMEs through a competitive Call for Proposals | WP3 | 6 | 860 | 5.5 | 788.3333 | Minus 0,5 PM | 19264.5 | 24080.625
Preparation of the Call for Proposals | T3.1 | 3 | 430 | 3 | 430 | Ok. | 10518 | 13147.5
Publication of the Call for Proposals and Proposal reception. | T3.2 | 0 | 0 | 0 | 0 | Ok. | 0 | 0
Evaluation and Selection of SMEs Proposals | T3.3 | 1 | 143.3333 | 1 | 143.3333 | Ok. | 3498.6 | 4373.25
Contracting with winner SMEs Projects | T3.4 | 0 | 0 | 0 | 0 | Ok. | 0 | 0
Payments and financial monitoring of winner SMEs Projects | T3.5 | 0 | 0 | 0 | 0 | Ok. | 0 | 0
Technical monitoring of winner SMEs Projects | T3.6 | 2 | 286.6667 | 1.5 | 215 | minus 0,5 PM (SHIFT to WP7) | 5247.9 | 6559.875
Business Support Services to winner SMEs | WP4 | 3 | 430 | 3 | 430 |  | 10495.8 | 13119.75
Programme of Business Support Services to winner SMEs | T4.1 | 0 | 0 | 0 | 0 | Ok. | 0 | 0
Business Support Service #1 Business & Tech Academy | T4.2 | 1 | 143.3333 | 1 | 143.3333 | Ok. | 3498.6 | 4373.25
Business Support Service #2 Brokerage & B2B matchmaking events | T4.3 | 0.5 | 71.6667 | 0.5 | 71.6667 | Ok. | 1749.3 | 2186.625
Business Support Service #3 Access to Finance | T4.4 | 0.5 | 71.6667 | 0.5 | 71.6667 | Ok. | 1749.3 | 2186.625
Business Support Service #4 One-to-One Mentoring and Coaching (prep + service) | T4.5 | 0 | 0 | 0 | 0 | Ok. | 0 | 0
Business Support Service #5 Branding | T4.6 | 0 | 0 | 0 | 0 | Ok. | 0 | 0
Business Support Service #6 Internationalisation | T4.7 | 0.5 | 71.6667 | 0.5 | 71.6667 | Ok. | 1749.3 | 2186.625
Business Support Service #7 Investor pitching | T4.8 | 0 | 0 | 0 | 0 | Ok. | 0 | 0
Business Support Service #8 Investor rounds | T4.9 | 0.5 | 71.6667 | 0.5 | 71.6667 | Ok. | 1749.3 | 2186.625
Large-scale Demonstrator (LSD) setup, validation, and impact assessment | WP5 | 0.75 | 107.5 | 0.75 | 107.5 |  | 2623.95 | 3279.9375
Set-up of the GreenOffshoreTech LSD in GreenOffshoreTech regions | T5.1 | 0.25 | 35.8333 | 0.25 | 35.8333 | Ok. | 874.65 | 1093.3125
Validation & Impact assessment of GreenOffshoreTech LSD (data collection & analysis) | T5.2 | 0.25 | 35.8333 | 0.25 | 35.8333 | Ok. | 874.65 | 1093.3125
Guidelines of Best Practice to foster cross-sector/-border collaboration and technology transfer through Clusters | T5.3 | 0.25 | 35.8333 | 0.25 | 35.8333 | Ok. | 874.65 | 1093.3125
Communication, Dissemination, Exploitation & Sustainability | WP6 | 2 | 286.6667 | 2 | 286.6667 |  | 6997.2 | 8746.5
Communication plan and Communication activities | T6.1 | 0.5 | 71.6667 | 0.5 | 71.6667 | OK. | 1749.3 | 2186.625
Dissemination strategy and Dissemination activities | T6.2 | 1 | 143.3333 | 1 | 143.3333 | OK. | 3498.6 | 4373.25
Exploitation strategy, IPR and Sustainability | T6.3 | 0.5 | 71.6667 | 0.5 | 71.6667 | OK. | 1749.3 | 2186.625
Project Management and Coordination | WP7 | 0 | 0 | 2 | 286.6667 |  | 6997.2 | 8746.5
Project coordination | T7.1 | 0 | 0 | 1 | 143.3333 | plus 1 PM | 3498.6 | 4373.25
Project administration & Financial Management | T7.2 | 0 | 0 | 1 | 143.3333 | plus 1 PM | 3498.6 | 4373.25
Quality Assurance | T7.3 | 0 | 0 | 0 | 0 | OK | 0 | 0
NOTE: Key Tasks to be marked light green |  | 17 | 2436.6667 | 17 | 2436.6667 |  | 59500.25 | 74375.3125
Table to the right is active as partner input to sheet Direct & Indirect Personnal Cost
YOUR BUDGETE NUMBERS: Column C is budgeted PM, column D is hours is assuming 1720 or 1 PM=143.333
COMPLETE COLUMN E TIL I for the AMD2
According to your re-allocation and salary cost.